CIP Ref	Pg in CIP	CIP Action	Deadline	Theme	SBUHB Delivery Update, July 2024	SBUHB Delivery Update, January 2025
8b.c	29	Health Boards and Trusts to work towards developing stratified prehabilitation services, in line with the National Prehabilitation Standards, for all cancer patients through the IMTP process, and will ensure that prehabilitation service models meet individual and population requirements.	March 2024	Earlier Diagnosis: Health Optimisation/Prehabilitation	Currently deliver thoracic surgery physiotherapy prehab via Joint Commissioning Committee funding. / To go live with colorectal surgical multi-professional prehabilitation in September. / All patients have access to Maggie’s prehabilitation offer. Also Alvie Health. / All SBUHB patients accessing Rapid Diagnostic Clinic are offered universal prehabilitation via the prehabilitation pharmacist. / All patients on a Suspected Cancer pathway will get access to universal E-learning (under development)	Currently deliver thoracic surgery physiotherapy prehab via Joint Commissioning Committee funding. / Went live with colorectal surgical multi-professional prehabilitation in September 2025. Looking to roll out to colorectal oncological treatment, before rolling out to other tumour sites. Planning underway. / All patients have access to Maggie’s Universal prehabilitation offer. / All SBUHB patients accessing Rapid Diagnostic Clinic are offered universal prehabilitation via the prehabilitation pharmacist for 3 clinics per week, over 52 weeks. / All patients on a Suspected Cancer pathway will get access to universal E-learning (under development) / Patients on a USC pathway with be offered an interactive universal webinar (under development) / All patients being referred into secondary care will be medically optimised at the earliest convenience, including frailty review (campaign in development) / All patients on a USC pathway will be medically optimised, plus a frailty review, earlier than is currently happening (campaign in development
9d	31	Each Health Board is to establish and sustain a Rapid Diagnosis Clinic access for their population to see patients with vague, non-specific symptoms suspicious of cancer and report waiting times, in accordance with the nationally endorsed National Optimal Pathway and Service Specification, within the Single Cancer Pathway.	March 2023	Faster Diagnosis	Complete - All Health Boards across Wales have an up-and-running Rapid Diagnosis Clinic service, in accordance with the Vague Symptoms NOP. / Note:- SBUHB Malignancy of Unknown Origin/Cancer of Unknown Primary Service have been nominated for an All Wales Award.	COMPLETE IN 24/25
10a	36	Health Boards to plan and deliver recovery and improvement trajectories on a sustainable basis including training and recruitment of staff and use of Business Intelligence to analyse demand and capacity. This should be ongoing, but a comprehensive assessment should form part of Health Board and Trust IMTPs.	March 2023	Elective Care Recovery	Complete - Improvement trajectories shared with WG as part of the monthly monitoring.	COMPLETE IN 24/25
10e	36	The Planned Care Improvement and Recovery Team and All Wales Teledermoscopy Group to work with and support Health Boards to establish teledermoscopy services for their populations with the target of reducing dermatology outpatient waiting list volumes by 30% within the first 18 months.	March 2024	Elective Care Recovery	The Health Board has recently undergone a Skin Peer Review and an action plan in place. Teledermoscopy for non-USC referrals with in-house reporting.	During Jan- Dec 2024, dermatology received 9492 referrals, 2046 were triaged to teledermatology (21.6%). The department are currently undertaking a holistic review of the service as further consultant sessions will be needed to increase capacity within the teledermatology service.
12b.a	45	Wales Cancer Network to work with Health Boards to launch a Patient Alert App for cancer patients undergoing treatment by end of March 2024. Longer term: Wales Cancer Network and Digital Health and Care Wales to explore linking the app to the Welsh Clinical Portal.	March 2024	Effective Treatments: SACT	Currently on the Cancer Network workplan. Funding identified through Industry partners through Collaborative working agreement. Currently, addressing barriers with finance to progress.	WCN Delivery
12b.b	45	Wales Cancer Network and Health Boards and Trusts to undertake an assessment of 24-hour advice and triage services, making recommendations for a safe accessible service for SACT providers and Unscheduled Care services across Wales. Once the recommendations paper is written Wales Cancer Network will facilitate national collaboration to identify what the models could be moving forward as well as developing a service specification.	March 2023	Effective Treatments: SACT	Currently on the Cancer Network workplan for completion in 2024/25. / SBUHB and HDD have a lead Advanced Nurse Practitioner in place for the Acute Oncology Service. Initiated quarterly Triage review meetings with both HB’s (first meeting July 2024)	Completed 2024
12b.e	46	Health Board and Trust SACT services to capture data in line with the National Cancer Data Standards for Wales and agreed Quality Performance Indicators. These will start with reporting of 30 day mortality after SACT treatment and time from decision to treat to treatment in line with the SCP.	March 2023	Effective Treatments: SACT	Data within ePMA systems will be extracted by DHCW and a dashboard produced to report the Quality Performance Indicators. First sample of data has been collected for data quality review.	COMPLETED IN 24/25
12c.b	47	Health Boards and Trusts to report against the Time to Radiotherapy metrics developed through COSC by end of March 2023 and look to develop mortality and morbidity reporting during 2023.	December 2023	Effective Treatments: Radiotherapy	Currently on the Cancer Network workplan for completion in 2024/25 / Regular reporting in place for both metrics through the Quality Metrics Subgroup of Cancer Outcomes Service Committee. In SBUHB these are reported to the Cancer Programme and Improvement Group and now requested to Executive Team at Targeted Intervention meetings.	COMPLETED IN 24/25
12c.c	48	Health Boards and Trusts hosting Radiotherapy Centres to ensure equitable access to hypofractionation.	September 2023	Effective Treatments: Radiotherapy	Currently on the Cancer Network workplan for completion in 2024/25 / Prostate and Breast hypofractionation available as routine. SABR implementation in South West Wales Cancer Centre (SWWCC) successful in lung and continuing to all commissioned tumour sites as planned with Liver SABR in SWWCC due this month.	COMPLETED IN 24/25
12c.g	48	Health Boards and Trusts hosting Radiotherapy Centres to begin capturing data in line with the RTDS and the agreed QPIs.	March 2023	Effective Treatments: Radiotherapy	Currently on the Cancer Network workplan for completion in 2024/25 / SBUHB have been collecting RTDS data for many years and are the test site for next version.	COMPLETED IN 24/25
12d.a	50	Wales Cancer Network to develop a national Acute Oncology Service Specification collaboratively with Health Boards which will be available for consultation by end of March 2023, and which will also align with the Welsh Government Six Goals for Urgent and Emergency Care.	March 2023	Effective Treatments: AOS	Completed - March 2024	COMPLETED IN 24/25
12d.c	50	Health Boards and Trusts to establish services in line with the national Acute Oncology Service Specification.	March 2024	Effective Treatments: AOS	Acute Oncology Service Clinical Lead and Advanced Nurse Practitioner in place for Acute Oncology Service. Implementation of full service specification at risk due to reassignment of staff to cover Acute Oncology and Haematology Assessment Unit at Singleton Hospital. Immuno-oncology toxicity service business case in development with HDD (and support of industry partners) SBUHB baseline data submitted to All Wales Acute Oncology Service. Service is currently compiling excel action tracker to identify timeline and resource required to match Acute Oncology Service minimum standards.	AOS Service Specification reviewed as part of the All Wales Group. Ongoing staff shortages due to sickness as well as cover of multiple clinical areas (not currently funded) does not allow for consistent cover of full acute oncology service. Provision of other services within the AOS specification in development. South Wales MSCC pathway commenced in the last year to provide consistent care in this patient group. / Immunotherapy Service Business Case still in development with weekly IO toxicity discussion meetings now established with other clinical specialities.
12e.f	56	Welsh Health Specialist Services Committee to take over the commissioning of both hepatic and pancreatic surgery following work led by the provider, with Health Boards to agree a future clinical model. It is anticipated that a recommendation on the future model will be submitted to WHSSC by end of June 2023. Depending on the nature of the recommendation a period of public consultation on the proposed future model may then be required.	June 2023	Effective Treatments: Specialist/tertiary service configuration and sustainability	Ongoing discussion with regards to OG Cancer. Executive and HPB Consultant representatives for SBUHB at Regional Meetings.	Discussions being led by the Joint Commissioning Committee
14a.d	63	Health Boards to develop action plans by end of March 2023 to address the findings of the Wales Macmillan Cancer Patient Experience Survey (CPES) which will be monitored at a national level by the Wales Cancer Network. Health Boards to track their Board’s performance against their CPES action plans through their Quality and Safety Committees or equivalent.	March 2023	Improving Patient Experience: Co-production of Care	Completed / Cancer Patient Experience Group established – meet quarterly.	COMPLETED IN 24/25
14b.c	65	Wales Cancer Network to work with Health Boards to launch a Health and Wellbeing information website and application for cancer patients by end of March 2024. Longer term, Wales Cancer Network and Digital Health and Care Wales to explore linking the application to the National Digital platforms.	March 2024	Improving Patient Experience: Assessing and meeting people’s needs	Currently on the Cancer Network workplan for completion in 2024/25	WCN Delivery
14b.e	65	Wales Cancer Network, Planned Care Improvement and Recovery Team and Health Boards and Trusts to deliver an online platform to enable self-management for prostate cancer patients.	March 2024	Improving Patient Experience: Assessing and meeting people’s needs	Urology Clinical Nurse Specialists are leading on implementing stratified follow up for Prostate patients. Business case in progress for Band 4 support.	Prostate follow up - continuing to use the Swansea Bay Patient Portal (previously known as Patient Knows Best - PKB) for self-management and virtual prostate follow up service. There are IT issues associated with My Medical Record. / Business Case for band 4 support in progress.
14b.f	65	Health Boards to be able to demonstrate that patients have had an opportunity to discuss any unmet needs, through the use of supportive conversations and patient needs assessment tools.	March 2024	Improving Patient Experience: Assessing and meeting people’s needs	Macmillan electronic Holistic Needs Assessment increased in tumour groups where Clinical Nurse Specialists Co-Ordinator in post. Monitored through Cancer Patient Experience Group.	COMPLETED IN 24/25
14b.g	65	Health Boards to ensure that all patients have access to Health and Wellbeing information.	March 2024	Improving Patient Experience: Assessing and meeting people’s needs	All Cancer patients have a Maggie’s Universal Prehabilitation offer.	COMPLETED IN 24/25
14b.h	65	Health Boards to have processes in place to develop electronic treatment summaries for every patient.	March 2024	Improving Patient Experience: Assessing and meeting people’s needs	SBUHB interface to add summary PDF to Welsh Clinical Portal(WCP) patient records to meet this requirement is currently in testing. Implementing RT and SACT treatment summaries onto WCP (latter being User Accepter Testing with DHCW). Pilot for patient treatment summaries to WCP and GP via Health Forms completed with Macmillan GP. Barriers exist to full routine implementation. / Workstream within Cancer Patient Experience Group.	User accepting testing for SACT and Radiotherapy summary software being written to develop data extract. / Aiming to go live Q1
14b.i	65	Health Boards to ensure that all patients have access to a cancer Key Worker.	March 2024	Improving Patient Experience: Assessing and meeting people’s needs	Clinical Nurse Specialists (CNS) (and key workers) are currently not in place for non-melanoma skin for Oncology and identified on risk register. CNS workforce paper completed on hold in current financial climate. There is a CNS in each tumour group except Skin. Cancer Services is leading on mitigating the risk and business case development.	Added to the skin peer review action plan. / Business case in progress awaiting funding opportunity
14c.a	66	Wales Cancer Network will work with Health Boards, Trusts and the Third Sector to provide better co-ordinated access for all patients to information and advice on welfare benefits. Health Boards to ensure that all patients diagnosed with cancer have the opportunity to be referred for welfare benefits advice, and to engage with the Third Sector regarding promotional activity/publicity. The impact of referral to welfare benefits advice will be evaluated through PREMs.	September 2023	Improving Patient Experience: Signposting to emotional support, benefits advice and other holistic services	Currently on the Cancer Network workplan for completion in 2024/25	WCN Delivery
15a.b	69	Health Education and Improvement Wales and Wales Cancer Network to work jointly and collaboratively with Health Boards to take forward reviewing the workforce issues along specific cancer pathways and to agree the programme of work to implement actions for priority areas.	March 2023	Key System Wide Enablers: Workforce	Currently on the Cancer Network workplan for completion in 2024/25	WCN Delivery
15b.g	73	Health Boards and Trusts to capture data required for the five national cancer audits and core data for all tumour sites as well as data required for Peer Review and the Quality Frameworks guided by Healthcare Quality Improvement Partnership (HQIP) and Cancer Site or Service Groups.	December 2023	Key System Wide Enablers: Information and Intelligence	Complete - all audits are reported annually.	COMPLETED IN 24/25
15d.a	78	Heath Board and Trust Innovation leads, Life Sciences Hub Wales, and Wales Cancer Network, through its Clinical Reference Group in particular, will work in partnership with a range of organisations to assess and create innovation opportunities, and encourage the establishment of a specific cancer innovation fund.	March 2024	Key System Wide Enablers: Innovation	Ongoing through Ministerial innovation initiative.	COMPLETED IN 24/25
15d.f	78	Heath Boards, Trusts and partners (e.g. LSH, HTW) will work together, facilitated by the Wales Cancer Network, to develop a route-map to prepare for the rapid national adoption of appropriately evidenced innovations for cancer.	March 2024	Key System Wide Enablers: Innovation	Ongoing through Ministerial innovation initiative.	COMPLETED IN 24/25