| Meeting Date | 27 March 2026 |  | Agenda Item |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Health Board In-Committee |  |  |  |  |  |  |
| Report Title | Western Bay Drug and Alcohol Services- Contract Award for Generic Prescribing Services |  |  |  |  |  |  |
| Report Author | Hannah Roan, Assistant Director of Planning & Partnerships |  |  |  |  |  |  |
| Report Sponsor | Marie Davies, Executive Director of Planning & Partnerships |  |  |  |  |  |  |
| Presented by | Hannah Roan, Assistant Director of Planning & Partnerships |  |  |  |  |  |  |
| Freedom of Information | Closed |  |  |  |  |  |  |
| Purpose of the Report | This report seeks approval to award the contract for Generic Prescribing Services as part of the implementation of the Western Bay Area Planning Board (WBAPB) for drug and alcohol services. |  |  |  |  |  |  |
| Key Issues | Drug and alcohol services for the population of Swansea Bay Health Board (SBUHB) are planned and commissioned via the Western Bay Area Planning Board (APB). A programme is in place to transform drug and alcohol services in line with the recommendations from the Drugs Commission Report. The focus of the programme is to adopt an alliance-based commissioning model to create a whole system approach. A key part of the whole system approach is to transform the clinical provision to ensure effective clinical service delivery to citizens. The Criminal Justice (CJ) commissioned clinical services contract will come to an end on 31st March 2026, and there will be a requirement to ensure individuals who are clinically prescribed as part of this de-commissioned Criminal Justice services contract, receive ongoing clinical treatment for their substance use need. Therefore, this paper seeks approval to award the contract from 1st April 2026 using the ‘Most Suitable Provider’ procurement route. |  |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☐ | ☒ |  |
| Recommendations | Members are asked to: - APPROVE sub-contracting of clinical Criminal Justice Services to Kaleidoscope via ‘most suitable provider’ procurement route |  |  |  |  |  |  |

WESTERN BAY Drug and Alcohol Services Update- Contract Award for Generic Prescribing Services

- INTRODUCTION

This report seeks approval to award the contract for Generic Prescribing Services as part of the implementation of the Western Bay Area Planning Board (WBAPB) for drug and alcohol services.

- BACKGROUND

Area Planning Boards (APBs) were established in 2010 as part of the new arrangements to deliver the Welsh Government Substance Misuse Strategy ‘Working Together to Reduce Harm’. The APBs were intended to provide a regional framework, to:

- Strengthen partnership working and strategic leadership in the delivery of the substance misuse strategy; and,

- Enhance and improve the key functions of planning, commissioning and performance management.

WBAPB’s members include Neath Port Talbot County Borough Council, Swansea City and County Council, Swansea Bay University Health Board, His Majesty’s Prison and Probation Service Wales, Police and Crime Commissioner for South Wales, South Wales Police and HM Fire and Rescue.  A member of the Substance Misuse Team from Welsh Government also sits on the APB in an advisory capacity.  The Health Board’s Executive Director of Planning & Partnerships is the current chair of the APB meetings.

Currently, substance use services across Swansea Bay are delivered under the umbrella term ‘Newid’ consisting of statutory and third sector agencies delivering drug and alcohol services. Clinical services include:

- Community Drug and Alcohol Team (CDAT), SBUHB service for individuals requiring medical assistance for their alcohol and/or drug use.  (MHLDSG).

- Low Threshold Prescribing Service (Neath Port Talbot), managed by CDAT, (MHLDSG).

- Primary Care Substance Abuse Liaison Team (PSALT), low threshold prescribing primarily in Swansea (PCTSG).

- A small number of Swansea GP practices (four) continue to prescribe under historic shared care arrangements (PCTSG).

- Community Pharmacy Supervised Administration of Medicines – Substance Use (PCTSG).

- Substance Use Pathway for Oral Health into Community Dental Service (PCTSG).

A transformation programme is in place whereby an alliance-based commissioning model will replace the historic arrangements of a range of contracts being in place between the APB partners and various providers.  The alliance model brings together non-clinical and clinical services, to create a whole system approach.

2.1 Clinical Services

A new clinical services model has been co-designed through stakeholder workshops, including individuals with lived experience. The vision is for all clinical services to be delivered by SBUHB under the alliance. The clinical pathway for Western Bay Alliance is outlined in Appendix 1.

While the alliance will formally commence on 1st April 2026, full implementation will take several years and require significant transformation, including introducing GP shared care arrangements.

The most immediate change for SBUHB will be assuming responsibility for clinical services within Criminal Justice settings from 1 April 2026. These services, currently commissioned by the Office of the Police and Crime Commissioner (OPCC) and His Majesty’s Probation Service, will transfer to the alliance funding pool and be allocated to SBUHB.

In order to take on these services, the options available to the HB are to maintain current service provision through sub-contracting arrangements or to TUPE existing staff over to the HB.  In the long term centralising the service within the HB would also help ensure a consistent and equitable approach for this client group as a fragmented service risks the clients disengaging from treatment, increasing the risks of reoffending.  Transition between services is an area of concern that has been identified in the Drugs Commission Report.

However, there would also be significant risks if staff were to be transferred into the HB:

- Current staff are already expressing concerns about being transferred over to the HB.  There is a risk that the staff may seek alternative employment before the alliance is fully operational which would leave a resource gap for the HB to manage.

- External legal advice may need to be sought to ensure that appropriate TUPE process are followed which comes at a cost.

- On-costs for HB staff tend to be higher than for those employed by independent providers therefore, it may cost more for the HB to provide the service.  SBUHB would need to be assured that the clinical model is properly costed to reflect real service delivery costs.  The HB cannot afford to take on delivery of a service that is not sufficiently funded.

- OPCC and HMMPS have already right‑sized the service to align with the reduced budget that will transfer to the alliance. It would be prudent to assess how this revised model operates in practice, and confirm that the service has been appropriately right‑sized, before committing to the transfer of staff.

To maintain continuity and avoid any service disruption from 1 April 2026, sub‑contracting was considered the least‑risk option for the HB at this stage. Given that the HB must assume responsibility for the service from this date, there was insufficient time to complete all necessary workforce processes required to TUPE staff from the incumbent provider into the HB.

In addition, the HB currently has limited visibility of how the existing service operates, including its compliance with statutory requirements such as Drug Rehabilitation Requirements (DRRs) and Alcohol Treatment Requirements (ATRs). These orders must commence as soon as possible following a court appearance and no later than 10 working days after a Community Order is imposed, placing clear operational and statutory expectations on the service to respond rapidly.

On this basis, sub‑contracting provides a stable and pragmatic interim mechanism that safeguards continuity, supports statutory compliance, and allows the HB time to gain the necessary assurance and understanding of service operations before considering longer‑term delivery arrangement.

It is proposed that the HB commissions the incumbent provider Kaleidoscope to continue to deliver the clinical prescribing service for Criminal Justice Services.  Advice from Head of Procurement was a formal tender process is not required and the ‘most suitable provider’ route could be followed on the basis that:

- The market was tested in September 2025 for a drug and alcohol prescribing service for primary care (PSALT).  Kaleidoscope won the award on the basis that the tender achieved an exceptionally high score plus they were the only bidder.

- Kaleidoscope are already the incumbent provider of the service as part of the Dyfodol Consortia (which will no longer exist from 1st April 2026).

- Kaleidoscope is already an alliance partner, having secured the third‑sector services contract. Commissioning from within the existing alliance structure strengthens strategic alignment, reinforces the shared delivery model, and maximises the value of the collaboration agreement and ten‑year contract. This approach supports coherence, reduces transactional complexity, and ensures that commissioning decisions directly reinforce the alliance’s long‑term strategic intent.

SBUHB will be given an additional £774,953.91 to commission a service that delivers to those currently in receipt of clinical treatment via the Criminal Justice commissioned service. A copy of the specification is included in Appendix 1 of this report. The costing includes consideration of the numbers in the service, plus allowing for 20% potential increases to allow for flexibility and includes cost of medication in total value of contract. Medication not covered by the contract is Buvidal as these costs will be met through current APB Buvidal ring fenced funding that is provided by Welsh Government.  Appropriate controls will be put in place to manage any financial risk from these arrangements.

As the service has historically been commissioned by OPCC and HMMPS, the Health Board has not previously had direct oversight of Kaleidoscope’s clinical governance arrangements. Transitioning to direct commissioning will provide the Health Board with significantly greater control over the clinical quality, assurance processes, and governance of the service from 1 April 2026. Robust contract monitoring and performance‑management mechanisms will be established to ensure value for money, strengthen accountability, and safeguard the quality and safety of service delivery.

Management Board are asked to approve the recommendation that the Health Board commissions Kaleidoscope.

There is less urgency for the remaining clinical services that come under the responsibility of the Health Board as work will need to take place between the Health Board’s clinical team and the non-clinical services arm of the alliance to work through pathways including entry and exit points to ensure a fully integrated service for the citizens of Swansea and Neath Port Talbot.

The commissioning of this interim arrangement will also allow the exploration and development of GP shared care arrangements, where we can ensure a seamless interface between primary care and specialist services. This will support continuity of care and help embed best practice prescribing and monitoring standards across the system.

- GOVERNANCE AND RISK ISSUES

3.1 Governance

Progress updates will be provided at formal APB meetings chaired by the Health Board’s Executive Director of Planning & Partnerships.

A mobilisation group has been established by the WBAPB Transformation Programme to oversee the implementation of clinical services for the alliance.  The group are responsible for providing direction, coordination, and oversight for the successful mobilisation of clinical services and partnerships within the alliance model. The group aims to ensure that the transition and activation of clinical services and future alliance non-clinical services are achieved in a timely, efficient, and collaborative manner, aligning with the strategic objectives and priorities of the alliance.

An internal oversight group will also be in place to plan for the delivery of the full clinical services model and will oversee performance against this contract.

  - Risks

The biggest risk to the prescribing service is the tight turnaround time to complete the most suitable provider process by midnight on 25th March 2026 and for approval to award the contract to be formally obtained by 27th March 2026.  If these timelines are not achieved, the contract will not be able to commence on 1st April 2026 leaving a gap in service provision.  Therefore, it is crucial that approval to award the contract is granted.

- FINANCIAL IMPLICATIONS

The vast majority of funding for the Drug and Alcohol Services in Western Bay is from the Substance Misuse Action Fund (SMAF) which is an allocation from Welsh Government.

From 1 April 2026, funding of £774,953.91 for this contract will be transferred directly to SBUHB to enable commissioning of the service. Any in‑year overspend will be covered by WBAPB to ensure that the Health Board is not exposed to financial risk. Conversely, any underspend will be returned to WBAPB as slippage.

- RECOMMENDATIONS

Members are asked to:

- APPROVE sub-contracting of clinical Criminal Justice Services to Kaleidoscope via ‘most suitable provider’ procurement route

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☐ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☐ |
|  | Effective Care |  | ☐ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |
| Implementing an Alliance approach is intended to improve the alignment of services with individuals’ and our communities’ needs and thus improve the effectiveness of services in reducing the harm from substance use and misuse. Action is aimed at providing a more wrap around range of services that reduce the need for patients to move between providers. |  |  |  |
| Financial Implications |  |  |  |
| There will be a need to establish a mechanism to pool and align funding between different agencies involved in the commissioning and delivery of substance misuse services. The new commissioning entity of arrangements should allow for better risk share between partners involved. The Alliance model is being developed within the current financial envelope of the statutory partners; no additional funding is being requested. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| The Alliance contracting framework has been trialled in England and legal aspects of this have been worked through. An alliance approach for substance misuse has been operational for some time in Cardiff & Vale University Health Board and the APB team have linked in closely to learn lessons from them. SBUHB has sourced expert advice from NHS Wales Shared Services Partnership - Legal & Risk Services regarding the proposed Alliance Contract. |  |  |  |
| Staffing Implications |  |  |  |
| Staffing implications are being worked through as there may be changes in the roles and numbers of staff involved in delivering substance misuse services. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| - Long Term – The Alliance model is intended to deliver better services to minimise the harm associated with substance misuse and to reduce the legacy of substance misuse issues in our communities. - Prevention – Acting to prevent substance misuse will form a central part of the overall approach. - Integration – Substance misuse affects the whole community and impacts on physical, social and mental well-being, crime, and the environment. It also has economic impacts. Tackling substance misuse effectively delivers on a wide range of well-being objectives for partner agencies. - Collaboration – The Alliance approach brings together agencies and the community to develop appropriate responses tailored to local situation. Involvement – The Alliance model has been developed through co-production with people with lived experience |  |  |  |
| Report History |  | None |  |
| Appendices |  | Appendix 1-Service Specification |  |

Appendix 2: Service Specification

Appendix 2: Service Specification

Appendix C

Specification of Requirements

AlliaNce prescribing interim Specification

[Contract REFERENCE]

Contents

1.	Background	3

2.	Requirement	3

The Requirement	3

Output Requirement	3

3.	Service Levels & Performance	3

## Background

Western Bay Area Planning Board (APB) is working collaboratively with a partnership of providers (the Alliance) to radically transform drug and alcohol clinical and support services across Swansea and Neath Port Talbot. As part of this transformation journey, a multi-disciplinary Substance Use Clinical Treatment Hub is being developed to deliver holistic care, improved access to services and ensure continuity of care. To ensure sufficient time for planning and implementation of this new service model, Swansea Bay University Health Board (SBUHB) is seeking to commission an interim drug and alcohol clinical service which includes provision for individuals in the criminal justice system. Purpose The delivery of prescribing interventions will be undertaken for stabilisation, reduction, withdrawal, detoxification and relapse prevention, with the aim of achieving recovery and/or abstinence in line with the persons choice. All prescribing interventions will be carried out in line with the Drug Misuse and Dependence – UK Guidelines on Clinical Management 2017 and NICE Guideline on Psychosocial Interventions in Drug Misuse. The Contractor will work collaboratively with SBUHB and partner organisations to support the development of the new Hub. The Hub will form part of the Alliance, delivering a holistic, whole-system approach to treatment and support. The below diagram outlines the Alliance pathways: The points of entry for individuals in the Criminal Justice system, will include Police Custody Suites, Court and Prison. Generally, referrals to the Alliance will be received through a non-clinical portal. Following triage, individuals will be supported to engage with the appropriate service(s) within the system, which may include the interim clinical service. Those referred from Court will have been assessed as suitable for a Community Sentence Treatment Requirement (CSTR), specifically a Drug Rehabilitation Requirement (DRR) or an Alcohol Treatment Requirement (ATR). Referrals from prison will focus on supporting release planning for individuals who have licence conditions to attend a substance use treatment service, comply with drug testing by HMPPS or are in receipt of Opioid Substitution Treatment (OST) upon release.

## Requirement

## The Requirement Overview The Service will provide clinical treatment interventions for individuals aged over 18 living in Swansea and Neath Port Talbot who have a substance use prescribing need. This can be delivered in a range of settings to maximise engagement. The services provided shall be within agreed prescribing protocol and will be subject to the Clinical Governance Framework adopted by the Alliance. Services should avoid unnecessary steps in the assessment process, particularly to reduce the risk of harm for those who need to stabilise on Opiate Substitute Therapy (OST). Initiation of OST needs comprehensive assessment of new patients. However, it is possible to make a diagnosis of dependence and collate sufficient information for a prescribing decision at first appointment if the relevant information is available. There is no justification for an arbitrary requirement to attend multiple appointments before prescribing. For people who are released in a planned or unplanned way from prison or court (time served) on a maintenance prescription, the Contractor will be required to ensure the prescribing programme shall continue without any interruptions to the person. ## Output Requirement The Contractor will aim to provide same day prescribing in all cases. Waiting times for prescribing shall not exceed 10 working days from referral to treatment or as outlined in the Criminal Justice specifics. A clinical assessment is mandatory prior to prescribing. A suitably qualified person (Nurse/ Nurse assistant) will provide assessment in the community and a first urine test completed, with doctor’s appointment issued at this point. This initial assessment completed travels with the person throughout their recovery pathway within the Alliance. Prescribed drug, amount and dispensing frequency for each person accessing clinical treatment will remain a clinical decision based on service user need and risk. However, providers shall need to evidence within this, that prescribing is carried out in a safe, cost effective and timely manner. Prescribing interventions shall be reviewed regularly with the person and prescriber (based on the risk, need and responsivity of the person) to ensure that the persons clinical prescribing needs are being met and they are still being appropriately supported in contributing towards their recovery plan goals. Detailed Requirements of this Service - Substitute Opioid Prescribing (Methadone, Buprenorphine, injectable Buprenorphine) Maintenance clinical treatment will be delivered by the provider, who will work in conjunction with an Alliance of providers delivering evidence based psychosocial interventions. The care plan for prescribing should include key working and the clinical provider will be expected to work with Key Workers within the non-clinical element of the Alliance to deliver: - Care plan reviews - Risk assessments and related risk management plans - Provision of advice and information - Harm reduction advice and interventions - Interventions to increase motivation - Relapse prevention. The treatment start date is the date of dispensing the first dose of medication. All prescribing interventions must be carried out in line with the Drug Misuse and Dependence – UK Guidelines on Clinical Management 2007. NICE Guideline on Psychosocial Interventions in Drug Misuse 2007 Drug misuse and dependence Drug misuse prevention: targeted interventions (nice.org.uk) Drug misuse in over 16s: opioid detoxification (nice.org.uk) The Contractor shall: - Provide same day access to prescribing for OST for people who meet the in-scope criteria - Ensure continuity of prescribing for individuals already in receipt of OST at the point of referral or release. - Ensure prescribing is available outside standard working hours, including weekends and bank holidays, to prevent treatment interruption. 2. Alcohol Treatment Community based prescribing for withdrawal from alcohol This can include pharmacological interventions and prescribing for symptomatic treatment such as nausea. This may include relapse prevention, respite, stabilisation and/or preparation for abstinence-based treatment. The Contractor shall: - Deliver (or coordinate access to) clinical alcohol treatment, including: - Assisted alcohol withdrawal - Home detoxification (also via clinical partners where appropriate) - Referral to inpatient detoxification - Support into residential rehabilitation where required - Criminal Justice Specifics Clinical treatment requirements for individuals identified through the criminal justice pathways: - Drug Testing on Arrest (DToA) and Arrest Referral Individuals identified through the DToA and Arrest Referral processes in the Police Custody Suites who have a prescribing need, shall commence prescribing within a maximum time of 10 working days from referral. Where an individual in custody is identified as having a substance use need and is already receiving prescribed OST medication, the Contractor shall liaise with the non-clinical Alliance staff to facilitate collection and continuation of their medication, where appropriate. The contractor shall liaise with custody medical and mental health staff, where relevant. - Drug Rehabilitation Requirement (DRR) A DRR can be made as part of a Community Order (CO) or a Suspended Sentence Order (SSO) where an individual is convicted of an offence on or after 1st December 2020. DRRs can provide a more cost-effective, therapeutic alternative to short prison sentences for drug-related offending. The length and intensity of the treatment delivered under a DRR should be tailored to the individual’s need, patterns of substance use and progression towards recovery, regardless of the seriousness of the offence. The Court determines the duration and intensity of the DRR, while the Contractor’s clinician determines the specific treatment plan and delivery method. The Contractor shall provide same day access to prescribing for a range of OST types and ensure prescribing begins within a maximum period of 10 working days from the date the order was made. For those already receiving OST from the Service, continuity of treatment shall be available in all cases unless it is clinically advised against. In cases of treatment disengagement, the Contractor shall provide rapid access (same day) access to prescribing, where appropriate and following clinical assessment. - Alcohol Treatment Requirement (ATR) An ATR can be made as part of a CO or a SSO under Part 11 Sentencing Act 2020 where an individual, aged 18 or over, is convicted of an offence on or after 1st December 2020, and dependent on alcohol. Treatment delivered under an ATR shall primarily consist of structured, community-based, care-planned interventions. Clinical support may include interventions for assisted alcohol withdrawal and access to home detox where appropriate. The Contractor shall support individuals to access established pathways for inpatient detoxification and residential rehabilitation services. - Continuity of care following release from prison The Contractor shall ensure continuity of care from prison to community services so that individuals continue receiving substance use treatment immediately upon release to reduce risks of overdose, reoffending and disengagement from recovery. Prescribing shall be available on the day of release for individuals who are returning to Swansea or Neath Port Talbot, including provision for evening and weekend/Bank Holiday coverage. This includes unplanned or unexpected releases, such as release on bail, no-charge outcomes, or time served from court. The Contractor will work pro-actively with Criminal Justice (CJ) agencies (South Wales Police, South Wales Police & Crime Commissioner, His Majesty’s Prison and Probation service and His Majesty’s Courts and Tribunals Service) to ensure every opportunity is maximised to engage with people and to provide or reinforce pathways into treatment and support. The Service shall include the delivery of high quality, safe, evidence based clinical substance use interventions across police custody and community. Clinical provision must integrate seamlessly with psychosocial interventions, criminal justice requirements, and local treatment pathways within Swansea and Neath Port Talbot. Clinical provision in the prison will continue to be delivered by existing prison healthcare service. The Contractor must ensure all clinical activity is compliant with statutory and regulatory frameworks, national clinical guidelines, and the requirements of the Commissioner and HMPPS. All documentation shall be available for inspection by the Commissioner, HMPPS, HIW, or other authorised agencies including the Alliance Leadership Team. People on Probation and People leaving Prison will no longer be treated as part of a separate service, although the Alliance will be aware that people within the Criminal Justice system may have distinct needs that must be considered as part of the overall clinical treatment and support package. The Provider will work with Criminal Justice to provide timely information sharing in relation to individuals who are required to attend drug and alcohol services as part of Statutory Court Orders and Licence conditions to allow HM Probation Service to carry out its legislative duties of protecting victims and the public with enforcement where necessary. 3.a Clinical Assessment for Criminal Justice The Contractor shall: - Undertake clinical assessments as required as part of unified assessment processes within: - Custody Suites (supporting clinical related decisions while an individual is in police custody) - Court settings (supporting clinical related assessment for presentence and post-sentence reports) - Community settings following referral - Use assessment findings to determine clinical need, risks, safeguarding concerns, and treatment requirements. It is acknowledged that the services being commissioned are for treatment and support, and statutory policing and HMP Prison and Probation services are responsible for enforcement activity.

## Service Levels & Performance

General Clinical Service level The Contractor shall: - Develop a clinically informed care plan for individuals receiving clinical interventions. - Review care plans following clinical milestones, relapse episodes, or at key transition points - Share care plans with practitioners where required and with patients in an accessible format. - Operate a robust clinical governance framework aligned to the Public Health Wales Seven Pillars of Clinical Governance, including feedback from people with living experience into clinical service design and delivery. - Undertake regular audit cycles (minimum quarterly) covering prescribing practices, clinical safety, documentation standards, and outcomes. - Share audit findings with the Alliance members as part of quarterly performance reviews. - Employ clinicians with appropriate qualifications, registration, and experience. - Ensure all clinical staff receive: - Regular clinical supervision - Mandatory training - Annual competency assessment - Deliver all clinical interventions in accordance with evidence- based practice and national clinical guidelines. - Ensure rapid access to clinical interventions based on assessed need. - Maintain clinical risk registers. - Implement protocols for medicines management, controlled drugs, adverse incidents, and emergency response. - Maintain: - Accurate clinical records for all patients - Medicines management logs. - Clinical incident reports. - Clinical audit documentation. - Training and supervision records for all clinical staff. - Ensure all clinical data is accurate, secure, and recorded in the agreed case management system. - Comply with GDPR, WASPI, and requirements for secure communication. - Provide ongoing clinical skills training, including updates in national guidelines, safeguarding, risk assessment, and trauma informed practice. Regulatory and Compliance Requirements The Contractor shall: - Maintain compliance with: - Independent Health Care (Wales) Regulations 2011 - National Minimum Standards for Independent Health Care in Wales - Notify the Commissioner immediately of any non-compliance or change in compliance status. The Contractor shall comply with: - Drug Misuse and Dependence: UK Clinical Guidelines (2017) - Welsh Government National Core Standards for Substance Misuse Services (2010) - Controlled Drugs Local Intelligence Network (CDLIN) requirements Level of Provision Required The level of provision can vary depending on factors such as the number of statutory court orders and the volume of prison releases. For significant fluctuations in figures from those represented here, a discussion with Commissioners would be required to agree how this will be managed. Criminal Justice clinical caseload (January 2026): 110 Non-Criminal Justice caseload (January 2026): 43 (N.B) Buvidal for this service will be provided via the APB Buvidal Welsh Government funding) Exclusion Criteria This service will not be available for individuals who have significant and/or unmanaged physical and/or mental health needs, who require medical interventions on top of their prescribing to include those who are pregnant and those who are over 80. This is because these cases will generally sit within CDAT (Community Drug and Alcohol Team) services. Similarly, where a person requires low threshold prescribing, transfer to provision under the PSALT contract will be considered. To summarise, providers will work collaboratively with all other providers of clinical services within the alliance (CDAT/PSALT) to ensure a persons’ clinical needs are met. Who delivers clinical care in the clinical system will depend on where the persons need will best be met. This can be considered in a joined-up way through the joint allocation processes, or any other future process that is designed for this purpose, and for the development of a system approach. The Contractor shall meet the minimum performance standards that will be developed as part of the Alliance Outcomes Framework, which will be reviewed on a yearly basis. Performance will be reviewing through the Alliance Leadership Team. The table provides details of minimal expectations. KPI Area; Requirement. Clinical Access Times; Prescribing commenced within 10 working days of assessment/sentence Individuals identified through the DToA and Arrest Referral processes in the Police Custody Suites who have a prescribing need, shall commence prescribing within a maximum time of 10 working days from referral. Individuals in receipt of a DRR and assessed as requiring a clinical intervention shall commence prescribing within a maximum time of ten Working Days from point of sentence.. OST Continuity of Care; OST available same day Individuals released from prison with ongoing substance use needs who are in receipt of OST and have transfer of care arrangements in place with community services to receive continuity of OST on day of release..