Strategic Risk Register

April 2026 Summary

| SRR Ref | Strategic Risk | Lead Director | Risk Score |  |  | Overall Assurance |  | Committee Oversight |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Previously | Currently | Target | Previously | Currently |  |
| Objective 1: People of Swansea Bay live healthier, fairer and more prosperous lives |  |  |  |  |  |  |  |  |
| 1.1 | Population Health Approaches to Address Health Inequity | DOPH | 20 | 16 | 16 | Moderate | Moderate | PHC Mar 2026 Received Dec 2025 |
| 1.2 | Partnerships & Collaboration | DOPP | 12 | 12 | 8 | Good | Good | QSC Feb 26 received Dec 25 SRR |
| Objective 2: Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |  |  |  |  |  |  |  |  |
| 2.1 | Urgent & Emergency Care CLOSED | COO | 16 | Risk merged following Executive team review – See SRR2.8 |  |  |  |  |
| 2.2 | Planned Care CLOSED | COO | 12 | Risk merged following Executive team review – See SRR2.8 |  |  |  |  |
| 2.3 | Cancer Care CLOSED | COO | 20 | Risk merged following Executive team review – See SRR2.8 |  |  |  |  |
| 2.4 | Quality, Safety & Patient Outcomes | EDON | 16 | 16 | 12 | Good | Good | QSC Feb 26 received Dec 25 SRR |
| 2.5 | Listening to People CLOSED | EDON | 16 | Risk transferred to CRR following Executive team review – See CRR111 |  |  |  |  |
| 2.6 | Perinatal Service | EDON | 16 | 16 | 9 | Good | Good | QSC Feb 26 received Dec 25 SRR |
| 2.7 | Mental Health | COO | 16 | 16 | 8 | Good | Good | QSC Feb 26 received Dec 25 SRR |
| 2.8 | Access to Services NEW | COO | - | 16 | 12 | TBC | TBC | PFC TBC |
| Objective 3: Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation |  |  |  |  |  |  |  |  |
| 3.2 | Estates | DOF | 20 | 20 | 12 | Moderate | Moderate | PFC Jan 26 received Dec 25 SRR |
| 3.3 | Sustainability of Digital Services CLOSED | DODIG | 20 | Risk transferred to CRR following Executive team review – See CRR113 |  |  |  |  |
| 3.4 | Digital Transformation | DODIG | 20 | 15 | 10 | Good | Good | DDRIC Mar 26 received Dec 25 SRR |
| 3.5 | Research, Development & Innovation CLOSED | EMD | 12 | Risk de-escalated from SRR following Executive team review to CRR112. CRR112 highlighted for further de-escalation by Exec risk owner. |  |  |  |  |
| Objective 4: The health board is a great place to work where all staff feel valued and work together towards a common goal |  |  |  |  |  |  |  |  |
| 4.1 | Staff Health & Wellbeing and Organisational Performance | DOWOD | 16 | Strategic risks related to Objective 4 to be replaced by fresh entries following completion of review by Director of Workforce & OD. |  |  |  |  |
| 4.2 | Leadership & Management | DOWOD | 12 | Strategic risks related to Objective 4 to be replaced by fresh entries following completion of review by Director of Workforce & OD. |  |  |  |  |
| 4.3 | Culture & Values | DOWOD | 12 | Strategic risks related to Objective 4 to be replaced by fresh entries following completion of review by Director of Workforce & OD. |  |  |  |  |
| Objective 5: The health board is a resilient, sustainable and responsible organisation |  |  |  |  |  |  |  |  |
| 5.1 | Recover & Sustainability | DOF | 25 | 25 | 15 | Good | Good | PFC Jan 26 received Dec 25 SRR |

Strategic Risk Register

April 2026 Detail

| Risk ID Number SRR-1.1 | Risk Label – Population Health Approaches to Address Health Inequity Risk Description – If we do not develop the capability and capacity across the organisation and with partners to enable prevention and early intervention approaches to health inequality then there is a risk that health inequalities across the Swansea Bay population continue to widen, undermining long term sustainability and population health outcomes. |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | People of Swansea Bay live healthier, fairer and more prosperous lives |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 5 | 5 | 25 |  | Lead Director / Risk Owner | Director of Public Health |
| Current Score | 4 | 4 | 16 |  | Monitoring Committee | Population Health Committee |
| Target Score | 4 | 4 | 16 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 2025 | Dec 2025 | Feb 2026 | Apr 2026 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 20 | 20 | 20 | 16 |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |
| 52 (1763) | Statutory Compliance: Engagement & Impact Assessment The Health Board does not have sufficient skills & resource in place to undertake integrated equality impact assessments in line with strategic service change and policy development. | 12 |
| 100 (TBC) | A lack of a robust approach to partnerships & collaboration If the health board does not have effective structures, processes and working relationships with its external partners at the Public Services Board (PSB) and/or Regional Partnerships Board (RPB), there is a risk that areas of work dependent upon collaboration with partners may not deliver what is required in a timely way, impacting on the delivery of health board priorities. | 12 |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | Strategy Execution: The Public Health Team have implemented and are pursuing an evidence-based engagement focused strategy execution methodology to support implementation of the Population Health Strategy |
| 2 | Governance: The Population Health Committee has been established to provide governance oversight of the Population Health Strategy. |
| 3 | Engagement: Engagement across the organisation in support of strategy execution has been extensive and encompassed all Service Delivery Groups and Corporate Departments to build competence, capability and capacity to enact strategy. |
| 4 | Strategic Planning: Population health has been integrated into key organisational processes (planning, business case development, partnerships, performance, strategy development). |
| 5 | Leadership: Strategy execution approach has developed tactical and operational level leadership to support strategy execution. |
| 6 | Performance Management: Reporting progress on Population Health Strategy execution through the Health Board Service Delivery Group quarterly performance (this will be reviewed with the implementation of care groups to enhance effectiveness.) |
| 7 | Policy Alignment: Wellbeing of Future Generations Act 2015 outlines 5 ways of working which provide a framework to embed sustainable development in public sector organisations in Wales. |
| 8 | Strategic objectives: The Population Health Strategy has been integrated into the SBUHB Strategic Objectives. Strategic indicators have been developed to support measurement of population health gain. |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1,2 | Strategy Execution & Governance: Implementation of the public health 2026/27 work plan | Supported by Executive oversight | Population Heath Strategy Internal Audit Completed Jan 25 | Reasonable |
| 3 | Engagement: The PSBs and RPB are receiving regular input from public health to inform their strategic direction, translation of strategy and commitment of resources to collaborative working. |  | Feedback from the chairs of PSBs and Welsh Government feedback. | Limited |
| 4 | Strategic Planning: Reports are presented to the Population Health Committee and risks communicated by the chair of the committee to the Board. | Supported by Executive oversight |  | Limited |
| 5 | Leadership: The organising for success programme is developing leadership capacity and reporting to the Executive Board. |  |  | Reasonable |
| 6 | Performance Management: public health performance is reviewed via a quarterly review against the Annual Plan and Breakthrough objectives. | Supported by Executive oversight |  | Limited |
| 7 | Policy Alignment: Any new Welsh Government policy requirements are incorporated into service level documentation and overseen by the Public Health Senior Management Committee. | Supported by Executive oversight | Directors of Public Health meet with Welsh Government representatives regularly to ensure alignment and delivery of national priorities through the Deputy CMO. | Reasonable |
| 8 | Strategic Objectives: There is executive oversight and screening of cost improvement programmes to ensure that strategic public health priorities are not adversely impacted. | Supported by Executive oversight |  | Reasonable |
|  | Current Overall Assurance Rating |  |  | Moderate |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Leadership | Leadership is identified as influencing engagement, motivation and decision making in developing a strategy supportive culture, creation of alignment and enabling collaboration. A lack of leadership engagement and consistency, leaders not prioritising the PHS, lack of understanding has been identified as barriers. Senior leaders are perceived as having limited understanding of the purpose of the PHS. | All Executives & Service Group Directors | Completed | No further work planned. There has been a strengthened focus at executive and senior level across the organisation in population leadership, in conjunction with PSBs. |
| 2 | Long term thinking/planning | Close collaborative work between public health and planning and partnerships on the Annual Plans and the development of an IMTP. | Director of Planning & Partnerships | 31/03/2027 | The IMTP was paused. We will continue to work with colleagues to ensure a population health focus as this work resumes. |
| 3 | Culture & Context | SBUHB is a service delivery focused organisation. Strategy execution is not a primary focus for executives and there is limited understanding of what is required to enact strategy in a complex operating environment. In addition, to this there is limited tactical capability and for a to enact strategy operationally and an absence of a recognised organisational methodology. | CEO & Executive Directors | Completed | No further work planned. The importance of inequalities is now much more embedded in the cultural approach of the organisation, communication and priorities. |
| 4 | Strategic Planning, Management & Alignment | SBUHB has in place 5 strategic objectives that underpin our high-quality organisational vision. Organisational structure, planning, finance, human resources, performance and decision making need to be aligned in pursuit of these objectives. Integration of PHS into strategic planning processes is as an enabler. A lack of clear organisational population health plan and population health priorities at SDG level is a major barrier. Strategic planning capability to support strategy execution is immature. Leadership engagement has been identified as a key enabler supporting improved strategic planning capability and supporting alignment of people, structure, process, finance and technology to execute the PHS. | Director of Planning & Partnerships | 30/08/2026 | April 26: A population health session is being planned for an informal board session, as was previously recommended by the Internal Auditors. Date revised. |
| 5 | Measurement | Development of the measurement and performance infrastructure to demonstration of impact of PHS execution was identified as a key condition and enabler. | Director of Public Health | 31/01/2027 | April 26: This work has had to be paused, due to the move form Service Groups to Care Groups, but will be picked up in the fourth quarter of the year, when new arrangements are in place. Date revised. |
| 6 | Organisational Structuring | Established Population Health governance mechanism. Absence of executive ownership of distinct population health priorities and the tactical forums to organise resources, finance and activity in pursuit of population health gain. | All Executive Directors & SDG Directors | Closed | No further work planned. There has been a strengthened focus at executive and senior level across the organisation in population leadership. New approaches to structure has been put in place by Planning and Performance, which address previous issues. |
| 7 | Engagement | The regional mechanisms for collaborative delivery of priorities with local government, third sector and other stakeholders will be used to enhance engagement. | Director of Public Health | 31/01/2027 | April 26: Relationships are being strengthened, for example by work on Marmot objectives in NPT, and Health Impact Assessment on Tata, and other joint activities. |

Additional Comments

30/03/2026: Risk reviewed by Executive Team. Agreed amendment to description. 29/04/2026 The target risk score has been modified. The gaps have been reviewed and refined. 13/05/2026: Current risk score reviewed at Executive Board and reduced to 16.

| Risk ID Number SRR-1.2 | Risk Label – Partnerships and Collaboration Risk Description – If the health board does not have effective structures, processes and working relationships with its external partners, there is a risk that areas of work dependent upon collaboration with partners may not deliver what is required in a timely way, impacting on the delivery of health board priorities. |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | People of Swansea Bay live healthier, fairer and more prosperous lives |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 4 | 4 | 16 |  | Lead Director / Risk Owner | Director of Planning, Partnerships & Performance |
| Current Score | 4 | 3 | 12 |  | Monitoring Committee | Health Board |
| Target Score | 4 | 2 | 8 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 2025 | Dec 2025 | Feb 2026 | Apr 2026 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 12 | 12 | 12 | 12 |  |  |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | Further work to be developed in relation to children & young people services. This will be considered as part of the Health Boards work on the CYP strategic plan. |
| 2 | Further work to develop internal governance and leadership in relation to Partnerships & Collaboration. |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | A SBUHB Strategic Plan for CYP will enable improved leadership and a strategic approach, both internally and externally. Feedback received from two CYP events held in 2024/2025 – the events included CYP leaders from across SBUHB. Approach for the development of the Plan agreed on the 27th April with the final Plan launch in Q1 2027/28. | Commitment made by Management Board to improve the position strategically for children & young people. | Audit to be undertaken in relation to CYP Services. | Reasonable |
| 2 | Ongoing commitment to develop and improve the role of the Strategic Partnerships Group (SPG). The SPG will provide oversight of partnership discussions, including the WGRPB and the Public Service Boards (PSB), and inform Management Board and SBUHB Board on partnership activity and decisions. In addition, specific and targeted reporting for some areas in the Health Board with an interest in external partnerships including Primary Care & Therapies, Mental Health & Learning Disabilities and Children & Young People. | Embedding of the Collaborative and Partnerships Framework and the SBUHB approach to Partnerships – Framework approved by Management Board in December 2024. | The work of the SBUHB Partnerships Teams including the SPG and the Framework are in line with the Shared Services Audit undertaken in 2023/24. All developments to date have been with the recommendations made. In addition to the audit recommendations, a Partnerships Tracker is in development. | Reasonable |
|  | Current Overall Assurance Rating |  |  | Good |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Commitment to the SBUHB approach to partnerships and collaboration | Raising the visibility of the external partnerships by informing the Management Board and SBUHB Board and listening to colleagues both internally and externally on any improvements to be made. | Marie Davies | Mar 2026 | Complete |
| 2 | There is scope to provide increased visibility and strategic leadership in respect of Children & Young People. | The establishment of the Women, Children & Young People’s Care Programme Board will provide increased visibility and strategic leadership in these key priority areas. A workshop in December was co-chaired by the Executive Director of Nursing and the Chief Operating Officer and the first meeting is scheduled for February 2026. The newly established Care Programme Board approved the approach to develop the Children & Young People’s Plan to be launched in Q1 2027/28. Development of the Plan to be clinically led via the Children & Young People’s Steering Group. | Marie Davies | Feb 2026 | Complete |
| 3 | Partnership governance: There is scope to improve oversight of the health board’s statutory duties and requirements in relation to partnerships and assurance at Board/Committee. | The Partnerships Tracker is now agreed and the first report will be submitted to audit committee in January 2026. The ongoing review and maintenance of the tracker will be the responsibility of the planning & partnerships team. | Marie Davies | Jan 2026 | Complete |
| 4 | Evaluation of internal strategic partnership arrangements to ensure that tools and resources continue to be effective and improve partnership and collaboration. | Evaluate the existing arrangements for strategic partnerships to ensure they are fit for purpose. The evaluation will be undertaken with SBUHB colleagues via the Strategic Partnerships Group. | Marie Davies | April 2027 | On track |

| Additional Comments |  |
| --- | --- |
| 30/03/2026: Risk reviewed by Executive Team. Agreed no change to description and risk scores. Amended assurance committee to reflect direct oversight by Board. 29/04/2026: Risk further reviewed & revised. |  |
| Risk ID Number SRR 2.4 | Risk Label – Quality, Safety & Patient Outcomes Risk Description – If we do not have robust quality governance systems and processes, use our data intelligently, and develop a strong safety culture that supports learning and improvement then this may result in increases in avoidable harm and mortality and poorer clinical outcomes. |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 4 | 5 | 20 |  | Lead Director / Risk Owner | Executive Director of Nursing |
| Current Score | 4 | 4 | 16 |  | Monitoring Committee | Quality & Safety Committee |
| Target Score | 4 | 3 | 12 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 2025 | Dec 2025 | Feb 2026 | Apr 2026 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 16 | 16 | 16 | 16 |  |  |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |
| 4 (739) | Healthcare Acquired Infection Risk of patients acquiring infection as a result of contact with the health care system, resulting in avoidable harm, impact on service capacity, and failure to achieve national infection reduction goals. | 20 |
| 111 | Listening to People If we do not listen to and act upon the issues raised by people there is a risk that matters of concern to them will continue unaddressed, resulting in dissatisfaction, the potential for poor outcomes, greater regulatory intervention and loss of public trust and confidence. | 16 |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | Quality and Safety Process Framework |
| 2 | Annual Strategy Quality Plan |
| 3 | Quality Assurance Framework |
| 4 | Quality Impact Assessment Process |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | Service group quality and safety group scrutiny. Weekly executive Quality Huddle | Service group reporting into QSG sub-groups (PSEG, PSCG, COEG, Safeguarding, IPC, QPPB). Service group performance reviews. Quality dashboard reporting to QSG (monthly), reporting to QSC (bi-monthly) and Management Board (monthly) Service group presentation at QSG (quarterly) | A&A Review – Quality Management System SBUHB-2324-003 (June 2024) – Reasonable Assurance Audit Wales Structured Assessment. | Reasonable |
| 2 | Reporting from action owners within annual strategic quality plan | Quarterly reporting to QSG Quarterly reporting to QSC and Management Board |  | Reasonable |
| 3 | Quality assurance visits within service groups. Service group AMaT scrutiny. | Service group bi-monthly updates to PSCG. PSCG bi-monthly reporting to QSG Corporate Quality Assurance audit programme and reporting into PSCG. Service group Quality Assurance Audit programmes and reporting to PSCG | HIW reviews Llais reviews A&A Review – Quality Assurance SBUHB-2425-009 (March 2025) – Limited Assurance Independent Members’ visiting programme | Limited |
| 4 | QIA scrutiny within service groups’ management boards for service groups decisions QIA scrutiny in Management Board for HB wide decisions | Board scrutiny of QIAs |  | Limited |
|  | Current Overall Assurance Rating |  |  | Good |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Individual, team and service level understanding of the Quality Assurance Process Framework requires embedding. | Action refreshed: QMS self-assessment undertaken and approved in QSG in April. Wider work to be undertaken as part of developing our organisational QMS to identify areas requiring strengthening across the organisation Date changed to reflect this work and the associated impact of Organising for Success | Head of Q & S | 31/3/2027 | On track |
| 2 | The Quality Strategy does not clearly align with organisational objectives, and actions within the implementation plan require review | Action Refreshed: Quality plan on a page developed as part of the IMTP and in line with the HB organisational strategy. | Exec Director of Planning Head of Q & S | 31/12/2025 Expected 31/03/2026 | Complete |
| 3 | Service groups need to ensure that quality assurance audits are completed regularly. AMaT completeness at service group level requires improvement. | Bi-monthly reporting from service groups to PSCG, as part of internal audit management actions. Service groups have developed forward plans for assurance activities and these are beginning to be reported through to PSCG. Service group quarterly reporting to QSC has been replaced with monthly reporting to QSG on key quality and safety metrics. Assurance activities are reported into PSCG. | Service Group Medical and Nurse Directors | 31/12/2025 Now expected 31/07/2026 | Off Track |
| 4 | The Quality Impact Assessment process is not fully embedded across organisation | Action Refreshed: Board reporting template being revised to reflect the key domains of the QIA. | Head of Corporate Governance | 28/02/2026 Now expected 31/8/2026 | Off track |

Additional Comments

30/03/2026: Risk reviewed by Execs. Description refreshed and score confirmed. Cross-reference to new CRR111 and CRR112 risks added (CRR112 subsequently removed following de-escalation of that risk from CRR. 13/05/2026: Actions reviewed & refreshed. Update: Controls effectiveness: • Key controls are operating effectively, with strengthened senior clinical leadership, established perinatal governance structures, a Board reported Perinatal Committee, an agreed Independent Review action plan, and ongoing external oversight through the Oversight Panel, providing clear accountability, scrutiny and assurance of progress against recommendations. Residual risks: • Residual risk remains in relation to digital maternity record implementation, specifically limited national system integrations and reliance on external dependencies, which continue to create operational, safety and workforce pressures; these risks are actively managed through escalation to national digital programmes, local mitigation planning, and continued executive and Board oversight.

| Risk ID Number SRR-2.6 | Risk Label – Perinatal Service Risk Description – If we do not respond in a timely and effective way to the recommendations of the External Review of Maternity & Neonatal services, there is a risk that matters of concern identified within the report will not be addressed, resulting in a lack of demonstrable improvement to quality, low morale and wellbeing amongst staff (with associated implications for recruitment and retention) and a potential loss of wider public confidence in these services. |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 4 | 5 | 20 |  | Lead Director / Risk Owner | Executive Director of Nursing & Patient Experience |
| Current Score | 4 | 4 | 16 |  | Monitoring Committee | Quality & Safety Committee |
| Target Score | 3 | 3 | 9 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 2025 | Dec 2025 | Feb 2026 | Apr 2026 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 16 | 16 | 16 | 16 |  |  |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | Appointment of new leadership roles (e.g., Clinical Director of Midwifery, Clinical Director of Womens Health, Associated Service Group Director, Associate Service Group Medical Director, Service Group Medical Director) |
| 2 | Establishment of a Perinatal Committee and enhanced governance structures. |
| 3 | Implementation of a maternity and neonatal dashboard for real-time monitoring |
| 4 | All-Wales MEWS tool has been implemented to identify and escalate deteriorating condition of pregnant women. |
| 5 | All Clinical Maternity staff attend Infant Fetal Surveillance training annually |
| 6 | Engagement with families through Maternity and Neonates Voices Partnership and community outreach. |
| 7 | Womens Experience Specialist Midwife role is in place to support wider engagement with women, families and the community. |
| 8 | Forward Audit Plan in place (this will be revised in view of the Independent Review report recommendations to ensure the ongoing assessment of implementation and impact continues throughout the year.) |
| 9 | Publication of a clear, time-bound action plan addressing all review recommendations (due Nov 2025 – see Actions) with regular progress updates reported to the Perinatal Committee. |
| 10 | Recruitment of a Project Manager to support and oversee the action plan and evidence base to demonstrate implementation and delivery of the report recommendations. |
| 11 | Ongoing support from the Chair and Oversight Panel members of the external review for 18 months to provide assurance and scrutiny in relation to actions and recommendations |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 4,5,6,7 | Perinatal dashboard for real time data monitoring by the Division and Service Group of key performance metrics along with exceptions from the perinatal assurance group. | Board oversight of service improvement using agreed outcome, process and experience measures via the Perinatal Committee – Chairs report presented at Board level meetings. | Chair and Oversight Panel members of the external review for 18 months to provide assurance and scrutiny in relation to progress in addressing actions and recommendations. | Reasonable |
| 8 | Elements of Forward Audit Plan are reviewed at Perinatal Assurance Group. | Elements of Forward Audit Plan is reviewed at Perinatal Committee and overview is maintained at COEG (and monitored by WG). | Chair and Oversight Panel members of the external review for 18 months to provide assurance and scrutiny in relation to progress in addressing actions and recommendations. | Limited |
| 5 | Reporting of compliance rate for completion of annual Infant Fetal Surveillance training by clinical Maternity staff at Perinatal Committee. | Board oversight of service improvement using agreed outcome, process and experience measures via the Perinatal Committee – Chairs report presented at Board level meetings. | Chair and Oversight Panel members of the external review for 18 months to provide assurance and scrutiny in relation to progress in addressing actions and recommendations. | Reasonable |
|  | Current Overall Assurance Rating |  |  | Good |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Consolidation of actions for oversight. | Development and approval of an action plan to deliver recommended improvements required by the Independent Review. | Executive Director of Nursing & Patient Experience | 30/11/2025 | In Progress Expected completion date 30/07/2026 |
| 2 | Improvement to triage access arrangements. | Development of business case and improvement programme objectives to implement a 24-hour Triage line. | Clinical Director of Midwifery, Clinical Director for Women’s health | 31/03/2026 | Complete |
| 3 | Gap analysis against national standard. | Benchmark local service provision against the Perinatal Engagement Framework for Wales. | Clinical Director of Midwifery | 31/12/2025 | Completed |
| 4 | Improvements to record-keeping arrangements. | Launch of Digital Maternity Electronic Record. | Clinical Director of Midwifery | 31/03/2026 | In progress Expected completion 19/05/2026 |

Additional Comments

30/03/2026: Risk reviewed by Execs. Risk retained on SRR and score confirmed. 13/05/2026: Actions reviewed and progress updated.

| Risk ID Number SRR 2.7 | Risk Label – Mental Health Risk Description – If we do not organise ourselves effectively, and secure and direct sufficient resource and effort to priority areas set out within our mental health and learning disability transformation plan, then there is a risk that we will not transform our environments and the delivery of care sufficiently and in a timely way in line with the recommendations of the mental health transformation plan and in line with the All-Wales Strategy for Mental Health & Wellbeing. This may result in poor patient experience, outcomes and at worst incidents of avoidable harm. |
| --- | --- |

| Risk Score |  | Consequence |  | Likelihood |  | Overall Score |  | Trend |  | Strategic Objective |  |  |  |  | Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Inherent Score |  | 4 |  | 5 |  | 20 |  |  |  | Lead Director / Risk Owner |  |  |  |  | Chief Operating Officer |  |  |  |  |  |  |  |  |  |  |
| Current Score |  | 4 |  | 4 |  | 16 |  |  |  | Monitoring Committee |  |  |  |  | Quality & Safety Committee and MH and LD Transformation Program Board |  |  |  |  |  |  |  |  |  |  |
| Target Score |  | 4 |  | 2 |  | 8 |  | N/A |  | Risk Appetite |  |  |  |  | T.B.C. |  |  |  |  |  |  |  |  |  |  |
| Risk Score Over Time | Nov 2025 |  | Dec 2025 |  | Feb 2026 |  | Apr 2026 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 16 |  | 16 |  | 16 |  | 16 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |
| 114 | Mental Health & Learning Disabilities Staffing If workforce shortages and fragility persist across Mental Health and Learning Disabilities services (vacancies, sickness, turnover, reliance on temporary staff and insufficient skill mix), then services will be unable to deliver safe staffing and consistent therapeutic input across community, crisis and inpatient pathways. This may lead to avoidable harm (including self-harm/suicide risk), increased restrictive practice, delayed access and extended length of stay, deteriorating staff wellbeing and retention, failure to meet national quality expectations and performance standards, and increased regulatory, financial and reputational impact. | 20 |
| 115 | Mental Health & Learning Disabilities Estate If the condition, configuration and security of the mental health inpatient, crisis and community estate (including ligature risks, blind spots, backlog maintenance, ageing infrastructure, water/heating/ventilation vulnerabilities and inadequate seclusion and Section 136 facilities) cannot be stabilised and improved at pace, then the Health Board may be unable to provide safe, therapeutic and dignified care. This may result in serious harm or death (including self-harm/suicide risk), increased violence/aggression and restrictive practice, service disruption or temporary closure/decant due to infrastructure failure, failure to meet statutory health & safety requirements, national standards and HIW expectations, and significant regulatory, financial and reputational impact. | 20 |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | Programme in place, with Chief Operating Officer (COO) as nominated Senior Responsible Officer (SRO), with formally agreed Project Initiation Documentation. |
| 2 | Programme Board with formal terms of reference (TOR), chaired by COO, reports periodically to Board / Quality & Safety Committee |
| 3 | Programme structure incorporates workstream groups to address; information; quality & safety; service redesign; workforce; estates. Each has TOR and reports to the Driver Group (see below). |
| 4 | External expert engaged to challenge & support the Service Group |
| 5 | There is a Driver Group, chaired by the independent expert, to oversee the workstream groups, provide challenge, and report into the Programme Board. |
| 6 | Key quality indicators have been identified aligned to improvements required |
| 7 | Engagement & partnership involvement has been strengthened, particularly in respect of modernisation & redesign workstreams. |
| 8 | Communication & activities relating to transformation feed into weekly MHLD management team and divisional meetings, and MHLD management board meeting (which includes partner agencies and service users). |
| 9 | Regular engagement sessions with staff. |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | Highlight reports are submitted to the monthly Programme Board meeting from each of the workstreams to maintain oversight of progress against delivery plans | Regular updates are provided to Executive Team meetings via the SRO | All workstreams are chaired by a Health Board Executive or a nominated deputy | Substantial |
| 2 | Updates from each workstream provided to the monthly Driver Group meetings, which are chaired by the Independent Expert and facilitate discussion for a collaborative approach |  |  | Reasonable |
| 3 | Quality and Safety workstream overseeing work to ensure recommendations from HIW and external inspection reports are embedded into improvement plans | Formal reporting of progress made against recommendations submitted to HIW directly and via IQPD process with NHS P&I team. |  | Substantial |
| 4 | Dedicated workstream established for Engagement and Communications to ensure coproduction and collaboration |  |  | Reasonable |
|  | Current Overall Assurance Rating |  |  | Good |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Leadership | Leadership is identified as influencing engagement, motivation and decision making in developing a strategy and implementation plan from the work within the Transformation Program. This needs to be at all levels of the organisation to influence such significant change across a service. | All Executives & Service Group Directors | Action subject to review by Lead |  |
| 2 | Review of actions for oversight as the Transformation Program continues to progress. | Development and approval of an implementation plan to deliver recommended improvements required by the MH Transformation Program which incorporates the NHS PI Adult MH Review. | All Executives & Service Group Directors | Action subject to review by Lead |  |

Additional Comments

30/03/2026: Risk reviewed by Exec Team on 30/03/2026. Risk retained on SRR and score confirmed. Risk CRR69 flagged for de-escalation in CRR following Exec team discussion. Reference removed from this SRR entry.

| Risk ID Number SRR-2.8 | Risk Label – Access to Services *New combined risk* Risk Description – There is a risk that the Health Board fails to deliver timely access to planned and unscheduled care, resulting in patient harm, regulatory escalation and reputational damage, if capacity and flow challenges persist. |
| --- | --- |

| Risk Score |  | Consequence |  | Likelihood |  | Overall Score |  | Trend |  | Strategic Objective |  |  |  |  | Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Inherent Score |  | 5 |  | 5 |  | 25 |  | - |  | Lead Director / Risk Owner |  |  |  |  | Chief operating Officer |  |  |  |  |  |  |  |  |  |  |
| Current Score |  | 4 |  | 4 |  | 16 |  |  |  | Monitoring Committee |  |  |  |  | Performance & Finance Committee |  |  |  |  |  |  |  |  |  |  |
| Target Score |  | 4 |  | 3 |  | 12 |  | N/A |  | Risk Appetite |  |  |  |  | T.B.C. |  |  |  |  |  |  |  |  |  |  |
| Risk Score Over Time | Nov 2025 |  | Dec 2025 |  | Feb 2026 |  | Apr 2026 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - |  | - |  | - |  | 16 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |  |
| --- | --- | --- | --- |
| Risk ID | Short Name | Description | Score |
| 80 (1832) | Transfer of Clinically Optimised Patients | Risk that we fail to significantly reduce the number of Clinically Optimised Patients in hospital beds. A deficit in the availability of appropriate community / domiciliary care results in unacceptable delays in discharging patients from acute hospital beds. As a result, patients can decompensate and never gain the independence that could have been available from an early discharge. The use of surge capacity across the Health Board to support UEC flow is directly impacted by the clinically optimised patient group remaining in acute beds for prolonged periods of time waiting for interventions or care in the community. Lack of access to same day domiciliary care/emergency placements in the community hinders ability to avoid admission and associated harms. | 20 |
| 109 | Access to Planned Care | If we do not have enough staff and physical capacity organised effectively across all services, including primary and secondary care, to meet the non-urgent physical and mental health needs of adults and children, there is a risk that we will be unable to improve access to timely, safe, effective, and person-centred planned care, resulting in a potential for patient harm, increases in length of stay, placement of patients in unsuitable places, and a negative impact on patient & staff experience | 12 |
| 110 | Access to Cancer Care | If we do not have enough staff and physical capacity organised effectively across all services, including primary and secondary care, to provide timely diagnosis and treatment of adults and children, there is a risk that we will be unable to improve provision of safe, effective, and person-centred cancer care, resulting in a potential for patient harm, poor outcomes, and a negative impact on patient & staff experience. This will impact not only on SBU patients but those of partner organisations depending on this health board as a regional centre for cancer care. | 20 |
| 117 | Access to Timely Urgent & Emergency Care | Detailed description and risk entry are in development with Chief Operating Officer’s team. | 20 |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 |  |
| 2 |  |
| 3 |  |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
|  | Current Overall Assurance Rating |  |  |  |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |

Additional Comments

30/03/2026: Risk description and assessment created from consideration of separate UEC, Planned Care and Cancer Care risks. Planned Care & Cancer risk detail has been transferred to CRR This risk will be populated by the Lead Director supported by her senior management team afresh during May 2026.

| Risk ID Number SRR-3.2 | Risk Label – Estates Risk Description – If our estate is not maintained and we do not secure sufficient funding and employ that effectively to address priority areas of deterioration and/or environments unsuitable for modern practice within our primary and secondary care estate, then our buildings and/or associated infrastructure may fail in part or wholly, resulting in increased risk to patient and staff safety, and the disruption of service provision. |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 5 | 4 | 20 |  | Lead Director / Risk Owner | Director of Finance & Performance |
| Current Score | 5 | 4 | 20 |  | Monitoring Committee | Performance & Finance Committee |
| Target Score | 4 | 3 | 12 | N/A | Risk Appetite | TBC |

| Risk Score Over Time | Nov 2025 | Dec 2025 | Feb 2026 | Apr 2026 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 20 | 20 | 20 | 20 |  |  |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |
| 64 (2159) | Health and Safety Infrastructure Insufficient resource and capacity of the health, safety and fire function to maintain legal and regulatory compliance. | 20 |
| 115 | Mental Health & Learning Disabilities Estate If the condition, configuration and security of the mental health inpatient, crisis and community estate (including ligature risks, blind spots, backlog maintenance, ageing infrastructure, water/heating/ventilation vulnerabilities and inadequate seclusion and Section 136 facilities) cannot be stabilised and improved at pace, then the Health Board may be unable to provide safe, therapeutic and dignified care. This may result in serious harm or death (including self-harm/suicide risk), increased violence/aggression and restrictive practice, service disruption or temporary closure/decant due to infrastructure failure, failure to meet statutory health & safety requirements, national standards and HIW expectations, and significant regulatory, financial and reputational impact. | 20 |

| Key Controls |  |
| --- | --- |
| Control Ref |  |
| 1 | Planned Preventative Maintenance prioritising highest risks dependent on funding availability e.g. Year 2 Targeted Estate Fund 25/27 (TEF), Discretionary availability. |
| 2 | There is an Essential Infrastructure Replacement programme – however, this is subject to availability of decant facility and progress of Business Case to obtain funding. Morriston Service Group have noted the need for a decant facility to be available from the end of the Emergency Department Test of Change from March 2026. |
| 3 | Electrical resilience is tested through Black Starts on both sites, Singleton and Morriston. Provision of further resilience is subject to funding of N+1, Sub stations and back-up generators, and alternative additional HV supply facilitated by Access Road (Felindre Sub-station). |
| 4 | There is an Estates Strategy in place informed by a 6 Facet Survey. That survey has now been superseded by the review and upgrade of the health board asset register to form a baseline for capital investment planning as well as the actual condition / life expectancy of plant. |
| 5 | Reactive Maintenance is ongoing. However, demands are increasing due to more frequent breakdowns and the age of the estate infrastructure, which is becoming more resource intensive with limited capacity and capability especially with regard to 24/7 shift cover and associated business continuity risks. |
| 6 | Adult Mental Health, Forensic Services and Learning Disabilities engagement on Business Case. |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | PPM: - Monthly SLT meetings with Capital and Estates reviewing risks and new DATIX notifications. - Reports bi-monthly to the Capital and Estates Board. - Fortnightly meetings with Performance and Finance Executive Director highlighting risks that impact on business continuity. - Bi-monthly reporting to Welsh Government through Capital Resource Meetings. - Assistant Director chairing all compliance groups and reporting through Capital and Estates Board. - Presentations to Estates Task and Finish Group with Independent Members. - Paper to Health Board covering Capital and Estates progress, risks and challenges. | Engagement with Independent Members on site walkabouts. Reports to Performance and Finance Committee are scrutinised and the Committee reports to Board to Alert, Advise or Assure on matters received. |  | Substantial |
| 2 & 3 | ESSENTIAL INFRASTRUCTURE MAINTENANCE & ELECTRICAL RESILIENCE TESTING: - Monthly SLT meetings with Capital and Estates reviewing risks and new DATIX notifications. - Reports bi-monthly to the Capital and Estates Board. - Fortnightly meetings with Performance and Finance Executive Director highlighting risks that impact on business continuity. - Bi-monthly reporting to Welsh Government through Capital Resource Meetings. - Assistant Director chairing all compliance groups and reporting through Capital and Estates Board. - Presentations to Estates Task and Finish Group with Independent Members. - Paper to Health Board covering Capital and Estates progress, risks and challenges. The absence of decant facility is a constraint to undertaking works, hence the assessment of level of control effectiveness as Limited. | Engagement with Independent Members on site walkabouts. Reports to Performance and Finance Committee are scrutinised and the Committee reports to Board to Alert, Advise or Assure on matters received. |  | Limited |
| 4 | REACTIVE MAINTENANCE: - Monthly SLT meetings with Capital and Estates reviewing risks and new DATIX notifications. - Reports bi-monthly to the Capital and Estates Board. - Fortnightly meetings with Performance and Finance Executive Director highlighting risks that impact on business continuity. - Bi-monthly reporting to Welsh Government through Capital Resource Meetings. - Assistant Director chairing all compliance groups and reporting through Capital and Estates Board. - Presentations to Estates Task and Finish Group with Independent Members. - Paper to Health Board covering Capital and Estates progress, risks and challenges. | Engagement with Independent Members on site walkabouts. Reports to Performance and Finance Committee are scrutinised and the Committee reports to Board to Alert, Advise or Assure on matters received. |  | Reasonable |
| 5 | ESTATES STRATEGY: Delivery of Estates Strategy is dependent upon the availability of capital & revenue funding. As such the level of control effectiveness to deliver the strategy and address estates priorities at place is assessed to be limited. This has implications for the effectiveness of the response to known matters within mental health & learning disability services, amongst others. |  |  | Limited |
| All |  |  | Internal Audit reports received on Estates matters as follows: Estates Condition (Oct 2023) – Limited Assurance Estates Condition (Mar 2025) – Reasonable Assurance Estates Assurance: Follow Up (Mar 2024) – Reasonable Assurance | Reasonable |
| All |  |  | HIW Inspection findings in the below areas: Tawe Clinic, MHLD (Mar 2022 & Oct 2025 indicative) Ward F NPTH, MHLD (May 2023) Caswell Clinic, MHLD (Sep 2023) Tonna Suite 2, MHLD (Oct 2024) Laurels & Briary, MHLD (Apr 2025) Oakwood & Ward M, Morriston (Jan 2023) | Limited |
| All |  |  | JCC Review findings in the below service: Caswell Clinic, MHLD (Oct 2025) | Limited |
|  | Current Overall Assurance Rating |  |  | Moderate |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | There is a need to focus on capacity, capability and resilience and to increase organisational understanding of the Estates department’s contribution to the safety of the built environment and the quality of the patient experience. There are significant risks associated with an under resourced, ageing and inconsistently trained workforce that is struggling to maintain the operational viability of an estate that was not built to deliver modern healthcare interventions and is mostly 40 years old. NHS trained staff with knowledge and experience of healthcare estate are the most capable resource for ensuring a quality service that clinical colleagues can rely on. Gaps and weaknesses in both capacity and capability are most often filled through reliance on contractors. Some of this intervention will always be necessary given the highly specialised and complex nature of the estate infrastructure but compared with other Health Boards Swansea Bay has a disproportionately high reliance on contractors. Failure to plan and invest may deliver short term cash reductions but will result in systemic failure and much higher cost to the Health Board. | An OCP proposal that deals with legacy capacity issues; legacy industrial relations issues; and essential capacity to respond to Business Continuity risks and longer-term sustainability is pending final approval in line with current Health Board financial processes. When this is approved the aim is to submit it to the HR Sub Committee on the 4th December so that the OCP process may commence. This OCP would be fully funded from existing approved budgets. Furthermore, approval from the Executive Director Performance and Finance requires additional savings to be generated to at least equal the key posts. It is also important to note that this OCP is intended to facilitate a more holistic approach to reducing the Health Boards run rate through more effective utilisation of the estates resource. | ED P&F | 4th December 2025 | Risk & action subject to review by Lead |
| 2 | Availability of funding from Welsh Government and the level of discretionary funding which needs to increase. | Business continuity and estates risks are being reviewed with bi-monthly Welsh Government Capital Resource meeting. | ED P&F | 1st February 2026 | Risk & action subject to review by Lead |
| 3 | Gap in information on extend of work required in Learning Disabilities estate. | A detailed survey of the condition of premises within the health board LD estates is required in order to identify areas of high and intermediate risk for works to be carried out this year. | ED P&F | 31st March 2026 | Risk & action subject to review by Lead |

Additional Comments

30/03/2026: Risk reviewed by Executive team on 30/04/2026 and description adjusted.

| Risk ID Number SRR-3.4 | Risk Label – Digital Transformation Risk Description – If the organisation does not have a clinically/service-led and sustainable approach to digital transformation, including timely investment in modern technologies and platforms, then the organisation may remain dependent on ageing, unsupported systems and manual or paper‑based processes, resulting in limited realisation of transformation benefits and reduced organisational resilience to increasing population and service demands. |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovation |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 5 | 5 | 25 |  | Lead Director / Risk Owner | Director of Digital |
| Current Score | 5 | 3 | 15 |  | Monitoring Committee | Digital, Data, Research & Innovation Committee |
| Target Score | 5 | 2 | 10 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 2025 | Dec 2025 | Feb 2026 | Apr 2026 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 20 | 20 | 20 | 20 |  |  |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |
| 36 (1043) | Paper Record Storage Lack of a single electronic record means there is greater reliance on the provision of the paper record. If we fail to provide adequate storage facilities for paper records, then this will impact on the availability of patient records at the point of care. Quality of the paper record may also be reduced if there is poor records management in some wards. There is an increased fire risk where medical records are stored outside of the medical record libraries. | 16 |
| 85 (2561) | Non-Compliance with ALN Act The Health Board is currently at risk of not reliably and consistently fulfilling the following duties: • Prompt provision of information requested by Local Authorities (Section 65) • Prompt response when asked if there is a relevant NHS treatment or service likely to be of benefit in addressing a learner’s needs (Section 20) • Securing the treatment or service identified by the Health Board in response to the Section 20 request • Notifying the Local Authority of pre-school children likely to have ALN (Section 64) | 16 |
| 90 (2796) | Subject Access Request Risk If the Health Board is non-compliant with the UK General Data Protection Regulation (UK-GDPR), then there is a risk of Information Commissioner’s Office (ICO) enforcement action being taken against SBUHB, as well as reputational damage and the potential for claims. Due to insufficient resources and inconsistent processes across Swansea Bay University Health Board, there is a risk that Subject Access Requests (SARs) will not be fulfilled in compliance with UK-GDPR Article 15, resulting in potential breaches of personal data which could cause distress and lead to a loss of public and government confidence in the Health Board’s trustworthiness and legal standing. Additional Potential Consequences: • Regulatory Enforcement: ICO may impose fines up to 4% of annual turnover for serious breaches. While the ICO has not historically issued fines for SAR breaches, this may change, especially as enforcement activity increases. Recent public reprimands issued by the ICO to another NHS Trust and several public bodies signals heightened regulatory scrutiny. There is also potential for Enforcement Notices to be issued by the ICO, requiring organisations to take corrective action when areas of failure have been identified. • Operational Disruption: Staff diverted from priority tasks to manage SARs, affecting service delivery • Legal Exposure: Increased risk of litigation & claims from individuals with compromised data rights. | 20 |
| 92 (3444) | Forecast Deficit Forecast deficit is not met due to (1) insufficient progress on run rate reduction, (2) the saving targets required across all areas are not achieved. | 25 |
| 93 (3448) | Reduced Capital Funds Reduced National NHS funds available for major capital schemes requiring a restricted Capital Plan for 2025/26. | 12 |
| 104 (443) | Failure to meet Tier 1 targets in Clinical Coding Completeness Because: The volume of new inpatient episodes exceeds the available clinical coding staff capacity; There are difficulties recruiting and retaining a sufficient number of trained clinical coding staff to address the gap, and clinical information is not always of sufficient quality or completeness electronically (such as the Discharge Advice Letter (DAL)) to support swift coding. There is a risk that: Clinical notes for inpatient episodes will not be coded in a timely way. Resulting in: The non-achievement of the Tier 1 Welsh Government target (which is that 95% of inpatient activity should be coded within 30-days of discharge); Insufficient coded data to support effective service planning for population health needs; Inadequate data being available for mortality review/quality and safety purposes, with increased risk of failure to spot variance that are negatively impacting levels of patient care and potentially causing avoidable deaths; Negative impact on accuracy of analysis to understand how resources are being allocated and used at Health Board level and national level (programme budgeting); Delays in claiming casemix sensitive contract lines with the Joint Commissioning Committee (JCC), Hywel Da and Cwm Taff (circa 70m per annum value in total) due to lack of coding data. | 20 |
| 108 (4334) | WCCIS/Connecting care - Provision of an Integrated Health Record for MH&LD and PCT If the Connecting Care programme fails to deliver a digital solution that meets the operational, clinical, and reporting needs of Mental Health & Learning Disabilities (MH&LD) and Community & Therapies services, Then wider MH&LD, Community and Therapies teams will lack access to timely, accurate, and shared information across care settings, resulting in fragmented service delivery, limited availability of high-quality data for performance monitoring and informed decision making, increased duplication of effort, and elevated clinical and governance risks. This includes the potential for further Regulation 28 reports, as previous Prevention of Future Deaths (PFD) notices have explicitly cited the absence of an integrated electronic system as a contributing factor to avoidable harm. Without a fit-for-purpose solution, the Health Board may be unable to fulfil the actions required under Regulation 28, particularly around effective information sharing and risk management across agencies. Whilst the issue facing current users across integrated teams from the loss of WCCIS will be largely mitigated through the approved procurement of replacement solutions through the strategic partnership with the supplier, there remains to be 3,000 users across MH&LD and PCT who continue to provide services without an appropriate digital solution to support them. The provision of a solution is a core component of the SBU Digital Strategy. A recent independent review of Mental Health and Learning Disability services at SBUHB identified the lack of a single digital solution as a critical barrier to safe and effective care, highlighting that fragmented systems and manual processes are contributing to clinical risk, delayed interventions, and repeated Regulation 28 reports due to inadequate access to shared electronic records. | 16 |
| 113 (4842) | Sustainability and Refresh of Digital System and Infrastructure If the organisation is unable to sustainably support, maintain, refresh and replace its digital systems, devices and infrastructure in a timely manner, there is a risk that ageing and legacy technologies will become increasingly unstable, insecure and costly to support. This may increase the likelihood of system failures, cyber security vulnerabilities and unplanned disruption to clinical and corporate services. Contributing factors include capital and revenue funding constraints, extended refresh cycles, ageing infrastructure, accumulating technical debt, and the ongoing need to support business‑as‑usual services | 15 |
| 105 (3114) | Significant increased cost for the replacement Pathology System LIMS If the national Laboratory Information Management (LIMS) 2.0 programme is unable to secure funds from Welsh Government for the overrun into Q1 and Q2 FY 2026/27, then there will be significant additional cost across NHS Wales which could impact the Health Board’s financial plans in 2026/27. Costs would have to be covered to avoid pathology losing access to the current LIMS system resulting in the inability of pathology to deliver diagnostic results and blood transfusion services across all Health Board services including emergency, acute, primary and community services. There is also an emerging financial risk associated with access to legacy data (see Gaps in Assurance). | 16 |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | Robust project management framework and governance in place within Digital Services |
| 2 | Benefits framework and methodology in place within Digital Services |
| 3 | HB Business Case Assurance Group process provides scrutiny to ensure digital resources are considered for all projects |
| 4 | Digital Services prioritisation process in place to ensure that requests for digital solutions are considered in terms of alignment to the strategic objective, technical solutions and financial implications. Project Boards established for all significant projects. |
| 5 | Clinical Reference Group established, providing a forum for engagement with and feedback from clinicians in respect of digital solutions and enhancements, and the strategic direction of digital services. Digital meetings with Service Delivery Groups to identify and prioritise requirements, monitor progress with implementation, and address issues with business-as-usual activities. |
| 6 | Receipt, approval and recording of changes/updates made to all existing digital solutions via the Digital Services Change Advisory Board. |
| 7 | The Health Board has representation on national groups such as Advanced Analytics Group (AAG), all Wales Business Intelligence & Data Warehousing Group and Welsh Modelling Collaborative. |
| 8 | IMTP, Digital Strategy, Business Intelligence Strategic Plan, along with Digital Procurement Policy, a number of Health Records and other Digital policies |
| 9 | Ten-year Financial Plan for replacement of devices and infrastructure. Prioritisation in place to ensure consideration given to highest areas of risk. |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | Reports to bimonthly Digital Services Business Meeting Monthly Digital Risk Management Group / Risk Register Reports to Digital Leadership Group (DLG) Monthly Digital Finance meeting Monthly Capital Finance meeting Digital Project Review Group Reports to Information Governance and Cyber Assurance Group (IGCAG) | Regular reports to Management Board and DDRI Quarterly Performance and Finance Review | Internal Audit: SBUHB 2324-20 Digital Support (23/24) (Reasonable assurance) (Completed) Digital Transformation Review – Audit Wales (25/26) Annual IG Toolkit submission | Reasonable |
| 2 | Reports to bimonthly Digital Services Business Meeting Monthly Digital Risk Management Group / Risk Register Reports to Digital Leadership Group (DLG) Monthly Digital Finance meeting Monthly Capital Finance meeting Digital Project Review Group | Regular reports to Management Board and DDRI Quarterly Performance and Finance Review | Internal Audit: SBUHB 2526-19 Benefits Realisation (25/26) (Substantial assurance)(Completed) | Reasonable |
| 3 | Reports to Digital Leadership Group (DLG) Digital Project Review Group | Regular reports to Management Board and DDRI Quarterly Performance and Finance Review | Internal Audit: SBUHB 2526-19 Benefits Realisation (25/26) (Substantial assurance)(Completed) Digital Transformation Review – Audit Wales (25/26) | Reasonable |
| 4 | Reports to bimonthly Digital Services Business Meeting Monthly Digital Risk Management Group / Risk Register Reports to Digital Leadership Group (DLG) Digital Project Review Group | Regular reports to Management Board and DDRI Quarterly Performance and Finance Review | Internal Audit: SBUHB 2324-20 Digital Support (23/24) (Reasonable assurance)(Completed) Management of the Delivery of National Systems (25/26) | Reasonable |
| 5 | Reports to Digital Leadership Group (DLG) Reports to Information Governance and Cyber Assurance Group (IGCAG) | Regular reports to Management Board and DDRI | Internal Audit: SBUHB 2526-19 Benefits Realisation (25/26) (Substantial assurance)(Completed) Digital Transformation Review – Audit Wales (25/26) Annual IG Toolkit submission | Reasonable |
| 6 | Reports to bimonthly Digital Services Business Meeting Monthly Digital Risk Management Group / Risk Register Reports to Digital Services Management Group (DSMG) | Regular reports to Management Board and DDRI | Internal Audits: - SBUHB 2324-18 Software / System Development (23/24) (Reasonable assurance)(Completed) - SBUHB 2526-21 Management of the Delivery of National Systems (25/26) | Reasonable |
| 7 | Reports to Digital Services Management Group (DSMG) Reports to Digital Leadership Group (DLG) | Regular reports to Management Board and DDRI | Internal Audit: SBUHB 2526-21 Management of the Delivery of National Systems (25/26) Digital Transformation Review – Audit Wales (25/26) | Reasonable |
| 8 | Reports to bimonthly Digital Services Business Meeting Monthly Digital Risk Management Group / Risk Register Reports to Digital Services Management Group (DSMG) Reports to Information Governance and Cyber Assurance Group (IGCAG) Reports to Digital Leadership Group (DLG) Monthly Digital Finance meeting Monthly Capital Finance meeting Digital Project Review Group | Regular reports to Management Board and DDRI Quarterly Performance and Finance Review | Internal Audits: - SBUHB 2425-18 BI Strategy Implementation (24/25) (Substantial assurance)(Completed) - SBUHB 2425-19 Records Management (24/25) (Limited assurance)(Completed) - SBUHB 2425-18 Health records migration - SBUHB 2425-20 Data Quality (24/25) (Reasonable assurance) - SBUHB 2425-17 Clinical Coding (24/25) (Limited assurance) Digital Transformation Review – Audit Wales (25/26) Annual IG Toolkit submission | Reasonable |
| 9 | Reports to bimonthly Digital Services Business Meeting Monthly Digital Risk Management Group / Risk Register Reports to Digital Services Management Group (DSMG) Reports to Digital Leadership Group (DLG) Monthly Digital Finance meeting Monthly Capital Finance meeting | Regular reports to Management Board and DDRI Quarterly Performance and Finance Review | Digital Transformation Review – Audit Wales (25/26) | Reasonable |
|  | Current Overall Assurance Rating |  |  | Good |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | SBUHB - 2425-020 Data Quality (2024/25) – Key Finding Ref 1: “Whilst the Welsh Patient Administration System (WPAS) benefits from proactive and comprehensive data quality checks and monitoring, other clinical systems within the health board do not have equivalent oversight, with limited data quality reporting and dashboarding. Whilst Product Specialists are in place for clinical systems, data quality issues in these systems are primarily identified and reported by users which can lead to inconsistent data quality management, and delayed identification and resolution of data quality issues.” Recommendation (Key Finding Ref 1): “The Product Specialists carry out various data quality tasks as part of their day-to-day duties and data quality forms part of their job description. The data quality measures for the systems managed by Digital Services will be formalised, documented and monitored to allow reporting and therefore improved oversight. A process will be implemented to agree data quality measures for new systems/ modules or upgrades to existing systems and these will form part of the transition to business-as-usual following implementation. SBU has a mixed economy of systems managed centrally within Digital Services and others that are managed within specialty/ service areas, such as Radiology, Pathology, Cardiology, where digital subject matter experts manage, maintain and monitor the service-specific systems in those areas. The subject matter experts provide quarterly updates to the Digital Services Management Group (DSMG). Taking a pragmatic approach to reporting from the specialty/ service areas, Data Quality will be added to the standard reports that these services provide to DSMG.” | Management Response (Key Finding Ref 1): “Data Quality reporting to Information Governance Learning & Operational Group (IGLOG) for systems managed within the Clinical Systems and Data Quality team in Digital Services. Data Quality reporting to Digital Services Management Group (DSMG) for service specific clinical systems.” No further update as next IGLOG meeting is May 5th 2026. However, due to competing priorities in 2025/ 26 Q4 and some staff absence in the Clinical Systems and Data Quality team, the Data Quality reporting for systems managed by the Clinical Systems team will be presented to the following meeting of IGLOG. [WPAS Data Quality reporting went to IGCAG in April as an exception due to IGLOG not meeting] | Director of Digital | 30/06/2025 | Off Track |
| 2 | SBUHB - 2425-020 Data Quality (2024/25) – Key Finding Ref 2: “Linked to key finding 1, not all clinical systems within the health board are proactively monitored for data quality issues. Whilst we note that the Information Governance Learning & Operational Group (IGLOG) will receive quarterly validity and consistency reports, this pertains to WPAS data only. As IGLOG includes data quality as a key agenda item, it is essential that it receives data quality updates and improvement plans across all clinical systems, not limited to just one. This approach ensures comprehensive oversight and facilitates consistent monitoring and improvement of data quality across the entire clinical system landscape.” Recommendation (Key Finding Ref 2): “As per Key Finding 1, provide data quality updates and improvement plans: To IGLOG for systems managed within the Clinical Systems and Data Quality team in Digital Services, and to Digital Services Management Group (DSMG) for service specific clinical systems” | Management Response (Key Finding Ref 2): “IGCAG minutes reflecting Data Quality reporting to IGCAG for systems managed within the Clinical Systems and Data Quality team in Digital Services. DSMG minutes reflecting Data Quality reporting to Digital Services Management Group (DSMG) for service specific clinical systems.” DSMG minutes from Nov 5th 2025 approved on Feb 25th 2026. | Director of Digital | 30/06/2025 | Nearly Complete |
| 3 | SBUHB-2425-17 Clinical Coding (2024/25) – Key Finding Ref 3.1a: “The non achievement of the Welsh Government target for clinical coding is recorded on the Digital Services Risk Register. Actions have been identified to address the issues impacting on clinical coding, some of which are currently underway. However, there is no formal service improvement plan which sets out all the actions to be undertaken, resource and timescale and responsibilities. Without a formal plan in place the health board may find it hard to effectively move forward and track actions.” Recommendation (Key Finding Ref 3.1a): “A formal service improvement plan should be developed, and progress against this monitored. The plan should include actions to address all the issues and include responsible officers, targeted deadlines and an identification of resources required.” | Management Response (Key Finding Ref 3.1a): “Appointment of a Band 6 Service Improvement lead responsible for creation and enabling of a service improvement plan following recruitment freeze. The service improvement lead post has now been approved for advertisement on TRAC and is in the process of being actioned. | Director of Digital | 30/11/2024 | Nearly Complete |

Additional Comments

30/03/2026: Risk reviewed by Executive team on 30/04/2026 and description adjusted. Cross-reference to new CRR113 added. 12/04/2026: Register reviewed. Gaps in assurance and related corporate risks updated. Records Management key findings 3.2 action has been completed (and removed from action plan above). 13/05/2026: Following discussion at Executive Board, the current risk score has been reduced from 20 to 15.

| Risk ID Number SRR-4.1 | Risk Label – Staff Health & Wellbeing and Organisational Performance Risk Description – There is a risk of a negative impact to staff wellbeing due to the psychological and physical impact of the sustained pressure of work, continued transformation of services and the challenge in reconciling continued high levels of clinical and non-clinical demand with available resources. This could lead to high levels of sickness absence, reduced organisational and individual effectiveness, higher staff turnover and staff burnout. This is exacerbated at times of industrial action which remains a risk in 2025/26. |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | The health board is a great place to work where all staff feel valued and work together towards a common goal |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 3 | 4 | 12 |  | Lead Director / Risk Owner | Director of Workforce & OD |
| Current Score | 4 | 4 | 16 |  | Monitoring Committee | Workforce & OD Committee |
| Target Score | 2 | 4 | 8 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 2025 | Dec 2025 | Feb 2026 | Apr 2026 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 12 | 12 | 16 | 16 |  |  |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |
| 3 (843) | Recruitment of Consultant Medical and Dental Staff Due to national shortages, there is a risk that that the health board will be unable to recruit consultant medical & dental staff into particular hard-to-fill roles which may result in difficulties fulfilling rotas on all sites, and adverse impact upon patient safety, service provision, quality and financial matters. | 16 |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | People Strategy |
| 2 | Staff Health & Wellbeing Plan |
| 3 | Managing attendance at work national policy |
| 4 | Sickness absence reporting |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | Strategy progress reports monitored through Management Group | Strategy progress reports assured through Workforce & OD Committee |  | Reasonable |
| 2 | Plan developed through Staff Health & Wellbeing Group | Plan approved through Management Board | Plan assured through Workforce & OD Committee | Limited |
| 3 | Adherence to policy monitored through monthly performance meetings | Adherence to policy assured through Management Group | Adherence to policy assured through Workforce & OD Committee | Limited |
| 4 | Trend data included in Integrated Performance Report for review by Management Group | Trend data included in Integrated Performance Report assured through Workforce & OD Committee | Integrated Performance Report assured through Board | Reasonable |
|  | Current Overall Assurance Rating |  |  | Moderate |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Gaps in recording and reporting of return-to-work interviews | IT solution being explored | DW&OD | 30/9/25 | Risk & action subject to review by Lead |
| 2 | Gaps in reporting on staff who have met the triggers/who are on formal stages of the policy | Reporting solution being explored | DW&OD | 30/9/25 | Risk & action subject to review by Lead |

Additional Comments

23/02/2026 R&A note: DOWOD discussed proposed changes to WOD risks for SRR 2026/7 with an undertaking to develop further for April 2026 alongside which current entries to be refreshed or replaced as part of that process. 30/03/2026: Risk reviewed by Executive Team. Register content is subject to further consideration by Director of Workforce & OD.

| Risk ID Number SRR-4.2 | Risk Label – Leadership and Management Risk Description – Without compassionate and effective leadership at all levels of the organisation there is a risk that staff will lack the confidence to enable informed decision-making at the appropriate level to continuously improve and transform our services, resulting in a lack of commitment, poor staff engagement, poor communication, deterioration of staff wellbeing, and difficulty in recruiting and retaining the staff we need. |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | The health board is a great place to work where all staff feel valued and work together towards a common goal |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 4 | 3 | 12 |  | Lead Director / Risk Owner | Director of Workforce & OD |
| Current Score | 4 | 3 | 12 |  | Monitoring Committee | Workforce & OD Committee |
| Target Score | 4 | 2 | 8 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 2025 | Dec 2025 | Feb 2026 | Apr 2026 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 12 | 12 | 12 | 12 |  |  |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | People Strategy |
| 2 | Leadership Development Plan |
| 3 | Joint Leadership Network (with Hywel Dda) |
| 4 | Management Development Plan |
| 5 | Staff Survey |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | People Strategy Highlight report reviewed through Management Group | People Strategy Highlight Report assured through Workforce & OD Committee |  | Reasonable |
| 2 | Leadership Plan approved through Management Group | Leadership Plan assured through Workforce & OD Committee |  | Limited |
| 3 | Terms of reference and highlight reports reviewed through Regional Steering Group | Progress on leadership network assured through Regional Joint Committee |  | Limited |
| 4 | Management Development Plan approved through Management Group | Management Development Plan approved through Workforce & OD Committee |  | Limited |
| 5 | Staff Survey results reviewed through Service Group Boards with local action plans developed for areas requiring improvement | Health board level results reviewed through Management Board with organisational action plan developed for top 3 areas requiring improvement | Staff survey results and action plans assured through Workforce and OD Committee | Reasonable |
|  | Current Overall Assurance |  |  | Moderate |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | National leadership offer still in development delaying the refresh of the local leadership and management development plans | Refreshed leadership and management development plans to be considered by Management Group in August 2025 | Director of WOD | 31/08/25 | Risk & action subject to review by Lead |

Additional Comments

23/02/2026 R&A note: DOWOD discussed proposed changes to WOD risks for SRR 2026/7 with an undertaking to develop further for April 2026 alongside which current entries to be refreshed or replaced as part of that process. 30/03/2026: Risk reviewed by Executive Team. Register content is subject to further consideration by Director of Workforce & OD.

| Risk ID Number SRR-4.3 | Risk Label – Culture, Values & Behaviours Risk Description – If we do not foster a cohesive culture in line with our organisational values, there is a risk that our people will not feel a sense of belonging, not feel valued in their roles, not understand how they contribute to organisational success, and will be unable to speak up in confidence, resulting in a negative impact on staff experience. |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | The health board is a great place to work where all staff feel valued and work together towards a common goal |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 4 | 3 | 12 |  | Lead Director / Risk Owner | Director of Workforce & OD |
| Current Score | 4 | 3 | 12 |  | Monitoring Committee | Workforce & OD Committee |
| Target Score | 4 | 2 | 8 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 2025 | Dec 2025 | Feb 2026 | Apr 2026 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 12 | 12 | 12 | 12 |  |  |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | Health board values and behavioural framework |
| 2 | One Bay Way Organisational Standards |
| 3 | Staff survey feedback and action plans |
| 4 | Freedom to speak up service |
| 5 | Employee relations (managed through Social Partnership Forum) |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | Values and behavioural framework developed through staff engagement | Embedding of values and behaviours assured through Workforce & OD Committee | Values and behavioural Framework agreed by Board | Reasonable |
| 2 | Organisational standards (One Bay Way) developed through staff engagement | Embedding of organisational standards assured through Workforce | One Bay Way Organisational Standards agreed by Board | Limited |
| 3 | Staff survey plans developed at Service Group and health board level | Staff survey plans approved through Management Group | Staff survey plans assured through Workforce & OD Committee | Reasonable |
| 4 | Regular Freedom to Speak up Reports to Management Group | Freedom to Speak Up Service assured through Workforce & OD Committee | Speak up in confidence culture assured through Board | Reasonable |
|  | Current Overall Assurance Rating |  |  | Moderate |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance What are we going to do, by when, to further manage and mitigate this risk? | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Values well embedded across the health board. Further work to do to embed associated behaviours | Refresh and relaunch of behavioural framework | Director of W&OD | Jan 2026 | Risk & action subject to review by Lead |
| 2 | Colleagues do not understand the concept of One Bay Way | Refresh, relabel and relaunch One Bay Way as organisational standards | Director of W&OD | April 2027 | Risk & action subject to review by Lead |
| 3 | Lack of benchmark data included in current Freedom to Speak up Reporting | Benchmark data to be included | Director of W&OD | Oct 2025 | Risk & action subject to review by Lead |

Additional Comments

23/02/2026 R&A note: DOWOD discussed proposed changes to WOD risks for SRR 2026/7 with an undertaking to develop further for April 2026 alongside which current entries to be refreshed or replaced as part of that process. 30/03/2026: Risk reviewed by Executive Team. Register content is subject to further consideration by Director of Workforce & OD.

| Risk ID Number SRR-5.1 | Risk Label – Recovery & Sustainability Risk Description – If we fail to manage our costs effectively, whilst optimising productivity and effectiveness, then we will not return to financial balance safely. This will result in poor use of public funds, and an inability to provide sustainable services for our patients. |
| --- | --- |

| Risk Score | Consequence | Likelihood | Overall Score | Trend | Strategic Objective | The health board is a resilient, sustainable and responsible organisation |
| --- | --- | --- | --- | --- | --- | --- |
| Inherent Score | 5 | 5 | 25 |  | Lead Director / Risk Owner | Director of Finance & Performance |
| Current Score | 5 | 5 | 25 |  | Monitoring Committee | Performance & Finance Committee |
| Target Score | 5 | 3 | 15 | N/A | Risk Appetite | T.B.C. |

| Risk Score Over Time | Nov 2025 | Dec 2025 | Feb 2026 | Apr 2026 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 25 | 25 | 25 | 25 |  |  |  |  |  |  |  |  |  |  |  |

| Related Risk on Corporate Risk Register Linked or associated risks which sit in the register immediately below the Strategic Risk Register |  |  |
| --- | --- | --- |
| Risk ID | Description | Score |
| 92 (3444) | Finance: Forecast Deficit Risk Forecast deficit is not met due to insufficient progress on run rate reduction, and the saving targets required across all areas are not achieved. | 25 |
| 93 (3448) | Finance: Reduced Capital Funds Reduced National NHS funds available for major capital schemes requiring a restricted Capital Plan for 2025/26. | 12 |

| Key Controls |  |
| --- | --- |
| Control Ref | Control |
| 1 | Annual Accountability Letters and Budgetary Management Framework |
| 2 | Recovery & Sustainability Board oversight of the identification and delivery of strategic long terms savings programmes, supported by the establishment of the Delivery Unit from April 2026. |
| 3 | Face to Face Budget Holder training – development for 2026/27 specifically for the 68 Budget Holders. |
| 4 | Continued transparent exchange of position with NHS Wales Performance & Improvement and Welsh Government |
| 5 | A financial planning and reporting process is in place which dovetails with the wider IMTP production timetable. These provide a schedule of planning activities intended to support the production of a financially balanced and sustainable IMTP, aligned to the statutory requirements of the Health Board. |

| Assurance on Control |  |  |  |  |
| --- | --- | --- | --- | --- |
| Control Ref | 1st Line Assurance | 2nd Line Assurance | 3rd Line Assurance | Strength of Control |
| 1 | Finance-specific monthly performance meetings held between Exec Directors and Service Group Directors receives assurances from SGD on development of plans and in-year delivery of plans and savings. |  |  | Reasonable |
| 2 |  |  | WG monthly monitoring returns and letters, signed by CEO and DoF. | Reasonable |
| 3 |  | Reports received and scrutinised by P&F Committee, including from the Recovery & Sustainability Board, and PFC reports onward 3As reports to the Health Board |  | Reasonable |
| 4 |  |  | Review of annual accounts by Audit Wales, and subsequent issue of ISA 260 | Reasonable |
| 5 |  |  | Audit Wales Report – Cost Savings Arrangements (2024) | Limited |
| 6 |  |  | A&A Report – Savings Programme (2023) | Reasonable |
| 7 |  |  | Internal Audit Draft Report – Budgetary Management | Reasonable |
|  | Current Overall Assurance Rating |  |  | Good |

| Gaps in Control and/or Assurance |  | Actions to Address Gaps in Control and/or Assurance | Lead Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- |
| 1 | Signed/Agreed Accountability Letters are received after the start of the financial year | Continue to enhance the process to achieve a position whereby Accountability Letters are signed off/agreed prior to the commencement of the financial year. | Director of Finance & Performance | 31/03/2026 | Action subject to review by Lead |

Additional Comments

30/03/2026: Risk reviewed by Executive team on 30/04/2026 and description adjusted. 13/05/2026: Risk reviewed and Controls updated.

Key / Convention / Glossary

| Strength of Control |  | Level of Overall Assurance |
| --- | --- | --- |
| Substantial – The identified control(s) provide a strong mechanism for controlling the risk. Few matters require attention, which are advisory or compliance in nature. |  | Significant – Key governance, risk management and control processes in place provide significant assurance that the risk(s) is/are being managed effectively. Evidence demonstrates that systems and processes are being consistently applied and implemented. Outcomes are consistently achieved across all relevant areas. |
| Reasonable – The identified control(s) provide a reasonable mechanism for controlling the risk, albeit there is scope to strengthen this further. Some matters require management attention in control design or compliance. |  | Good - Key governance, risk management and control processes in place provide a good level of assurance that the risk(s) is/are being managed effectively. Evidence is available to demonstrate that systems and processes are generally being applied and implemented, but no across all relevant areas. Outcomes are generally achieved, but with inconsistences in some areas. |
| Limited – The identified control(s) provide only limited/partial mechanisms for controlling the risk. There are notable weaknesses which require management attention. |  | Moderate – Key governance, risk management and control processes in place provide moderate assurance that the risk(s) is/are being managed effectively. Evidence is available to demonstrate that systems and processes are being applied, but is insufficient to demonstrate implementation across all relevant areas. There is some evidence that outcomes are being achieved, but this is inconsistent and/or there are risks to current performance. |
| Unsatisfactory – The identified control(s) is/are not effective in providing a mechanism for controlling the risk. Action is required to address the whole control framework in this area. |  | Weak – Key governance, risk management and control processes in place provide only weak assurance that the risk(s) is/are being managed effectively. There is only limited evidence available that systems and processes are being applied or implemented. |

Lines of Assurance

First - This is the internal control environment put in place by Managers. It will typically include reports which detail their plans, performance monitoring data, and the results of local checks and reviews of controls within departments performing relevant day-to-day operational activities. Examples would include: - Results of compliance reviews undertaken within Departments/Functions, and reported to senior management - Progress and/or performance reports received by SDG Boards / Committee Sub-Groups

Second – This level of assurance is often referred to as organisational oversight. It is typically provided by Health Board corporate departments and functions which do not directly manage or deliver specific services, but which oversee and report on how controls are operating, thus providing a greater separation from day-to-day management. Typically, this level of assurance is typically provided to the Board or one of its committees (which allows Independent Members to bring an additional level of challenge and scrutiny), as well as to senior management groups (e.g., Management Board). Examples would include: - Reports on the results of Infection Control Audits undertaken by the IP&C Team - Reports on Fire Safety Audits - Progress and/or performance reports received by the Board or one of its committees

Third – This is independent assurance, which typically comes from outside the organisation. Examples would include reports received from: - NWSSP Audit & Assurance - Audit Wales - Healthcare Inspectorate Wales - Llais - Royal colleges

| Glossary of Register Fields & Their Use |  |
| --- | --- |
| Table / Field | Considerations for completion |
| Key Controls | What key controls/systems/processes/governance mechanisms do we already have in place to manage this risk? |
| Assurance on Control | What information do we have about the adequacy, effectiveness and application of each of our controls, where is it coming from, and what is it telling us? |
| Current Overall Assurance Rating | The Lead Director and/or nominated representative should state the overall level of assurance that can be taken and given regarding the effective management of this risk, having considered all of the information available regarding the adequacy, effectiveness and application of each of the controls in place, and any gaps identified. A convention is provided. |
| Gaps in Control and/or Assurance | Do we require further assurance that the key controls / systems / processes / governance mechanisms we have in place are working effectively? What more do we need to do to control this risk, that we are not already doing? |
| Actions to Address Gaps in Control and/or Assurance | What are we going to do, by when, to further manage and mitigate this risk? |

This column indicates the Committee to which the risk is assigned, the last meeting to received it (bold) and the version of the SRR received. Entries without dates reflect Committee yet to receive the SRR.

This risk has been re-numbered (previous reference was 3.1) and realigned to objective.