Area Plan and

Action Plan Priorities

for 2025-2026

UPDATE – December 26

Region: West Glamorgan Regional Partnership

Contact: west.glamorgan@swansea.gov.uk      Website: www.westglamorgan.org.uk

Contents

Vision and Aims of the Partnership	1

Communities and Older People	2

Carers Partnership Board	6

Dementia	8

Wellbeing and Learning Disability	10

Emotional Wellbeing and Mental Health	12

Children and Young People	16

Neurodiverse Programme	19

Regional Commissioning Programme	21

# Vision and Aims of the Partnership

| West Glamorgan developed a co-produced set of vision and aims at its inception that the region continues to follow: - We will drive transformational improvements in wellbeing, health and care for the populations we serve through better practice, better services, better technologies and better use of resources. - We will change the way that we work with citizens away from paternalistic care to shared responsibility and co-production. - We will secure the delivery of seamless care which will meet the outcomes that matter to the people we serve and support through integration, earlier intervention and prevention - We will manage our common resources collaboratively and pool resources wherever we can. - We will have a single and simple governance structure covering Public Service Boards, the Regional Partnership Board and sub-structures for the region. | The Regional Programme exists to: - Drive continuous improvement in wellbeing, health and care in partnership. - Work in co-production with partners from the third sector, voluntary sector, private sector, statutory sector and our citizens to secure more seamless care in communities. - Cross service boundaries to develop better, more seamless care. - Promote a healthier region through asset-based communities. - Make sure our agencies put people at the heart of wellbeing, health and care transformation, integration and prevention. - Help to make sure that people live healthier and happier lives - Deliver the Regional Transformational Strategy and Plan |
| --- | --- |

| Programme | Area Plan Priority |  | Models of Care Supported |  | Programme Lead |
| --- | --- | --- | --- | --- | --- |
| # Communities and Older People | - Transforming Health and Care Services at Home - Strengthening Communities |  | - Place Based Care – Prevention and Community Co-ordination - Place Based Care – Complex Care Closer to Home - Home from Hospital |  | Dave Howes and Craige Wilson |
| Overview of the Programme Our Communities and Older People programme has an ambition to transform health and social care with innovative, financially sustainable models. We have a vision where every community member and older adult thrives in safety, health, and prosperity. We will achieve this though partnering with community & older people, third sector and statutory partners, working hand-in-hand with the communities to design services that truly meet their needs. Part of our efforts involve creating a Prevention and Early Intervention Model designed to help individuals remain in their communities longer, without needing statutory services. At the other end of the spectrum, we support individuals in being safely and promptly discharged from statutory services with the support of the community. Together, we will build a brighter, healthier future for all |  |  |  |  |  |
| Workstream |  | Brief Description of Workstream |  | Progress to Date |  |
| Regional Performance and Finance of Section 33 Intermediate Care / Integrated Community Care System |  | The workstream oversees the financial performance and service delivery for Section 33 services, by reviewing budgets, actuals, and key metrics like referrals, discharges, and reablement outcomes. The group also evaluates the full scope of funding sources—Core, Regional Integration Fund, 6 Goals Funding, Further Faster, and Allied Health Professional Funding—to ensure resources are used effectively |  | Project Aim: Deliver comprehensive financial and performance data to support informed strategic decision-making Finance Monitoring - Map financial contributions and resources across partners, ensuring figures match and are consolidated for board consideration. - Support Decision-Making and Continuous Improvement. - Identify and address financial risks, funding uncertainties, and operational challenges, escalating issues to senior leaders as needed The initial version of this work was presented to the Community and Older People’s Board in October, and efforts are ongoing to further refine and enhance the information in preparation for the December board meeting Performance Monitoring Dashboard - A PowerBI dashboard is being developed to support service leads and directors in monitoring service performance. - We aim to Provide robust data and performance dashboard to inform strategic decisions, budget planning, and service redesign. - Maintain transparency in data reporting, ensuring all partners have access to comprehensive data for joint planning. - Track KPIs such as referrals, discharges, length of stay, readmission rates, and other service metrics to evaluate service/operational impact An initial preview of the data dashboard will be presented to the Community and Older People’s Board in December |  |
| Monitoring and Oversight Joint Equipment Store |  | This workstream monitors the performance and the financial aspects of the Joint community equipment stores (CES) |  | There is currently a review the CES the immediate scope of review confirmed: Immediate focus on scrutiny of equipment spend & development of options to increase required investment from partners and/or reshape of regional equipment store ‘offer |  |
| Development of the Prevention and Early Intervention Model |  | The workstream aims to collate what early intervention provisions are currently in place across the region. Create a regionally agreed definition and vision Develop an optimal model of early intervention services for older people, delaying and reducing the need for statutory interventions. |  | - A Task and Finish Group has been established to identify themes to pilot data collection and analysis across the region to demonstrate the benefits of early help. The group will pilot across both geographical areas to understand the themes coming through from the population as part of a research quadrant into the community. - The group meet monthly to analyse / verify data from July 2025 – January 2026 - Cross reference themes to a model of prevention work being undertaken by the lead for Mental Health and Wellbeing. It has been recognised that, for an early intervention model to be truly effective, it must incorporate all population cohorts. Subject to approval at the next Communities and Older People’s Board, the workstream will initiate the process of aligning the model to establish a consistent and standardised approach across all programmes |  |
| Pathways of Care Delays Action Plan and Implementation |  | This project aims to Review the status of Pathways of Care Delay Actions Plan. By doing this we can: - Ensure accountability by holding service leads responsible for the timely completion of their assigned actions. - Identify and address challenges that may prevent the timely execution of actions. - Monitor progress against key performance indicators (KPIs) to evaluate the effectiveness of actions. - Facilitate collaboration across departments to ensure alignment and efficient problem-solving to address operational issues. - Manage risk effectively by identifying proactive solutions. - Reviewing timelines, milestones, and deliverables to address care delays. |  | The programme continues to progress across four key deliverables aimed at improving operational performance and service outcomes: Refreshed Action Plan to Reduce POCD - Reviewed and updated by all partners in July 2025; presented to OP & C for approval. - Key actions include LOS reviews, EDD compliance audits, P3 readmission analysis, Board Round refresh, and deep dives into delays related to family support, assistive technology, and equipment. Digital Dashboard for Daily Reporting - Improvements shared at DPRG in September; 'On Hold' status removed and reclassified as 'Incomplete'. - RRR tab scheduled to go live in December. 12-Week MH & LD Improvement Plan (Post-MADE Event) - Weekly Task & Finish group concluded; plan signed off by all partners. - Delivery commenced end of September. Social Services Allocation Improvements - Weekly deep dives underway to drive targeted improvements. - Identified need for daily FAC Panel in Swansea and proportionate assessment application in NPT/Gorseinon Hospital. Governance - Escalation of Issues: Any unresolved or red-rated actions are escalated to senior leaders (CEOs, COOs, Directors of Social Services) via weekly reports. Updates are also shared with the UEC and Communities & Older Peoples Boards. |  |
| D2RA Processes |  |  |  | The programme is progressing across four key workstreams aimed at establishing a sustainable ID2RA hub and improving discharge pathways: Establishing the Interim ID2RA Hub - Significant progress made in identifying the resources required to operate the interim hub. - Key achievements include: - Development of a new SOP covering both front and back door processes. - Agreement on a new data collection framework and KPIs to measure volume, efficiency, and impact. - Completion of a needs assessment to define essential resources. - Feedback provided to Directors regarding the requirements for a full multi-disciplinary team (for discussion at C&OP Board on 23 Sept). Trusted Assessor Model Development - Professionals identified to undertake the Trusted Assessor role; training programme in development. - Trusted Assessor Form approved by C&OP Board. - Urgent updates agreed regarding RRR and 'On Hold' status. - Discussions underway with digital colleagues to implement the form electronically. Policies, Procedures & Communications - Draft documents under review for final sign-off, including Overarching discharge policy and Patient choice and discharge guidance - P&P Subgroup now aligned with HB’s Board Round Review Group to ensure regional integration. D2RA Pathway Processes - Map current D2RA pathways and processes, focusing on efficiency and resource use. - Use process mapping workshops to identify improvements and operational actions for each pathway. - Ensure changes that require executive sign-off are escalated to the appropriate board. - Analyse current and projected demand for Discharge to Recover and Assess (D2RA) services, considering demographic trends and service pressures. - Review and map existing capacity across intermediate care, reablement, and discharge services to identify gaps and opportunities for improvement. - Determine the resources (staff, infrastructure, funding) required to meet demand and ensure sustainable service delivery. - Establish further pathways to facilitate the discharge of individuals presenting with specialised needs, including those related to family disputes and housing or homelessness. |  |
| Communities and Older People Aging Well Strategy: “Stronger for Longer” |  | The aim of this strategy is to unlock the potential of the communities within the West Glamorgan region to support this cohort of individuals to gain knowledge of what is available to them to help them to maintain a level of wellbeing and independence wherever they live. This strategy will help steer the work of the Communities and Older People Programme and help focus the work on the most urgent priorities |  | - Engagement with the community has been undertaken to gain the knowledge required to complete a purposeful strategy for the region. - A vision and themes have been agreed. - Draft document shared with the Communities and Older Peoples Board in October 2025 |  |
| Unscheduled Care Board |  | The UEC board is focused on creating a clear workstream group with defined aims and objectives, aligning with strategic priorities, and providing updates on the UEC work through presentations and reports. The board also addresses funding and performance monitoring issues related to urgent and emergency care. The UEC board updates the C&OP board to keep everyone informed about ongoing work and prevent duplicated efforts or resources. |  | The UEC programme continues to deliver across multiple workstreams aligned with Ministerial Priorities, GIRFT, and E/6G initiatives. Summary reports on all UEC activity are available upon request. Key Work Areas and Progress - Ambulance Patient Handover & ED Quality - Linked to the 45-minute handover target. - Event held on 12 September 2025 supported by the 4S Handover Taskforce (WG/NHS Executive). - Acute Front Door Frailty Service - OPAU now operational. - National focus on expanding to 7-day provision with direct pathways and roving frailty teams supporting SDEC and SPOA. - SPOA for UEC - Front-end triage and signposting to implement ‘call before convey’. - Builds on SDEC and WAST stack review with co-located MDTs. - Funding secured to support staffing (initially via overtime) with aspirations for 7-day coverage. - Optimal Hospital Flow - National framework rollout includes SAFER Board rounds, R2G, D2RA pathway updates, and deconditioning prevention. - Project group formed to reinvigorate previous efforts and improve data capture. - Community-Based Falls Response - Funding secured until end of financial year. - Procurement underway (St John Ambulance with first aiders). - Lifting cushions distributed to care homes. - Exploration of enhanced therapies to support Level 2 falls service. - High Intensity Users at Front Door - Funding secured to support officer role at front door. - Focus on identifying frequent attenders and developing alternative pathways. PDSA Activity – MGH (Anglesey Ward) - Improvements include: - Streamlined ED and AMU assessments. - Enhanced specialty access and response. - Increased SDEC capacity including ‘1-day SDEC’. - Criteria-led discharge and ‘Your Next Patient’ initiative. Impact: - Ambulance handover delays <45 minutes improved by 155% - Average handover time improved by 82.2% - ED breach reduction of <63% (Source: Joint Commissioning Committee) |  |

| Programme |  | Area Plan Priority | Models of Care Supported |  | Programme Lead |
| --- | --- | --- | --- | --- | --- |
| # Carers Partnership Board |  | Strengthening Communities | - Community Based Care – Prevention and Community Coordination (MC1) - Community Based Care – Complex Care Closer to Home (MC2) - Promoting Good Health and Wellbeing (MC3) - Home from Hospital (MC5) |  | Gaynor Richards |
| Overview of the Programme The Regional Carers Programme one of six population boards sitting within the West Glamorgan Region. The Programme oversees the implementation of the Regional Carers Strategy which was coproduced with unpaid carers across the region and launched in April 2023. The vision of the Carers Strategy represents the future we aspire to, where we recognise the contribution of unpaid carers to our society. The Strategy aspires to build upon previous successes and make changes where needed to transform services, enabling unpaid carers across the region to have fulfilling lives based on what matters to them. We plan to do this by actively identifying unpaid carers, to listen, respect, and properly support unpaid carers to not just continue their caring role but to enable them to have fulfilling lives. We are refreshing the current Strategy for post April 2026, to refocus efforts across the region and ensure we are meeting the needs of unpaid carers. |  |  |  |  |  |
| Workstream | Brief Description of Workstream |  |  | Progress to Date |  |
| Access to Services | Learning from feedback from the 24/25 Short Breaks Grant Scheme, continue to review and further transform the current respite/ short breaks provision across the region, Undertake research to understand the respite provision on offer across the country and compare this to the regional offer. |  |  | The Short Breaks Grant Scheme remains an integral part of the Programme. Unpaid carers consistently state that a break from caring is a key priority to maintaining their wellbeing and their ability to continue to care. Feedback from the grant offered in 24/25 has been considered and slight amendments made to the process for 25/26. Respite – requires a scoping exercise in 25/26 to understand the remit and expectations. This continues to be delivered as part of the Programme. |  |
|  | Develop guidance for employers across the region to raise awareness of the needs of unpaid carers in the workplace and offer practical solutions for how they can support them. |  |  | This will roll over into the refreshed Strategy 2026-2031. Work in this area is already underway with the three statutory partners developing support for unpaid carers in their workforce, however this needs further work. SBUHB have now appointed a ‘Carers Champion’, Liz Ricks who has also taken the role of Chair of the regional Carers Partnership Programme and who will drive this forward. |  |
|  | Review, promote and improve the access to services for carers (MC3) in Primary Care settings such as Pharmacies, Opticians and Allied Health Professions |  |  | The pilot continues in the Upper Valleys Cluster. Pharmacies have all received ‘Care Aware’ training and materials are being produced which will raise awareness of the role of unpaid carers and sign post them to support services. Once the Pilot is completed, the approach will be rolled out across all Pharmacies in the Upper Valleys Cluster. |  |
| Information, Advice, Assistance & Awareness including Comms & Engagement | Ensure accurate and high-quality information, advice and assistance (IAA) (MC1) by developing an unpaid carers handbook. The handbook will compliment similar resources which are on offer via national organisations and will be offered to unpaid carers (in the 1st instance) when they become unpaid carers for the first time, usually in a hospital setting). |  |  | Work continues to map out the information needed in a carers handbook and which form this should take (digital or digital and physical). A leaflet has been produced to be shared with unpaid carers in hospital settings which will provide high level IAA and signpost carers to where they can access further support. This has been approved by the relevant customer focussed channels and is now being printed. This approach will need to be piloted, wards have been identified for the pilots in Morriston and NPT Hospitals. There is a slightly different approach being designed for young carers to make the information more accessible and meaningful to them. Carers will have their own space on the regional Sorted; Supported web platform in due course. |  |
|  | Raise awareness of the essential role of carers across the region, including the challenges and issues facing carers today (MC3). |  |  | The Unpaid Carers event held on 18th September 2025 at the Swansea.com Stadium brought together carers, professionals, and community partners to explore how to turn vision into action for unpaid carers across the region. The event featured a range of breakout sessions, including “Bridging the Gap,” which focused on understanding barriers faced by young carers—many of whom may not recognise themselves as carers. Discussions highlighted the need for improved identification, support, and awareness, especially within education and health settings. Attendees shared insights on the emotional and practical challenges carers face, and the importance of co-produced solutions that reflect lived experience. Feedback from the event emphasised the value of networking opportunities and the visibility of local resources through information stalls. Carers appreciated the chance to connect with others in similar roles and to contribute to shaping future service delivery. The event also reinforced the importance of regional collaboration and the role of the Carers Partnership Board in driving forward meaningful change. The atmosphere was described as inclusive and energising, with a clear commitment from all involved to continue building a system that recognises, supports, and empowers unpaid carers across West Glamorgan. This is all feeding into the refreshed Unpaid Carers Strategy which will be ready for consideration and approval in March 2025. |  |
| Future Funding for Unpaid Carers | Develop a revised approach to the current funding (commissioning model) which will be developed in line with lessons learned from the EWMH Programme: New Commissioning Workstream lessons learned. |  |  | This is on hold for the moment to enable learning from the EWMH Programme. |  |

| Programme |  | Area Plan Priority | Models of Care Supported |  | Programme Lead |
| --- | --- | --- | --- | --- | --- |
| # Dementia |  | - Transforming Mental Health Services | - Community Based Care - Prevention and Community Coordination - Promoting good emotional health and wellbeing - Complex Care Closer to Home |  | Stephen Jones |
| Overview of the Programme The vision for the Dementia programme is that people with dementia and their carers can access the services and support when, where and how they need it across health, social care and voluntary services. The focus of the programme is the implementation of the 20 All-Wales Dementia Standards. The All-Wales Dementia Care Pathway and Standards were published in 2021 following extensive engagement with 1800 individuals living with dementia, unpaid carers, voluntary organisations and health care professionals across Wales. The work has been led by Improvement Cymru as part of the Dementia Care Programme and directed by the requirements of the Dementia Action Plan for Wales, overseen by the Welsh Government Dementia Oversight Implementation and Impact Group (DOIIG) The pathway includes 20 standards that represent what people believe will make a positive difference to dementia care in Wales. The standards sit within four themes: Accessible, Responsive, Journey, Partnership & Relationships. |  |  |  |  |  |
| Workstream | Brief Description of Workstream |  |  | Progress update – 22nd August – 3rd October |  |
| Regional Strategy, Community and Connectors | - Review the feedback from the two pilot areas of the local listening campaigns carried out in 24/25. - Carry out engagement for a regional strategy that will inform the priorities for people with dementia and their carers - Produce resources on brain health and modifiable risk factors for circulation - Development of a network of organisations that support people with a Dementia diagnosis to be involved in future coproduction opportunities - Continue to pilot the role of Dementia Connector across the region to support people to make the connections into services that help with their health and wellbeing. - Continue to build links with community groups that can support individuals with a dementia diagnosis - Facilitate a lesson learnt exercise on the Dementia Connector pilot (March 2026) |  |  | - Additional copies of the Brain Health Booklet to be printed and distributed across the region - Easy read version of the booklet also in development and will be made available alongside the above. - QR code for online version of the booklet to be distributed to partner comms teams and easy read version in development; also looking at providing copies in different languages - Virtual Network has been set up – 30 organisations signed up so far - NHS Exec Performance and Improvement Team running a showcase event on the 12th of February in Cardiff, each region will have a space to demonstrate best practice and learn from other regions – this date is being delayed to April due to the issues experienced with planning the event (by the organisers) - Welsh Government consultation on next Dementia Action Plan to be circulated before Christmas - Regional Strategy engagement questionnaire ready for circulation - Planning for regional engagement event in progress - SAB1 gave direction that the Listening Campaigns are not providing the region with any new information and that we need to move on to considering what we know, and what we can do to meet needs and change experiences of PLWD and their carers. - A short term dementia grant scheme has been circulated which is ring fenced to existing RIF funded 3rd sector dementia projects and will focus on providing basic training to carers and family members of PLWD who are currently in the OPAU in Morriston Hospital, with a view to this basic training increasing confidence in family members and supporting packages of care, thus assisting with getting people out of hospital and back home as quickly as possible. This pilot will run until 31st March 2026. Applications for this grant scheme close on Monday 8th December 2025. |  |
| Memory Assessment | - Develop a Memory Assessment Pathway and Standard Operating Procedure for all staff to follow - Work with teams to ensure people with Learning Disabilities have access to the Memory Assessment Service. - Implement a process to ensure individuals that have received a diagnosis is referred to a Dementia Connector immediately |  |  | - SAB1 approved the unallocated funding bid of £45,000 to undertake a review of the Memory Assessment Service across the region. Work is underway to ensure this review is able to start as soon as possible – the proposal is to commission external agency to deliver the revised pathway and standard operating procedure, utilising current unallocated funding (ring fenced) - Swansea University are working with the Dementia Hwb on the demand for a dedicated MCI clinic for the region - SBUHB clinics have been involved in the Memory Assessment toolkit pilot - Area 4 has completed a piece of work on quality improvement on post diagnostic support that will be scaled up - Continuing to respond to the requirements of the National Dementia Audit |  |
| Hospital Charter | The charter will be publicised in each hospital across the region demonstrating how the health board have promoted a person-centred, rights-based approach. |  |  | - No update |  |

| Programme |  |  | Area Plan Priority |  | Models of Care Supported |  |  |  |  | Programme Lead |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # Wellbeing and Learning Disability |  |  | Transforming Complex Care |  | - Community based care –prevention and community coordination (MC1) - Community based care – Complex Care closer to home (MC2) - Promoting good emotional health and wellbeing (MC3) - Home from Hospital (Home First) (MC5) - Accommodation Based Solutions (MC6) |  |  |  |  | Amy Hawkins |
| Overview of the Programme The Wellbeing and Learning Disability Programme is one of six population boards sitting within the West Glamorgan Region and is underpinned by its recently launched five-year regional co-produced Learning Disability Strategy. The West Glamorgan Regional Partnership Board ratified the strategy on the 12th of December 2023. The Strategy is broader than RIF, with RIF enabling system change alongside supporting changes in core service delivery. Vision Statement “In the West Glamorgan Region, people with a learning disability have the right support to make their own choices to achieve a happy, healthy life that is meaningful to them. They have opportunities to learn, work and actively contribute to their communities” The Wellbeing and Learning Disability Programme aspires to build upon previous successes and make changes where needed to transform services, enabling people with learning disabilities to have fulfilling lives based on what matters to them. We plan to continually learn from those with learning disabilities throughout the lifetime of the strategy. |  |  |  |  |  |  |  |  |  |  |
| Workstream |  | Brief Description of Workstream |  |  |  |  |  | Progress Update - 22nd August – 3rd October |  |  |
| Transport |  | - Workshop coproduced held in 2024 to review what transport issues people with learning disabilities are impacted by across the region and what can be done to make transport better |  |  |  |  |  | - No update – work has now completed and workstream is closed |  |  |
| Getting the Right Care and Support |  | - Review the easy read information available to help people with a Learning Disability access to health and social care services - Continuation of people with a Learning Disability being fully involved in developing their care and support plans, as required under the SSWB (Act) 2014 - Work with people with learning disabilities on what support they want to receive at a community-based level, including how and when it should be provided - Increase the number of people with a Learning Disability received an annual health check |  |  |  |  |  | - Integrated Working. Plan on a page signed off in July board meeting. This work sits alongside the Regional Commissioning Board Pooled Funds work. - Easy Read: Task and Finish Group. The first task and finish Group was held on 2nd October. The meeting involved a good selection of partners involved in Learning Disability services across the region. While the group is not yet quorate, key partners from the Health Board and NPT Council have been identified and will be engaged ahead of the next meeting to ensure full representation.​ - Chaired by project lead, Neil Williams (a board rep with lived experience) the session set a clear focus on accessibility and inclusion for people with learning disabilities. Discussions explored why easy read is important and barriers using easy read for people with learning disabilities and professionals. |  |  |
| My Community |  | - The scope includes developing an approach to help support people who use social care support to work with others around them to maximise their wellbeing and to build capacity in the communities in which they live, helping them to be more health, social, confident, skills and valued. - It will reduce paid care as people living within supported living provision will be accessing resources and participating within their local community, rather than being passive recipients of paid care - Methodology used will be recorded to enable other supported living providers to implement the approach within their organisations |  |  |  |  |  | - Working group comprising of third sector supported living providers and Swansea officers have met to develop the scope of the project. The work is user led. - Killay, West Cross and Fairwood network meet monthly and are developing a locality plan, the group of 57 residents have identified activities and outcomes they wish to work - Friends United Together is a direct payment cooperative who manage the support they are using - Better Together NPT held an event in 2024 and are in the process of organising Wellbeing Taster Days to widen out the range of activities that they run |  |  |
| Making my own decisions and having my say |  | - Ensure people with learning disabilities and their families have a meaningful voice in decisions that affect them. - Ensure involvement in the Wellbeing and Learning Disability Board by making them accessible - Development of a network of organisations that support people with Learning Disabilities to ensure future coproduction opportunities are available to access |  |  |  |  |  | In July 2025, three projects were awarded Regional Integration Funding (RIF) to deliver under the My Community priority, running until March 2027:​ - Supporting the Delivery of Wellbeing Outcomes through Community-Based Options (Swansea)​ - Community Pathways to Independence: Enhancing Day Services through Early Help and Engagement (Neath Port Talbot)​ - NEXT STEPS – From Day Services to Early Help, Prevention and Community Engagement (Swansea)​ These projects will connect with the other, established RIF projects that fit within the ‘my community’ priority with the aim to align and support collaboration. Work is now underway across all three projects, with plans in place to align delivery regionally. This collaborative approach aims to maximise impact, share learning, and embed sustainable models of community-based support. |  |  |
| Programme |  |  |  | Area Plan Priority |  | Models of Care Supported |  |  | Programme Lead |  |
| # Emotional Wellbeing and Mental Health |  |  |  | Transforming Mental Health Services |  | - Community Based Care – Prevention & Community Coordination (MC1) - Promoting Good Emotional Health & Wellbeing (MC3) - Accommodation Based Solutions (MC6) |  |  | Karen Stapleton |  |
| Overview of the Programme The Regional Emotional Wellbeing & Mental Health Programme oversees the implementation of the Regional Emotional & Mental Wellbeing Strategy which was endorsed in April 2023. Vision Statement To have vibrant, diverse, and individually focussed services which promote emotional and mental wellbeing, are delivered and commissioned in a dynamic and integrated way, adopting innovative models and promoting the strengths of communities to improve the lives of those in the region. The Aims are: • To focus and promote emotional and mental wellbeing (rather than illness) • To enable communities to generate solutions for themselves, work from their strengths supported within a dynamic multiagency environment. • To truly join up commissioning and provision of services to support service design around the individual not the organisation. • To work to a common set of values and service model principles which permeate everything we do and the way that we do it. • To underpin this with a good understanding of the need supported by granular data/information. • To develop and deliver services which are supported by the evidence and ensure that there is a strong underpinning emphasis on research and development within the Region to add to the evidence base. |  |  |  |  |  |  |  |  |  |  |
| Workstream | Brief Description of Workstream |  |  |  |  |  | Progress to Date |  |  |  |
| Joining it Up: Therapeutic Services Review | Develop and enhance prevention and low-level support services for people with Mental Health (MC1) by moving to a transformative Joint Commissioning model for Voluntary Sector mental health and wellbeing services which will be ready to be implemented in April 2027: - Coproduce outcomes for People with Lived experience via a series of workshops and engagement activities which will determine ‘What Matters to me?’ - Begin to codesign and commissioning model (with People with Lived Experience and the voluntary Sector) which will meet the outcomes of those who will access services and the operational needs of organisations delivering the services - To explore opportunities for a more joined-up approach to psychological therapies across NHS and third sector services, ensuring people can access timely, coordinated, and effective support. The project aims to map existing provision, identify duplication and gaps, and develop shared understanding of pathways, governance, and clinical risk across sectors. This exploratory work will inform future system design and commissioning, with the goal of improving access, reducing waiting times, and strengthening early intervention through integrated models of delivery. This workstream links to the National Strategy work about improving access to psychological therapies in Wales (National Psychological Interventions Programme Board, NHS Wales Performance and Improvement) |  |  |  |  |  | - Due to the commissioning work in this workstream stalling during the Summer months, the workstream has shifted focus. - Mapping of Psychological Therapy Provision: Comprehensive mapping of NHS, third sector, and cluster-based psychological therapy provision to identify overlap, gaps, and opportunities for integration. - Analysis and Thematic Insights: Collation and analysis of information gathered from statutory and third sector providers to identify key themes, risks, and opportunities for greater integration. - Analysis of 3,500 adults waiting for psychological therapy in NHS: The project will analyse the 3,500-person NHS waiting list to understand patterns of need, including geography and demographics. This will help identify where pressure points exist and where third sector or community-based provision may complement NHS capacity. The insights gathered will be shared with partners to inform discussions on improving access, coordination, and efficiency across the system, influencing the development of future service specifications and commissioning priorities, and ultimately reducing waiting times. - Feedback to stakeholders and begin to co-produce efficiencies in current system: Sharing findings with partners and collaboratively developing new service specifications to inform future service design (improve system efficiency, coordination, and access across NHS and third sector provision). This will included people with lived experience and cross sector partners. |  |  |  |
| Cementing it Together: Improving Access to Services (including Comms & Engagement) | This workstream focuses on developing multi-agency pathways that ensure people (adults and children) receive the right support at the first point of contact through the No Wrong Door model. The approach brings together partners across sectors to create a more coordinated and responsive system that aligns with the First Contact, Right Response principle. For CYP, the next phase will focus on laying the groundwork for delivery by mapping current referral pathways, establishing governance and information-sharing protocols, and co-designing practical models for multi-agency panels in Swansea and Neath Port Talbot. A project Coordinator post was approved at SAB3 (September 16th) to support this work and to move the CYP project from the planning to the delivery stage by March/April 2027. |  |  |  |  |  | - This website is being widely used across the region www.sortedsupported.org.uk, and is a comprehensive mental health and wellbeing resource for adults living in region. It offers guidance, self-help tools and information on local services to support emotional wellbeing. - Further developments are planned to expand the site to include specific topics such as ‘support for unpaid carers and learning Disability focussed pages. - No Wrong Door: The Children and Young People’s Board is in the advanced stages of developing a single point of access model for emotional wellbeing and mental health support, based on the well-established and effective SPACE model (Single Point of Access for Children) which is well established in Gwent. The Project Coordinator Post has been advertised, and interviews are scheduled for mid-December 2025. - The redesign of the Programme, following the publication of the all-Wales Mental Health Strategy and the review of mental health services by the Health Board will impact the ‘Access to Services’ delivery plan. Adult work to be negotiated in Service Redesign MH Transformation work-stream |  |  |  |
|  | Develop a unified theoretical ‘Wellbeing Framework’, delivered in partnership with WGLAM RPB, Swansea University, Swansea Bay University and Public Health Wales. Theory and model written up and submitted for publication. Develop an accessible version of the Wellbeing Framework through an animation to share with stakeholders and the communities we serve. This will involve co-production with key stakeholders across the life span. The Wellbeing Framework will begin to develop and improve access to services across the region, clarifying pathways and entry points. (MC3) |  |  |  |  |  | - This is reaching completion and will be shared at the next EWMH Board in Autumn 2025. |  |  |  |
| Filling in the Gaps; Community Psychology | To develop and embed an evidence-based, community-led Community Psychology model across West Glamorgan that strengthens early intervention, enhances wellbeing, and reduces reliance on statutory services through psychologically informed practice. |  |  |  |  |  | - The Community Psychology approach is being developed as a key part of the Emotional and Mental Wellbeing Strategy, focusing on joined-up, preventative support rooted in the needs of communities. It brings a psychological understanding into community settings and multi-agency work. - Business Case for City Cluster: Business case completed and presented at the EMWB on November 5th, 2025. It was approved pending final approval at SAB2. - Recruitment to City Cluster Post: Recruitment to the City Cluster Community Psychologist post, subject to funding approval. - Community Psychology Strategic Plan: Strategic Plan will be finalised to guide delivery, consistency, and sustainability of the model, and iterated following evaluation feedback. - Evaluation and Insight Sharing: Evaluation will be completed, with insights from distinct pieces of work shared throughout to inform ongoing development and future commissioning. - Ongoing Co-produced Interventions: Psychologically informed, community-led interventions will be continuously co-produced and embedded as standard practice across clusters, responding to emerging local needs. |  |  |  |
| Understanding Data and Evaluation | Ensure that planning is based on accurate data collection and demographics (MC3) by developing a regional Data Framework that combines population-level data with community insights which will create a more comprehensive understanding of unmet need, helping to inform strategic commissioning. To develop a more data-informed, evidence-based understanding of emotional wellbeing and mental health needs across West Glamorgan that can inform commissioning, service redesign, and the 2027 Population Needs Assessment. This work aims to bring together existing population datasets, lived experience insights, and local intelligence into a shared regional picture of need. Where possible, these datasets will be linked through a potential partnership with the SAIL Databank. Digital mapping and a developing Data and Insight Steering Group will support alignment of data across partners, reduce duplication, and strengthen collective understanding over time. |  |  |  |  |  | - Engagement Analysis and Report Updates: The Lived Experience Engagement Report and analysis will be updated as needed to ensure citizen perspectives continue to inform planning and commissioning. - Data and Insight Steering Group to be established: Steering Group to be established to support Population Needs Assessment (PNA) development and data alignment across partners. Currently engaging with relevant partners. - Community Psychology Insights Collection: Local intelligence and community psychology insights will be gathered to inform the regional RBP wide PNA, as part of wider evaluation and understanding of community needs. - SAIL Databank Application: An application is being developed and submitted to enable linkage of existing population datasets for deeper analysis of emotional wellbeing and mental health needs. - Embedded PhD Research (Supervised by Workstream Lead): Doctoral research supervised by the workstream lead, focusing on the Community Psychology model and use of SAIL data to strengthen evaluation, inform service development, and contribute to the regional Population Needs Assessment. |  |  |  |

| Programme |  | Area Plan Priority |  | Models of Care Supported | Programme Lead |
| --- | --- | --- | --- | --- | --- |
| # Children and Young People |  | Transform complex care |  | - MC1: Community Based Care – Prevention and Community Coordination - MC 3: Promoting good emotional health and well-being - MC 4: Supporting families to stay together safely, and therapeutic support for care experienced children - MC 6: Accommodation Based Solutions | Keri Warren |
| Overview of the Programme Our vision as outlined in the Business Case from 2022 for this programme is that West Glamorgan will support children and young people to be safe, healthy and prosperous. The Children and Young People [CYP] Programme covers the services and support for people who are under the age of 18 (supporting children and young people to 25 with Additional Learning Needs-ALN). This programme focuses on: - Emotional wellbeing of children and young people including behavioural support. - Children and young people who require specialist support from health and social care, such as children who are looked after or at risk of being looked after by the local authority and children and young people with complex needs such as mental health conditions, learning disabilities or illness. - Supporting children and young people who receive services and support as they transition into adulthood, where they may receive a different type of service as an adult. To achieve this, we will need to work closely with CYP, their carers, their families, local communities and other important stakeholders such as Education in order to hear the ‘voice of the child’ and understand their rights/needs and what matters to them, in order to co-produce services and support that will meet those needs. An underlying principle of this work is to follow a ‘whole systems approach’ to change across health and social care services for children and young people (covering statutory and voluntary sectors). |  |  |  |  |  |
| Workstream | Brief Description of Workstream |  | Progress to date: September 2025 |  |  |
| CYP Emotional Well Being and Mental health | Improve access to Emotional Wellbeing and Mental Health support for children and young people including behavioural support through the development of a multi-sector multi-disciplined single point of entry/access for CYP emotional health and wellbeing to implement a No Wrong Door approach. Implement Welsh Government NYTH/NEST framework NEST framework (mental health and wellbeing) ¦ GOV.WALES . Undertake a review of the tidy.minds website |  | No Wrong Door: Recruitment for No Wrong Door Project Manager: x22 applications received. Shortlisting completed and preparing for interviews 11th 12th Dec 2025. West Glam self assessment complete and submitted to Welsh Government-awaiting regional specific feedback. Ongoing – A joint Sorted Supported and tidyMinds steering group developing content. OTHER: HIW, together with CIW and Estyn, undertook a joint national review. The focus of the review was to consider whether children and young people are receiving timely and effective support for their mental health needs. The report was published on 21 November 2024. Joint response and action plan submitted. An update required on the action taken to date, in response to the report recommendations and to establish the progress made with implementing the required improvements. Joint response coordinated and submitted to Welsh Government. |  |  |
| Transition from Child to adult services (CYP Complex Care). | Further develop regional approach to Transition (from Child to adult services, CYP Complex Care ) by implementing the Regional Principles and Standards developed 2024. Develop guidance for children, young people and professionals across the region to raise awareness of multi-agency transition process. |  | No further update. |  |  |
| CYP Accommodation | Develop and deliver new regional and local accommodation models for safe, secure accommodation and wrap around support for Children and Young People with complex needs, with a focus on prevention and early intervention. (MC 3, 6) |  | Development of ‘Business Case’ for a regional accommodation model for children with learning disabilities and behaviours that challenging in progress, considering cost efficiencies, impact, and the integration of health, education, and social care. ‘Eliminate’ Resources produced by WG: - Removing profit from the care of children looked after: information leaflets ¦ GOV.WALES resources - Removing profit from the care of children looked after ¦ GOV.WALES WG website-updates |  |  |
| Children’s Services Review | Focused on strengthening multi agency complex needs panels for CYP to ensure that they function effectively and efficiently. The review aims to tighten how these panels operate, this involves improving early communication, ensuring the right people are present at meetings, and having decision-makers or those who can quickly escalate decisions involved to avoid delays, especially in crisis situations. The goal is to strengthen governance and expedite decision-making processes to provide timely and appropriate care. |  | A task and finish group has been working towards strengthening the Multi-Agency complex needs Panels and Governance arrangements (Phase 1). A ‘Standard Operating Procedure’ has been drafted and is being reviewed by health, social care and education partners. This aims to outline the processes and protocols for managing children and young people with complex care needs that require a coordinated multi-agency response from health, education, and social care services. A review of current documentation to streamline process to regional approach: - Regional Multi Agency Complex Needs Panel Terms of Reference - Regional Request to present at Panel Proforma. - Regional Request for Funding to Health Cover Letter. |  |  |
| CYP Participation and Engagement | ‘Working together to include the voices of Children and Young People across West Glamorgan Regional Programmes’: undertake engagement with children, young people, parents and carers on the priorities of Children and Young People Programme will ensure the voices of Children and Young People, Parents, Carers, Families, guardians and others are considered and heard (MC 3) |  | Engagement completed at the World Mental Health Day event 10th October. |  |  |
| Prevention and early intervention | Review and improve models of care that wrap around families to keep families together. (MC4) Continue to identify and implement transformative prevention and early intervention services (MC1, 3, 4) |  | Promotion of RIF projects continue and ongoing workshops/networking and gathering evidence of implementation to inform practice. In person event: National Practice Guidance for Therapeutic Support for Care Experienced Children and Young People 10/11/25 |  |  |

| Programme |  | Area Plan Priority | Models of Care Supported |  | Programme Lead |
| --- | --- | --- | --- | --- | --- |
| # Neurodiverse Programme |  | Transform complex care | - Community Based Care – Prevention and Community Coordination (MC1) - Community Based Care – Complex Care Closer to Home (MC2) - Promoting Good Health and Wellbeing (MC3) |  | Julie Davies |
| Overview of the Programme The Neurodiverse Programme (ND) has been established to ensure that people with neurodevelopmental disorders have access to the services and support they need to participate fully within their communities and live fulfilled lives regardless of an assessment or diagnosis. Partners have agreed to develop a co-produced Neurodiverse Strategy which is focussed on the needs of people (including children and young people) with ND regardless of assessment. The strategy development will take a needs-led, person centred approach to supporting individuals (including families) who are neurodiverse in our communities to live their best lives. This will include: • a system shift towards building community resources. • implementing an inclusive approach to neurodiversity. • focus on a need led approach which is not based on an assessment or confirmed diagnosis. |  |  |  |  |  |
| Workstream | Brief Description of Workstream |  |  | Progress to Date |  |
| Neurodiverse | Implementation of Welsh Governments Autism Code of Practice |  |  | Full National report: Evaluation of the Code of Practice on the Delivery of Autism Services ¦ GOV.WALES To be reviewed as substantive item at next ND Board |  |
|  | Coproduce, develop a plan and implement a programme that Increases opportunities for neurodiverse individuals to be involved in their local community (MC3) |  |  | No Update |  |
|  | Review and develop local groups that support social interaction for neurodiverse individuals |  |  | No Update |  |
|  | Develop and enhance the availability of preventative services that would enable autistic people in their daily lives (MC1) |  |  |  |  |
|  | Codesign and develop a regional Neurodiverse Strategy with people with lived experience. |  |  | A joint meeting of the ND Board and Strategy Development group discussed the proposed regional strategy development. Key reflections included: - Purpose: Define clear intentions, avoid duplication, and create a needs-led, person-centred vision for all ages, shaped by lived experience. - Collaboration & Mapping: Strengthen cross-organisation collaboration and map existing services to share information effectively. - Access to Information: Improve clear pathways, communication, and support during waiting periods. - Training & Awareness: Develop/utilise existing ND-specific resources, e-learning modules, and raise awareness among staff, professionals, and families. - Inclusivity & Representation: Ensure diverse board representation, embed ND needs, and support individuals at all stages, including undiagnosed. - Support & Advocacy: Prioritise advocacy, early intervention, and assistance through diagnosis and life transitions. Decision Made to develop Pledges instead of a strategy which hold agencies accountable. Second workshop planned 20/1/2026. |  |
|  | Establish ND Liaison Network to ensure the work of the region is co-produced (enabler) (MC3) |  |  | Not yet started. |  |
|  | Refined information management to strategically support demand and capacity modelling (Enabling Digital Programme) |  |  | West Glam referenced as best practice in efforts to routinely review ND data (assessments & Waiting times).This has resulted in several requests for shared learning sessions which have been facilitated with other RPB’ s and Health Boards. Request from WLGA to support data priority as a national issue and present at next meeting. |  |

| Programme |  | Area Plan Priority | Models of Care Supported |  | Programme Lead |
| --- | --- | --- | --- | --- | --- |
| # Regional Commissioning Programme |  | Transform complex care | All |  | Marie Davies |
| Overview of the Programme The programme has been designed to develop a partnership-led approach to commissioning across MH/LD, older adults and children’s services. The purpose of the programme is to: - Improve outcomes for citizens with complex needs - Develop consistent, region-wide commissioning processes - Strengthen partnership working All population cohorts receiving a commissioned package of care will be included in this work prioritised in 3 stages: - Mental Health/Learning Disabilities - Older Adults - Children and Young People |  |  |  |  |  |
| Workstream | Brief Description of Workstream |  |  | Progress to Date |  |
| Joint Working Workstream (MH/LD) | Development of a joint working protocol to support and enable joint working between partners (LA and Health) in learning disability and mental health teams. It will include: - Inter-agency dispute policy - Joint funding split - CHC (Continuing Healthcare) process for partners to follow - Joint funding arrangements and process - Regional brokerage and monitoring of packages of care - DST tracker monitored at a regional level |  |  | Agreed to create this workstream on 16th September at Regional Commissioning Board, this needs approval though the Steering and Advisory Boards |  |
| Commissioning Specification & Accommodation Plan (MH/LD) | Define service models, capacity/demand and market approach to delivery of accommodation services for people with Learning Disabilities/complex needs and Mental Health. Priorities include: - Closer to home (repatriation) - Specialist MH/Dementia nursing provision - Expansion of shared lives - Cross boundary voids and matching - Expansion of shared lives project |  |  | Agreed to create this workstream on 16th September at Regional Commissioning Board, this needs approval though the Steering and Advisory Boards |  |
| Market Stability Report | A Market Stability Report (MSR) in Wales is a strategic assessment of the social care market, required by the Social Services and Well-being (Wales) Act 2014. It evaluates whether the care and support market in a specific region can meet current and projected needs, assessing both the stability and sustainability of services like care homes and home care. These reports help local authorities and health boards plan and commission services by identifying gaps and risks, and they include an analysis of current supply, future demand, and potential issues. Reports are required every five years, the next report is due in 2027 |  |  | - Agreement on template for partners to use - Agreement on data sets - Agreement on quality metrics - Development of provider questionnaire - First data gathering exercise is being undertaken for April to Sept to evaluate data sets with feedback due in November |  |