| Meeting Date | 29 January 2026 |  | Agenda Item |  | 4.3 |
| --- | --- | --- | --- | --- | --- |
| Name of Meeting | SBUHB Board |  |  |  |  |
| Report Title | Welsh Government (WG) Oversight and Escalation Update and SBUHB Integrated Performance Report |  |  |  |  |
| Report Author | Meghann Protheroe, Head of Health Board Performance |  |  |  |  |
| Report Sponsor | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention Darren Griffiths, Director of Finance and Performance |  |  |  |  |
| Presented by | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |
| Purpose of the Report | To provide the Board with a summary of the performance and outcomes issues for the services escalated as part of WG Oversight and Escalation Framework, along with a general update of the Health Boards Performance against the Key Strategic Objectives. |  |  |  |  |
| Key Issues | This report provides a monthly update on all areas of delivery currently in escalation against WG Oversight and Escalation Framework, namely: Level 4 - Maternity and Neonates (escalated in July 2025). - Finance, strategy and planning. - Performance and outcomes relating to cancer, Urgent and Emergency Care and quality of care related to HCAIs. Level 3 - Performance and outcomes relating to planned care and CAMHS. The attached Integrated Performance report (IPR) is a routine report that provides an overview of how the Health Board is performing against the National Delivery measures and key local quality and safety measures. The IPR includes an update against four three priority areas for the Health Board: - Welsh Government Escalation (RAG Rating status) - Performance against the Health Boards 5 Strategic Objectives - Service Specific Updates The Performance metrics outlined within Section two of the Integrated Performance Report have been aligned to the Health Boards five Strategic Objectives. Key Updates will therefore be provided against the five Strategic Objectives below: - - People of Swansea Bay live healthier, equitable and more equal and prosperous lives - Care is high quality, safe, efficient and delivers the best possible outcomes for people - Care is delivered in safe and appropriate settings supported by innovative digital solutions - The health board is a great place to work where staff feel valued and work together towards a common goal - The health board is a resilient, financially sustainable and responsible organisation An additional section has been included in the report which will provide “Service Specific Updates” as and when requested by the Performance and Finance Committee work programme. In this paper, the following service specific updates will be included: - Neurodevelopmental Disorders Service (Appendix 1) - Theatre Utilisation (Appendix 2) |  |  |  |  |
| Specific Action Required (Please choose one only) | Information | Discussion | Assurance | Approval |  |
|  | ☐ | ☐ | ☒ | ☐ |  |
| Recommendations | Members are asked to: - CONSIDER the monthly update in respect of performance against escalation measures and de-escalation criteria. - ACKNOWLEDGE and DISCUSS the Health Board performance against key measures and targets. |  |  |  |  |
| Appendices | Appendix 1: Integrated Performance Report Appendix 2: Theatre Utilisation |  |  |  |  |

WELSH GOVERNMENT OVERSIGHT AND ESCALATION UPDATE

- INTRODUCTION

The previous reports have described the actions and longer-term proposals being developed and implemented in response to services escalated to targeted intervention status. The reports provided an update on the operational programme to manage the delivery of improved performance and outcomes for services under targeted intervention.

The current report will provide an update against all levels of Oversight and Escalation of services within Swansea Bay University Health Board (SBUHB) and will include;

Performance against Areas of Targeted Intervention (Level 4)

- Cancer

- Urgent & Emergency Care

- Quality of Care related to Healthcare Acquired Infections

- Maternity and Neonatal Services

- Finance

- Strategy and Planning

Performance against Areas of Enhanced Monitoring (Level 3)

- Planned Care

- Child and Adolescent Mental Health

- BACKGROUND

Following WG tripartite meeting in December 2023, SBUHB was notified of an escalation of performance monitoring for performance and outcomes from enhanced monitoring to Targeted Intervention.  The services listed in the introduction of this report were specifically included in the escalation.

On 12th April 2024, SBUHB had its inception meeting with Welsh Government colleagues and on 24 April 2024 the first quarterly meeting was held with the Chief Executive of NHS Wales.  Quarterly meetings subsequently alternate with formal Joint Executive Team (JET) meetings.  Monthly review meetings are with WG officers focussing on key updates against the escalated areas.  The Chief Operating Officer is the Senior Responsible Officer (SRO) for targeted invention and each work programme is supported by senior management and clinical leads. Summarised updates against the escalation levels will be provided throughout this report.

Following the Tripartite meeting in February 2025, the levels of escalation have been revised and updated as follows;

- Child and Adolescent Mental Health Services de-escalated from level 4 (targeted intervention) to level 3 (enhanced monitoring).

- Planned care de-escalated from level 4 (targeted intervention) to level 3 (enhanced monitoring).

Updated de-escalation criteria was provided by WG in April 2025 which provided updated targets for several areas within Level 3 Enhanced Monitoring. The updated de-escalation criteria can be seen throughout the paper.

Following the publication of the Independent Maternity and Neonatal Review published on 15 July 2025, the decision was made to escalate Maternity and Neonates to Level 4 (Targeted Intervention) from Level 3 Enhanced Monitoring. Updated de-escalation criteria relating to Maternity & Neonates was published in September 2025 and has been incorporated into this paper.

- PERFORMANCE AGAINST THE TARGETED INTERVENTION SERVICES

3.1 Cancer

| Criteria to Achieve | Current Performance |
| --- | --- |
| - 60% performance maintained for 3 months against the Single Cancer Pathway (SCP) target. | - September – 60% - October – 56% - November – 52% |

Actions being taken to improve include:

- Continued focus on front end of pathway for all specialties

- Commencing demand and capacity work in relation to the cancer pathway supported by Transformation Team

- Outsourcing pathology backlog for Skin, Urology and LGI

- Detailed Dermatology demand and capacity exercise, supported by Healthcare Systems Engineering team currently in progress.

- Phase 2, business case development for the long-term provision of complex gynae-oncology surgery commences.

3.2 Urgent and Emergency Care

| Criteria to Achieve | Current Performance |
| --- | --- |
| - A continuous reduction of ambulance handovers over an hour of at least 11% in three consecutive months and maintained for 3 months (Based on quarter 2 and 3 2023 baseline). | - October – 173 (19% increase) - November – 162 (6.4% reduction) - December – 329 (103% increase) |
| - Continuous improvement towards no more than 7% of patients waiting over 12 hours at each individual site and across the health board. | - October – 9.17% - November – 8.83% - December – 9.95% |
| - Median time from arrival at an emergency department to assessment by a clinical decision maker should not exceed 60 minutes. | - October – 90.28% - November -89.62% - December – 84.87% |
| - A continuous reduction in delayed pathways of care of 5% for three consecutive months and then maintained for three months (based on Oct-Dec 23 baseline). | - October – 186 - November – 179 - December – 169 (In target) |
| - Assessment of declared BCIs, including reasons why, actions taken, and lessons learnt. | - BCI declared 6th – 8th January and 11th – current. (Robust weekend plans are in place to minimise risk and to maintain patient flow). |

Actions being taken to improve include:

- Full implementation of D2RA model – Focus on D2RA has rapidly shifted into understanding the demand and capacity position for pathway 2 beds and utilisation of that bed pool. Therapy led audit undertaken in December of all patients occupying a pathway 2 bed. Data analysis in progress with Deloitte’s support. Early indication is that there is opportunity to work with Local Authority partners to potentially reduce the Pathway 2 bed pool and enhance the Pathway 1 offer. The reset fortnight in December demonstrated good opportunity for partnership working, with a focus on those patients who are clinically optimised. This process has continued and there has been some improvement in patient flow. Planning for the transfer of 30 clinically optimised patients from Morriston to Singleton took place during December 2025 and the plan was implemented w/c 5th January 2026.

- UEC Care co-ordination Hub – The single point of access has been in place since the 1st October 2025 and the first data submission took place on the 21st November. There is specific focus on the “clinical conversation before convey”, aimed at reducing conveyance of patients from care homes where clinically appropriate to do so. Work is also focussed on the management of patients who fall with the implementation of a level 2 Falls service made up of therapy technicians and a registered therapist, supported by St Johns ambulance provision.

- Pathway of Care Delays (PoCD) – SBUHB has seen a recent increase in the POCDs. Focussed attention on this position continues following the learning from reset fortnight with a daily review meeting taking place to focus on flow.

- Revised flow operating model: The revised operating models implemented as part of the test of change in Morriston remain in place. However, increase in demand for emergency care, high levels of patient occupancy driven by medical bed day utilisation has challenged the Health Board’s ability to maintain flow and thus the level of ambulance handover performance achieved following the tests of change. The emergency pressures have tipped the Health Board into two formal Business Continuity incidents, consistent with the pattern currently seen across NHS Wales. A complicated Infection Control picture further contributes to the interruption of patient flow with capacity reduced as a result of winter illnesses.

- UEC capital redesign – Recent communication from the Chief Executive to the Director General of NHS Wales sets out an urgency to progress to an Electronic Patient Record across the Urgent and Emergency care services. Whilst there remains ambition to co-locate front door assessment processes with the emergency department, this programme of work cannot be progressed in the absence of Capital investment.

Elements of the above are all linked to front door assessment in patient pathways, and complex discharge is being tested via the Quality Improvement process around the thematic review of Urgent and Emergency Care Services. Deloitte are leading on this work as part of the financial recovery and sustainability programme.

3.3 Maternity and Neonatal Services

On 12th December 2023, maternity and neonatal services were escalated to level 3 (enhanced monitoring) following an assessment of issues and concerns related to staffing levels, quality and safety issues, the issues within the HIW unannounced inspection at Singleton as set out in the report published on the 15 December 2023. Subsequently, in July 2025, following receipt of the Independent Review report, the decision was made to escalate Maternity and Neonatal Services to Level 4 – Targeted Intervention.

Detailed progress against these areas will be provided as part of the Perinatal Committee, chaired by the Executive Director of Nursing. However, a summary of progress can be found in the table below:

| Criteria to Achieve | Current Performance |
| --- | --- |
| - Ensure that the recommendations and actions in the Independent Review are progressed in line with agreed timescales and report progress to Welsh Government monthly, highlighting risks to delivery. | - Perinatal improvement programme has been established Dec 2025 - Exec led workstreams are underway Dec 2025 - Quarterly Perinatal updates to Board ongoing |
| - Ensure that the agreed actions in the family-led review into Swansea Bay maternity services are progressed in line with agreed timescales and report progress to Welsh Government monthly, highlighting risks to delivery. | - The agreed actions of the family led review have been integrated to the Independent Review improvement plan – Jan 2026 |
| - Receive a positive assessment from the Welsh Government independent observer on progress against the agreed maternity and neonatal action plan. | - We await the outcome of the assessment process – anticipated Jan/Feb 2026 |
| - Agree a set of sustainability conditions with Welsh Government that can be used to track improvements. | - Have developed Perinatal reporting to Board through Quality & Safety committee Jul 2025 - Routinely reviewing staff retention and well-being plan – revised plan launching Q4 2026 - Pulse surveys underway – quarterly - Robust Governance processes in place – Dec 2025 |
| - Evidence effective Board scrutiny and oversight of maternity and neonatal services. | - Governance structure in place – July 2025; updated Dec 2025 |
| - Embed the maternity and neo-natal dashboard across the service to demonstrate that data is driving real decision making. | Complete |
| - Regularly review the risk register, appropriate risk management, and mitigations. | - The risk register is reviewed at monthly Perinatal committee and flagged at Quality & Safety Committee and through to the Board |
| - Regularly review against agreed outcomes to demonstrate that there is continued embedding of the LRI/NRIs, complaints and concerns process within quality governance, ensuring responses in a timely manner. | - Monthly reporting through Perinatal Committee and Board - Ward to Board reporting |
| - Evidence a joint and effective PMRT meetings across the service with engagement of affected families. | Ongoing - Part of the improvement plan and reported through perinatal committee |
| - Maintain the required staffing establishment at appropriate numbers and grades. | Ongoing - Reported monthly through Perinatal committee, into Quality & Safety committee and into Board. - Key element of performance report |
| - Achieve and maintain training compliance rates for all staff in maternity and neonatal services. | Complete - Reviewed at monthly performance and perinatal committee – key element of the report |
| - Demonstrate required corrective action against Patient Reported Outcome Measures and Patient Reported Experience Measures data for maternity and neonatal services. | Ongoing - All reported monthly through Perinatal committee, into Quality & Safety committee and into Board. - Additional requirements included in perinatal improvement plan |
| - Evidence how women and family feedback shapes service design within the health board. | Ongoing – Perinatal Improvement Plan outlines engagement blueprint as follows: - Service specific engagement undertaken by the service itself, mostly using its own contact with service users; ongoing rolling programme with reporting through Perinatal Committee. - Service specific engagement undertaken by corporate teams, particularly DICE and the independent review’s engagement lead - “Always on” engagement at a pan Health Board level which sees generic engagement activity offering up insights and feedback relevant to the maternity and neonatal services. Ongoing - Mapping of groups across the Swansea and Neath Port Talbot areas – to be completed April 2026 - Develop a Network of Sounding Boards that builds on work being undertaken as part of the Women’s Health Plan – April 2026 |
| - Provide assurance that clinical leadership is consistent, visible, effective, and that leadership development support is in place. | Ongoing - Senior clinical staff present as required by BAPM guidance; underpinned by audit cycle and key indicators which include care planning in decision making. Reported to Perinatal Committee on monthly basis. - Multidisciplinary Team Development Programme rooted in compassionate leadership, culture and behaviours to be delivered between Feb and April 2026 |
| - Provide assurance and evidence of an improving culture through appropriate surveys, and/or qualitative assessment for maternity and neo-natal services. | Ongoing - Reported through monthly Perinatal committee and includes: - Workforce heat maps that cover staff feedback - Patient feedback - Guardian service - Patient voices forum - Pulse surveys - Feedback from all visitors reporting positive change |

3.4 HCAI Improvements

| Criteria to Achieve | Current Performance |
| --- | --- |
| - Stabilisation of the increased trajectory of cases of HCAI and evidence of continuous improvement accompanied by a strong QI approach and plan that has oversight and monitoring by board Quality Safety (Q&S) Committee and Board. | - Embedded Quality Improvement approach in this area, monitored closely via Q&S Committee and Board. |
| - The Health Board to have a clear improvement plan based on a root cause analysis to address the issue of hospital onset HCAIs. | - In place |
| - C.difficile: reduce the number of hospital onset infections by 40% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 10 cases to no more than 6 per month) | - October -5 - November – 10 - December - 10 |
| - Staph aureus: reduce the number of hospital onset infections by 25% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 4 cases to no more than 3 per month) | - October – 4 - November – 4 - December - 3 |
| - E-coli: reduce the number of hospital onset infections by 20% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 5 cases to no more than 4 per month) | - October – 5 - November – 5 - December - 4 |
| - Klebsiella: reduce the number of hospital onset infections by 10% and maintain for 3 months based on 2017/18 figures (baseline – 54 cases in 2017/18, reduce to average of at most 4 per month) | - October - 4 - November – 3 - December - 7 |

From the beginning of December 2025, there were 19 new infection related incident/outbreaks (non-C. difficile related), involving two or more patients affecting a total of 76 patients (124 bed days lost). These new incidents/outbreaks occurred over 19 wards, with concurrent infections in several wards.

  - Mental Health: Two incidents, one with Norovirus, one with a respiratory virus (15 bed days lost).

  - Morriston: Ten incidents. Three associated to COVID-19, four to Influenza and three to Norovirus. Two wards were affected by concurrent incidents of Influenza and Norovirus (Total bed days lost 82).

  - Neath Port Talbot: Five incidents across three wards. One ward affected by Norovirus, one ward had concurrent incidents associated to Norovirus and Covid-19, and one ward had concurrent infections associated to Covid-19 and Influenza. (Total bed days lost 15).

  - Singleton: two incidents affecting two wards, both associated to Influenza A. (Total bed days lost 12).

There were five new C. difficile periods of increased incidence (PII) detected involving thirteen patients in total, with one new transmission event between two patients.

HCAI case review themes: 
Over occupancy, insufficient single room capacity, inability to decant bays and deep clean (4D clean) the care environment and patient equipment.

Patient risk factors that may have contributed to the development of C. difficile infection episodes include old age, prolonged and frequent admissions to health care settings, multiple co-morbidities and antibiotic requirements to treat other infections.

Actions being taken to improve include:

- Gold C. difficile High Incidence Management Group.

- Monitoring of C. difficile Standards: Risk Assessment & Governance Framework.

- Continuation of QI Project in Acute Medical Unit focusing on AMS and 72-hour review and improving switch to oral route for administration.

- Scoping exercise to explore the feasibility of extending role of ward based enhanced cleaner.

- Trial of new Microfibre cleaning systems

- Primary care QI projects to reduce urinary tract infections in care home residents.

- Scoping the development of an equipment decontamination facility.

- Review of prescribing guidelines for antibiotic prophylaxis during prolonged surgical interventions.

3.5 Finance

The Health Board’s assessment on performance against the £58.7m deficit has three components Operational Pressure, Savings Target, and Planned Deficit. Performance against these three elements at Month 9 is summarised in Table 1 below. At Month 9 there was an In-Month deficit of £3.8m, which is £1.0m below the £58.7m planned deficit, with the YTD position reporting a £55.2m deficit, which is £11.2m above £58.7m plan.

It is clear from the Table above that the Year-to-Date issue remains the non-delivery of savings. This shortfall in delivery YTD is in part mitigated by ‘Delegated Budget’ position underspending and the central N/R opportunities as set out in the 11 September submission delivering (as reported in the Table above). Whilst excluding the non-delivery of saving most areas are within the delegated operational budgets, the key exception to this is Mental Health & LD Services.   Throughout the year there have been pressures linked to pay and CHC but also Temporary Adult Placements. The latter issue has resulted in an in-month pressure of £0.7m, with YTD expenditure of £5.3m. During November the service saw the highest number of patients in Temporary Adult Placements at 33, which at the time of closing the ledger for Month 9 was at 25. This pressure will need to continue to reduce through Q4 and managed alongside the other pressures linked to ENIC and Nurse Streamline numbers that the Health Board will need to mitigate in-year.

On savings performance the submission made on 11 September 2025 set out the Plan to deliver the £55.4m savings in 2025/26. This was a combination of (1) Part A - budgetary releasing savings delivery supported by our external strategic partner; alongside (2) Part B - delivery of underspends in the operational budgets specifically around the corporate directorates and N/R opportunities. The monitoring of the performance for Part A is undertaken through the existing governance arrangements, using the Health Board’s savings trackers. This data is then used to complete the WG Monthly Monitoring Return (MMR) Savings Tables. However, as Part B are improvements in run rate and not a formal budgetary savings this element of the plan is not reported in Savings Tables of the WG MMR or standard trackers. A summary of the assessed performance is provided in  the table:

With regard to the delivery of the £46.8m the top section of the below demonstrates the original plan at 11 September, the plans as per the trackers at Month 9 and the forecast delivery at Month 9. The scheme type is split based on the Amber and Green as per the MMR, Local Red schemes, Local Pipeline ideas and those schemes presented by Deloitte. As the Local Red schemes, Local Pipeline ideas and those schemes presented by Deloitte move to Green and Amber the value of the Plan figure will reduce. As you will see from the table there is still significant work to be completed to ensure the two parts of the Deloitte schemes translate to Green and Amber.

The focus on savings is critical both in terms of supporting the 2025/26 delivery but also on mitigating the impact on the Underlying Deficit, particularly given the £6.9m Deloitte Part 1 Plan had a recurrent impact of £29m.

Post Month 9 closedown the Health Board undertook an assessment of the 2025/26 outturn based on data provided by Service Areas in November 2025 and the actual trend over Quarter 3. Without further intervention and actions, the Health Board will likely end the year £10m-£12m above plan. The actions and mitigations needed are detailed below and are no different to those previously agreed and noted by the Board and are summarised below:

- 16th December Special Board meeting, approved a paper that set out the actions to address the savings shortfall. In summary the actions to address the savings shortfall agreed were:

  - Urgent emergency Care (UEC) – reconfiguration of beds to manage Clinically Optimised Patients via a new model to be in place 5 January 2026.

  - CHC - continued focus on repatriation of patients and address Social Work support for package reviews by 16 January 2026.

  - Variable Pay minimum 50% reduction in nursing variable pay with cap within Allocate in place by 15 December 2025.

  - Variable Pay - other staff group minimum 50% reduction (excluding WLI and some ADH) to be enacted by 19 December 2025.

  - Bans effective from 15 December 2025 building on previous controls already agreed to increase certainty:

    - all travel, except those directly linked clinical care

    - all Printing/Stationery/Books except those directly linked to clinical care

    - all Study leave that not mandated/urgent via professional CPD

    - catalogue restriction with ban on areas such as Furniture and Fittings except in exceptions circumstances

    - Deferral of discretionary spend where possible 7.

Of the above list, the majority of this was due to commence from the end of Month 9, although there was a £0.5m reduction in variable pay in Month 9. Delivery will be tracked and reported from Month 10.

- Further Opportunities Non-Recurrent managed centrally: there are a currently 13 areas of opportunities under assessment to establish viability and value to support the delivery of the £58.7m on a non-recurrent basis. If all delivered to 100% these would provide a maximum of £7m.

The likely outcome is that the delivery of the £58.7m will be met through a combination of the actions agreed at 16 December Special Board meetings and materialisation of some of the further opportunities, although it is the first set of actions that will be critical in delivering the recurrent position in 2026/27.

3.6 Planning

Updates against the de-escalation criteria outlined by Welsh Government can be found below;

| De-escalation Criteria | Actions – Updated Jan 2026 |
| --- | --- |
| Submission of a balanced and credible three-year medium-term plan or acceptable annual plan in line with the current planning framework. | - Revised NHS Wales Planning Framework and financial allocation received from Welsh Government on 19th December 2025. - Work progressing at pace to consolidate and quantify the Annual Plan priorities aligned to the existing R&S Programmes, into appropriately quantified plans that deliver both the opportunities identified through the Deloitte work, as well as addressing national requirements, i.e. Minimum Delivery Expectations and Enabling Actions 26/27 set out by the Cabinet Secretary. - Key next steps in providing an Annual Plan for Board approval for submission to Welsh Gov on 31st March, involve engagement and detailed assessment of the Plans being developed by Programmes by 21st January 2026 |
| Evidence of a clear roadmap and implementation of the health board’s Clinical Services Plan. | - First meetings of the Clinical Reference Groups for Integrated Community Care and Networked Hospitals held 16 and 18 of December. With broad representation from across secondary and primary care. - First draft of ‘State of the Nations’ Report and Overview Demand and Capacity completed - Draft overview of strategic Demand and Capacity completed |
| Welsh Government’s confidence in delivery based on an assessment against an agreed planning maturity matrix | - Re-assessment of SBUHB position completed. Action Plan and supporting evidence being collated. - Re-assessment submitted to Welsh Government 28 November |
| Progress made with regional planning | - Previous Regional Joint Committee 18th August. Subgroup updates were received for: Regional Health Economy, Clinical Services Planning, Workforce and OD, Data and Digital, Finance and Commissioning, Research and Innovation. - The Regional Drive and Delivery Group, Chaired jointly by Abi Harris and Phil Kloer, met on 16 October and provides oversight of subgroup work programmes. - Full updates are scheduled to be reviewed at the next RJC meeting 22 January. |

- PERFORMANCE AGAINST THE ENHANCED MONITORING SERVICES

4.1 Planned Care

| Criteria to Achieve | Current Performance (December 2025) |
| --- | --- |
| - 100% of open outpatient pathways to be waiting less than 52 weeks and maintained for 3 months. | - 100% |
| - Continuous improvement towards 75% of all open outpatient pathways waiting less than 26 weeks. | - 78.44% |
| - 100% of open pathways to be waiting less than 104 weeks and maintained for 3 months. | - 100% |
| - Continuous improvement towards 80% of all open pathways waiting less than 36 weeks. | - 75.11% |
| - 12% reduction in the number of patients delayed by 100% for their follow up appointment in three consecutive months and maintained for 3 months (Based on the November 2024 baseline). | - 20.76% increase against baseline |
| - 68% R1 ophthalmology patient pathways to be waiting within or no longer than 25% of their target date for an outpatient appointment and maintained for 3 months. | - 71.94% - meets de-escalation criteria |
| - 85% of patients waiting for a diagnostic test to be waiting less than 8 weeks and maintained for 3 months. | - 66.84% |
| - 85% of patients waiting for a diagnostic endoscopy to be waiting less than 8 weeks and maintained for 3 months. | - 43.95% |
| - 85% of patients waiting for a NOUS and non-cardiac MRI to be waiting less than 8 weeks and maintained for 3 months. | - 67.65% |
| - 90% of patients waiting for therapies to be waiting less than 14 weeks and maintained for 3 months. | - 100% |

Actions being taken to improve include:

- Robust monitoring via live dashboards

- Weekly monitoring meetings chaired by Service Group Directors

- Bi-weekly oversight meeting chaired by the Chief Operating Officer

- Specific support commissioned for Gynaecology improvement plans

4.2 CAMHS

| Criteria to Achieve | Current Performance |
| --- | --- |
| - 80% of LPMHSS mental health assessments undertaken within 28 days from the date of receipt of referral. | - October – 98% - November – 97% - December – 98% |
| - 70% of therapeutic interventions started within 28 days following an assessment by LPMHSS. | - October -65% - November – 66% - December – 70% |
| - 85% of HB residents in receipt of secondary mental health services who have a valid care and treatment plan. | - October – 95% - November – 92% - December -98% |

Actions being taken to improve include:

- CAMHS Part 1B:

  - Recruitment to vacancies has been successful (1.65wte recruited, due to start in February and March 2026), however sickness and maternity leave weakens the capacity pool to almost pre-recruitment levels presently. The CAMHS Directorate continues to utilise agency staff to offset staffing gap.

  - Despite this, the recovery plan roll out is underway, which includes changes to the delivery of the initial therapeutic offer for 1:1 intervention, which enables young people to commence support more quickly and the offer of SilverCloud support for those suitable.

  - This has resulted in 4 months of small, but consistent improvement in the Part 1B performance irrespective of staffing challenges, which is now at 70% (submitted for Dec 2025)

  - Weekly meetings continue to oversee booking and clinic capacity utilisation, and to utilise our staffing resource as flexibly as possible.

Important update: The Swansea-based clinic space (Ty’r Meddwl) has been closed until April 2026 due to water ingress requiring roof replacement. Whilst Part 1A and Part 1B activity is being prioritised, the loss of 6 clinic rooms 5 days per week (40% room capacity) will have an impact on staffing capacity, who will need to utilise various alternative community-based locations requiring travel time.

- INTEGRATED PERFORMANCE REPORT

The detailed Integrated Performance Report can be found in Appendix 1 of the attached report. The purpose of this report is to provide an update on current performance of the Health Board at the end of the most recent reporting window in delivering key performance measures outlined in the NHS Wales Delivery Framework, local Quality & Safety measures, updates against Welsh Government De-escalation targets and routine reporting against measures outlined within the NHS Wales Planning Framework.

In alignment with the revised Swansea Bay University Health Board (SBUHB) Performance and Assurance Framework, the Integrated Performance Report has been reviewed and will now update against three key areas: -

- Welsh Government Escalation

- Performance against the Health Boards 5 Strategic Objectives

- Service Specific Updates

As and when required, the Integrated Performance Report will provide ‘Action and Intervention’ focus on areas of performance which are off target or an area of concern for the Executives. Additionally, as and when Committee/Board members are concerned with an area of Performance, they can request that an Action and Intervention focus be undertaken within the IPR. An ‘Action and Intervention’ focus will provide a deeper look into the service and will provide detailed action steps which are being taken to recover performance.

The Performance metrics outlined within Section two of the Integrated Performance Report have been aligned to the Health Boards five Strategic Objectives. Key Updates will therefore be provided against the five Strategic Objectives below: -

- People of Swansea Bay live healthier, equitable and more equal and prosperous lives

- Care is high quality, safe, efficient and delivers the best possible outcomes for people

- Care is delivered in safe and appropriate settings supported by innovative digital solutions

- The health board is a great place to work where staff feel valued and work together towards a common goal

- The health board is a resilient, financially sustainable and responsible organisation

An additional section has been included in the report which will provide “Service Specific Updates” as and when requested by the Performance and Finance Committee work programme.

In this paper, the following service specific updates will be included:

  - Neurodevelopmental Disorders Service (Appendix 1)

  - Theatre Utilisation (Appendix 2)

- RECOMMENDATION

Members are asked to:

- CONSIDER the monthly update in respect of performance against escalation measures and de-escalation criteria.

- ACKNOWLEDGE and DISCUSS the Health Board performance against key measures and targets

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Outlined within the body of the paper but in summary considerable backlog of patients awaiting a diagnostic and treatment services across a range of services. Issues of harm in relation to high levels of HCAIs noted. |  |  |  |
| Financial Implications |  |  |  |
| Funding not yet agreed for 26/27 |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| Delay to diagnosis and treatment potential in service delivery |  |  |  |
| Staffing Implications |  |  |  |
| Additional support staffing required to deliver the programme |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| Report History |  | First comprehensive update presented. |  |
| Appendices |  | Appendix 1: Integrated Performance Report Appendix 2: Theatre Utilisation |  |