| PHASE | DATE |  |
| --- | --- | --- |
| SETTING DIRECTION | 4th August 2025 | Draft priorities & parameters: Test back with Execs – Informal Exec session |
|  | 20th August 2025 | Draft health board priorities and parameters to MB |
|  | 26th August 2025 | Health Board priorities to IM briefing |
| DEVELOPMENT | 3rd September 2025 | IMTP Workshop – issue priorities and launch process; facilitate plans on a page (24/25) - review and update |
|  | W/C 22nd Sept. – 29th Sept 2025 | Facilitated sessions with Delivery Programme Boards to map delivery actions based on plans on page |
|  | W/C 20th October 2025 | Corporate touchpoints; Digital, Workforce etc |
|  | 24th October 2025 – TBC | Half day workshop - Quarterly performance review; progress to date |
|  | W/C 6th October 2025 – 24th October 2025 | Complete delivery actions |
| REVIEW & SCRUTINY | 30th October 2025 | Present system plan overview to Board Dev. |
|  | 3rd – 14th November 2025 | Scrutiny of delivery actions |
|  | 17th – 21st November 2025 | Scrutiny feedback of delivery actions |
|  | 24th – 28th November 2025 | Updates responding to scrutiny |
|  | 1st – 5th December 2025 | Planning review of scrutiny updates |
|  | 8th – 19th December 2025 | Exec scrutiny/ prioritisation sessions |
| FINALISATION & APPROVAL | Mid Jan 2026 | Agree final draft of Annual plan at MB |
|  | 29th Jan 2026 | Share draft plan with Board members |
|  | 26th Feb 2026 | Final draft plan to go to Board Dev. |
|  | W/C 9th March 2026 | Finalised Plan |
|  | Thursday 26th March 2026 | Board to approve plan |
|  | Tuesday 31st March 2026 | Submit plan to WG |

- Plan style and structure to mirror 25/26 plan

- Plan process to assume planning framework 25/26