| Meeting Date | 31 July 2025 |  | Agenda Item |  |  | 4.7 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Health Board |  |  |  |  |  |
| Report Title | Approval to progress with 5th Linac (Radiotherapy Treatment machine) Business Case |  |  |  |  |  |
| Report Author | Ruth Tovey, Head of Strategic Planning, SBUHB Anne Simpson, Head of Strategic Commissioning, HDUHB On behalf of the SWWCC Regional Radiotherapy Modernisation Group |  |  |  |  |  |
| Report Sponsor | Marie Davies, Executive Director of Planning and Partnerships, SBUHB Lee Davies – Executive Director of Strategy and Planning, HDUHB |  |  |  |  |  |
| Presented by | Marie Davies, Executive Director of Planning and Partnerships |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The South West Wales Cancer Centre (SWWCC) Strategic Programme Case (SPC) was developed to support regional non-surgical oncology services in South West Wales. The SPC specifically refers to radiotherapy and oncology outpatients that will require the development of regional service models and joint business cases. The SPC was signed off by both Swansea Bay University Health Board (SBUHB) and Hywel Dda University Health Board (HDUHB) in January 2023. A key priority for the programme is the expansion of radiotherapy capacity to meet increasing demand. This report seeks Board support for the development of an additional 5th Linear Accelerator (Linac) utilising the current empty bunker in Singleton, plus an additional 6th Bunker in Singleton to ensure capacity is maintained during the Linac replacement programme. The Board is required to approve these developments in order to approach Welsh Government for a capital scoping meeting to formally initiate this major capital project. The paper also highlights the necessity to undertake further reviews for additional capacity within the HDUHB (satellite) or SBUHB geographical areas for a potential 6th and 7th Linac business case in the future. In addition, this paper highlights the proposed approach to progressing the linked capital developments, such as construction of spare bunkers and the ongoing replacement Linac programme. Additional capacity will require additional revenue and an assessment will need to be made by both Boards prior to final approval of any case that the revenue costs are affordable within the overall financial context at the time. Any investment needed will need to be prioritised in the financial plans of both Health Boards. |  |  |  |  |  |
| Key Issues | - Radiotherapy treatment is becoming more suitable for increased numbers of patients with cancer. This supports improved patient outcomes; however, together with increased complexity of treatments, this is generating increased demand for radiotherapy which current capacity in South West Wales is struggling to keep up with. - An additional (5th) Radiotherapy treatment machine, known as a Linac, for the South West Wales region is required to meet demand in 2026/2027, as shown by demand and capacity modelling. - An options appraisal undertaken in 2024 demonstrated the preferred site for the 5th Linac is in the South West Wales Cancer Centre, Singleton Hospital. - Progressing implementation of the 5th Linac requires development of a joint Health Board (SBUHB and HDUHB) revenue and Welsh Government major capital business case. - Regional work has taken place in 2024/25 to commence the 5th Linac business case prior to approaching Welsh Government for scoping and formal initiation of the major capital project. This includes production of estimated revenue costs which have been acknowledged in principle by both Health Boards and, if supported by both Boards, addressed in future financial planning purposes. - There are key interdependent capital radiotherapy developments which need to be considered and included as subsequent phases to the 5th Linac business case, these being the construction of an additional bunker in the South West Wales and the existing Linac replacement programme in SWWCC. - Given the significant revenue implications and the complexities, this paper requests support from Welsh Government to develop the capital and revenue case. Once the final case is available both Boards will need to consider the revenue affordability in the context of the financial climate at the time and any identified investments be factored into the financial plans of the Health Boards as a priority. This position will be made clear to Welsh Government. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☐ | ☒ |  |
| Recommendations | Members are asked to: - APPROVE the 5th Linac and 6th bunker brief in order to approach Welsh Government for a scoping meeting, in view of formally initiating the capital project. - AGREE that should approval to proceed to develop the case be granted by Welsh Government, the revenue affordability of the case will be considered again by both Boards ahead of approval to proceed. Any agreed investment then being prioritised in the financial plans of both Health Boards. - CONSIDER that given the growth in clinical demand, any delay to the commissioning of the of the 5th Linac will require the Health Boards to source alternative treatment capacity/ mitigations which would likely require additional revenue to bridge. |  |  |  |  |  |

APPROVAL TO PROGRESS WITH 5TH LINAC (RADIOTHERAPY TREATMENT MACHINE) BUSINESS CASE

1. BACKGROUND

The South-West Wales Cancer Centre (SWWCC) at Singleton Hospital in Swansea is a vital healthcare facility serving nearly a third of Wales’s population. It is one of three specialist cancer centres in the country, providing non-surgical oncology services to the region. In 2023, both SBUHB and HDUHB approved a 10-year strategic plan (SPC) to improve these services. An essential element of the SPC is the delivery of radiotherapy.

Radiotherapy (RT) is a key treatment for cancer, to achieve cure while maintaining good quality of life. Radiotherapy uses radiation to kill cancer cells and may be used in the early stages of cancer or after it has started to spread. Approximately 50% of all patients require radiotherapy as part of their cancer treatment and this is projected to increase to 60% over the next year.  The SWWCC provides radiotherapy treatment using machines called Linear Accelerators (Linacs). The SWWCC currently operates with four Linacs and one void ‘decant’ bunker, which is essential for replacing equipment without loss of treatment capacity, as replacement can take up to a year.

Radiotherapy is delivered in small portions called ‘fractions’ and advancements in RT techniques now enable more precise treatment over fewer attendances. This ‘hypofractionation’ delayed the anticipated need for an additional 5th Linac in SWWCC by over 5 years. However, more complex approaches, such as Stereotactic Body RT (SBRT) and hypo fractionated RT require more time, typically 2-3 x 30-minute slots per attendance. As a result, ‘slots’ have become the new more accurate metric for measuring activity than fractions or attendances. On average, currently 1 fraction = 1 attendance = 1.4 slots with 12.8 slots per patient RT course.

Two groups were established in 2024/25 under the SWWCC Regional Strategic Programme (within the ARCH governance) to take forward the key pieces of work: -

- Oncology Outpatients Modernisation Group

- Radiotherapy Modernisation Group

Membership includes key members of the SBUHB Oncology Team who provide the clinical advice to the group, i.e. Clinical Director for Oncology, Clinical Lead for Radiotherapy, Head of Radiotherapy Service, and Head of Radiotherapy Physics.

The Radiotherapy Modernisation Group priorities are: -

- 2nd CT SIM at Singleton – Joint Health Board and Welsh Government Capital Case approved January 2025, to be operational end Q2 2025/26.

- An additional 5th Linear Accelerator (Linac) utilising the current empty bunker in Singleton.

- An additional 6th Bunker in Singleton to ensure capacity is maintained during replacement programme.

- Options to site 6th/7th working Linacs as per modelling, within Hywel Dda (Satellite Centre) or Swansea Bay

Key Issues

- Radiotherapy is becoming a more suitable treatment for the increasing numbers of patients diagnosed with cancer. This supports improved patient outcomes; however, together with increased complexity of treatments, this is generating increased demand for radiotherapy which current capacity in South West Wales is struggling to keep up with.

- Access times for radiotherapy at the SWCCC are currently not within national targets (primarily Scheduled and Urgent Symptom Control).

- An additional (5th) Radiotherapy treatment machine, known as a Linac, for the South West Wales region will need to be operational in 2026/2027, as shown by demand and capacity modelling and also a 6th bunker ready to facilitate the Linac replacement programme commencing in 2027/28.

- An options appraisal undertaken in 2024 demonstrated that the preferred site for the 5th Linac is in the South West Wales Cancer Centre, Singleton Hospital.

- Progressing implementation of the 5th Linac and 6th bunker requires development of a joint Health Board (SBUHB and HDUHB) revenue and Welsh Government major capital business case.

- Regional work has taken place in 2024/25 to commence the 5th Linac business case prior to approaching Welsh Government for scoping and formal initiation of the major capital project. This includes production of estimated revenue costs which have been supported in principle by both Health Boards and provisionally taken into account for future financial planning purposes.

- There are key interdependent capital radiotherapy developments which need to be considered alongside the 5th Linac/6th bunker business case

- Given the significant revenue implications and the complexities, it is necessary that both Boards are fully appraised and have provided formal approval to progress to the next phase, i.e. to approach Welsh Government to commence the major capital project.

Demand is outstripping capacity, necessitating the addition of a new (5th) Linac in 2026/27 and a void bunker by 2027/28. Two key factors are driving this increased demand: growth and adaptive radiotherapy.

- Demand & Capacity - The current capacity of the 4 Linacs is 32,525 slots which equates to an average of 8,131 slots per Linac per annum.

Pre-COVID, there was an urgent need to move to a 5th Linac model due to demand exceeding capacity. In 2018 and 2019, 2 cohorts of prostate patients were outsourced to Rutherford Cancer Centre to mitigate this issue. Based on 2019 data, this cost circa £6k per patient to outsource. New developments in (primarily breast) hypofractionation which became mainstream during COVID were able to release Linac capacity to temporarily maintain the 4 Linac model. This resulted in the single CTSim becoming the rate limiting step in ‘machine infrastructure’ capacity and Time to RT workflow, which necessitated the priority capital development of the second CTSim development.

Based on the updated modelled demand and using 8,131 slots per Linac the table below shows the 5th Linac will need to be in place for 2026/27, void bunker by 2027/28 and an additional Linac will be needed in South West Wales almost every 2 years up to 2030/31. By 2030/31, it is projected that 7 working Linacs in total will be required.

For context Velindre NHS Trust serve a population of c1.5million and currently have 10 Linacs (including 2 new satellite Linacs based in Nevill Hall which will be fully operational by June 2025). SWWCC serving a population of c0.9million currently has 4 Linacs and North Wales serving a population of c0.6million has 4 Linacs.

- Adaptive Radiotherapy is an advanced approach to radiation treatment that adjusts the therapy plan in response to changes in a patient’s anatomy or tumour characteristics over time. Unlike conventional radiotherapy, which relies on a static treatment plan, adaptive radiotherapy continuously monitors and modifies the dose and targeting to improve precision and effectiveness. Consequently, the most complex treatment, requires daily ‘adaptation’ of the RT which in turn increases Linac demand – this is driving the need to expand the Linac model to 7 total required by 2030/31.

2. ASSESSMENT

REGIONAL RADIOTHERAPY REQUIREMENTS

5th Linac, Progress to date:

In Summer 2024, a high level strategic options appraisal for the siting of 5th Linac was completed with stakeholders in SBUHB/HDUHB. This demonstrated that the SBUHB site (specifically, using the space in place of existing, currently empty 5th bunker on SWWCC site) is the preferred option for the 5th Linac development, due to feasibility within the 2026/27 timeline. Appendix 2 provides the Options Appraisal document.

Summary papers were shared with SWWCC Regional Strategic Group, ARCH Regional Strategic Group, SBUHB Cancer Programme & Information Group and HDUHB SRC /SDOC committees. A version of the paper has been through the Strategy and Planning Committee in April 2025. This paper has been updated to incorporate the 6th Bunker at Singleton to ensure the viability of the ongoing replacement programme.  It also further clarifies the link between the 6th & 7th Linac and opportunity for a satellite centre in Hywel Dda. On this basis, estimated revenue costs for the 5th Linac have been prepared, circa total £2m spilt equally between HBs – see Finance Implications section for details.

In terms of the programme timelines the capital timeline for completion of works if the 5th Linac and 6th bunker need to be built together could be for programme of works is around 24 month end to end but if the works can be uncoupled this would be circa 18 months (see Governance and Risks section for detail on implications of this). This paper is not seeking approval to commit revenue, it is seeking approval to approach Welsh Government to discuss scoping and developing a case, ahead of board Boards considering the final case when available. Should the case be acceptable to both Health Boards the revenue requirements will need to be prioritised in future years’ financial plans.

6th Bunker in Singleton (to maintain capacity) to be in place by 2027/28

As the preferred option is for the 5th Linac to go into the existing spare (5th) bunker on SWWCC site, this will leave no spare bunker, until a 6th (void space or decant) bunker is constructed. There are risks to not having a spare bunker, including service interruptions and limited flexibility which could lead to delayed treatments and impact on patient outcomes.

The 6th (void space) bunker must be in place by 2027/28, to support the next planned replacement.  The replacement schedule is a national requirement as set out by the Service Specification for External Beam Radiotherapy Services in Wales approved by all Health Boards and NHS Trusts in Wales, as Linacs have a lifespan of about 10 years. The replacement of the next ‘oldest’ machines in Singleton will take place around every two years from 2027/28.

On 7th May 2025, the Regional Joint Committee formally acknowledged that the original business case for the 5th Linac has been amended to now incorporate the addition of a 6th bunker at Singleton Hospital by 2027/28.

Expansion to a 7 Linac Model across South West Wales / Potentially a satellite in Hywel Dda

There needs to be consideration of an option for expanding to a 7 Linac model on a phased basis to enable 6 Linacs to be operational from 2028/29, and 7 Linacs to be operational by 2030/31. This would meet the demand and capacity projections for the region, as outlined in the table above.

Having benchmarked radiotherapy requirements, the South West Wales region requires 7 Linacs (this would be proportionate and equivalent to provision in the South East, which has 10 Linacs).

A full strategic options appraisal will be carried out to determine whether these could be located within either SBUHB or HDUHB sites.

Depending on the outcome, if HDUHB is the favourable site, this would then progress to a satellite centre.  This has clear benefits for the HDUHB population in terms of travel time to a Linac, directly linked to the % accessing this key cancer treatment option.

Summary

The following schematic sets out the proposed phases, timelines and key decision points for the developments outlined above:

3.  GOVERNANCE AND RISK ISSUES

Risks and Mitigations

Risks: As per the demand and capacity modelling, there is an urgent need to progress with implementation of the 5th Linac and the development of a 6th void bunker. Refreshed demand and capacity modelling has demonstrated the 5th Linac is required to be operational in 2026/2027 and the 6th void bunker in place by 2027/28. However, given the complexity of the steps involved (i.e. the development requires a formally approved Joint HB revenue and Welsh Government major capital business case, and then capital build/ clinical commissioning), there is a significant risk that this timeline may not be met.

If the timeline is not met there is a risk that backlogs in the Radiotherapy treatment pathway will occur and impact on delivery of the Welsh Government reported quality measure, ‘Time to Radiotherapy’ and to a lesser extent the Ministerial Priority ‘Time to First Definitive Treatment’. This could adversely affect patient safety and quality if not resolved. The Health Board would therefore need to creatively source additional capacity to meet demand and maintain access to treatment for this patient group; see mitigation section below.

The 5th Linac machine carries substantial revenue costs. At this point, the indicative revenue costs (5th Linac) have been acknowledged by both SBUHB and HDUHB, however this is subject to full business case scrutiny by Health Boards through respective governance processes. The final decision to proceed to implement the case, should it be supported to proceed by Welsh Government, will be a matter for both Boards once the case is fully developed and if so will need to feature as a priority in future financial plans for both Health Boards.

Mitigation: There are a number of options to be considered, however financials and feasibility assessments will need to be identified and worked through jointly. At this point, these could include: -

- Outsourcing (Private and NHS) – Costs likely to exceed that of the 5th Linac development revenue costs (early calculations suggest outsourcing equivalent activity would equate to £2.3m per annum), while also potentially poorer for patients in terms of experience and outcomes. Currently the Rutherford Cancer Centre, previously used for this purpose, is not operational.

- Temporary Linac machine – to be confirmed if feasible.

- Increased hrs/weekend working (extended working) of existing Linac machines – would need to fit in with maintenance and limited sustainability with existing workforce.

All of the above are short term solutions only. A thorough appraisal of these options will be included in the business case. It would be prudent for the Boards to develop strong mitigating plans to ensure that sufficient capacity is available to meet demand should the 5th Linac not be available as indicated by the timeline; the absolute timing of the 5th Linac’s operational date will be determined by the detailed design and commissioning work to be undertaken.  Time to Radiotherapy is currently on the SBUHB Risk Register with a score of 20; this is likely to increase to 25 should the 5th Linac not be in place in 2026/27

4.  FINANCIAL IMPLICATIONS

.

5th LINAC – revenue costs (indicative)

The table below provides an initial estimated revenue cost of £2m for the 5th Linac. A more detailed breakdown of the costs is available, however in summary the 5th LINAC requires an additional 21.30 WTEs which costs c£1.44m per annum (and non-pay totals £0.53m (of which £0.3m relates to new adaptive RT non pay costs). The cost sin the table below are full year revenue costs and may have a part year effect in one year depending on commissioning timescales.

|  |  | Indicative Costings (NB. pay based on top of scale 2024/25 pay scales) | Current Baseline |  | Additional |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 4 Linacs |  | 5th Linac |  |  |  |
|  |  |  | WTE | £000s | WTE | £000s |  |  |
|  |  | Pay Costs - Medical Physics | 19.70 | 1,516 | 6.80 | 466 |  |  |
|  |  | Pay Costs - Radiotherapy* | 43.75 | 2,440 | 13.50 | 829 |  |  |
|  |  | Pay Costs - Oncology Consultants | 4.00 | 579 | 1.00 | 145 |  |  |
|  |  | Total Indicative Pay Costs | 67.45 | 4,535 | 21.30 | 1,439 |  |  |
|  |  | Non Pay - Medical Physics & Radiotherapy |  | 697 |  | 213 |  |  |
|  |  | Non Pay - New Adaptive RT |  | 0 |  | 314 |  |  |
|  |  | Total Indicative Non Pay Costs |  | 697 |  | 527 |  |  |
|  |  | Facilities Management Costs |  | 159 |  | 40 |  |  |
|  |  | Total Indicative Cost | 67.45 | 5,391 | 21.30 | 2,006 |  |  |
|  |  | * Radiotherapy Pay costs above include 2.5wte advance practitioner posts (£194k) that is not specific to 5th Linac |  |  |  |  |  |  |

Finalised costings will be subject to the development of the full business case, once this has been agreed to proceed by Welsh Government. Scrutiny on the detail of costings will be undertaken through the respective governance organisations as required for formal approval of the revenue costs, which would be spilt (50/50) jointly between SBUHB and HDUHB in line with agreed commissioning principles set out in the SPC.

6th Bunker – revenue costs

It is anticipated that the 6th bunker will incur minimal revenue impact.

The contractual mechanism between the organisations for radiotherapy treatment is based on staffing model as opposed to a cost & volume. The current cost sharing mechanism will continue to exist, albeit recognising the increased costs which would be borne between the two Health Boards. Costs will only start to be incurred once staffing posts have been recruited.

Workforce – SBUHB is currently working on the workforce strategy and will share once completed.  However, SBUHB does not envisage any issues with the staffing of the 5th LINAC.  SBUHB is already working on strategies for alternative routes to registration (to ensure the workforce) and training for advanced and Consultant Radiographers. They are working with HEIW on funded training at all levels.

For clarity, the request in this paper is to approach Welsh Government, through the capital planning team, to commence scoping and then to prepare the detailed business case as outlined above. Approving this paper will not commit the Board to additional revenue spend which will need to be considered separately by both Boards (and if approved prioritised in future financial plans) once the case is prepared in full.

5. RECOMMENDATIONS

Members are asked to:

- APPROVE the 5th Linac and 6th bunker brief in order to approach Welsh Government for a scoping meeting, in view of formally initiating the capital project.

- AGREE that should approval to proceed to develop the case be granted by Welsh Government, the revenue affordability of the case will be considered again by both Boards ahead of approval to proceed. Any agreed investment then being prioritised in the financial plans of both Health Boards.

- CONSIDER that given the growth in clinical demand, any delay to the commissioning of the of the 5th Linac will require the Health Boards to source alternative treatment capacity/mitigations which would likely require additional revenue to bridge

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Improving Radiotherapy is linked to improved patient quality, safety and experience. |  |  |  |
| Financial Implications |  |  |  |
| As set out in the paper |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| Full business case will be subject to QIA and EQIA |  |  |  |
| Staffing Implications |  |  |  |
| As set out in the paper |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The Annual Plan aims to deliver our Strategic Objectives which were aligned to our Wellbeing Objectives through the development of the Organisational Strategy. This paper sets out the alignment of the approved Health Board Wellbeing Objectives directly to the Annual Plan Deliverables. |  |  |  |
| Report History |  | A Version of the report will be shared with HDUHB Health Board for approval. |  |
| Appendices |  | Appendix 1: 5th Linac Options Appraisal Appendix 2: RT Performance Reporting as at April 2025 |  |

The NHS Wales Executive (2024). Service Specification of External Beam Radiotherapy services for the NHS in Wales.