| PHASE | DATE | WHAT/ DETAIL |
| --- | --- | --- |
|  | By mid-Oct 2025 | COMPLETE - Confirm Templates and Documentation for completion by Programme Boards |
|  | Sept / Oct 25 | COMPLETE - Engagement with Programme Boards |
|  | 30th Oct | COMPLETE - Annual Plan 26/27 Development Touchpoint Workshop |
|  |  | Revision of System Plans on a Page to agree Year 1 priorities and Work Programmes, and confirm processes, documentation, and timelines for finalising Operational Plan Delivery Actions. |
|  | 31st Oct - 21st Nov | Developing Operational Plan Delivery Actions |
|  |  | Programme Boards, working with Service Delivery Groups, to complete Operational Plan Delivery Actions to deliver System Priorities and Work Programmes using Planning Team templates that will detail requirements and expected outputs/benefits. Drafts are to be submitted to the Planning Team by Friday 21st November. |
|  | 31st Oct - 21st Nov 25 | Corporate touchpoints sessions |
|  |  | Support for developing Operational Plan Delivery Actions will cover Digital, Finance, Workforce, Quality, Performance, and Planning |
|  | 19th Nov 25 | Management Board meeting: Update on Plan |
|  | 25th Nov 2025 | Performance & Finance Committee meeting: Update on Plan |
|  | 27th Nov 2025 | Health Board meeting: Update on Plan |
| REVIEW & SCRUTINY | 3rd Dec 2025 | Annual Plan 26/27 Development Touchpoint Workshop |
|  |  | Programme Boards to share Operational Plan Delivery Actions, clarifying assumptions and expected 12-month deliverables, highlighting gaps and options to address them for triangulation |
|  | 3rd – 12th Dec 25 | Corporate scrutiny of Operational Plan Delivery Actions |
|  |  | Planning, Finance, Workforce, Digital, Quality, and Performance teams will undertake corporate scrutiny of Operational Plan Delivery Actions |
|  | 16th Dec 25 | Performance & Finance Committee meeting |
|  | 17th Dec 25 | Management Board meeting |
|  | 18th Dec 25 | Board Development meeting |
|  | 20th Dec – Early Jan 26 | Programme Boards update to Operational Plan Delivery Actions |
|  |  | Programme Boards will update Operational Plan Delivery Actions in response to corporate scrutiny and Welsh Government guidance, developing detailed milestones for delivery. |
|  | Mid Jan 26 | Annual Plan 26/27 Development Touchpoint Workshop |
|  |  | Focused sessions will be held with Executives for System area leads to review and respond to comments, informing final decisions on inclusion in the Plan. |
| FINALISATION & APPROVAL | 26th Feb 26 | Final draft Plan to Board Development |
|  | W/C 9th Mar 26 TBC | Annual Plan 26/27 Development Touchpoint Workshop |
|  |  | Finalise plan |
|  | 26th Mar 26 | Board to receive Plan |
|  | 31st Mar 26 | Submit Final Plan to Welsh Government |