## Slide 1
Project:
Delivery Plan: Transfer of Patients from Gorseinon to Singleton
EW/MC
Ops Leads PCT/Sing
PH/SP
Nursing Leads PCT/Sing
MD/JH
Workforce Leads
Lead
Emily.warren3@wales.nhs.uk
Melanie.collins@wales.nhs.uk
Paula.heycock@wales.nhs.uk
Sharron.price2@wales.nhs.uk
Melanie.dellibovi3@wales.nhs.uk
Contact
Brief description
To improve patient safety and staff wellbeing in Gorseinon achieve the urgent temporary relocation of West Ward to Singleton Hospital. This has been agreed to commence from 3/10/25-31/03/26. A daily Operational Group (OG) of senior clinical and ops leads has been established to oversee delivery within the agreed timeframe.
The OG includes:
PCT- Associate Group Director/Head of Nursing
SINGLETON HOSPITAL- Associate Director (Ops)/ Head of Nursing
WORKFORCE- HR Business Partner PCT/Singleton
SUPPORT SERVICES- Head of Support Services
Aims and objectives
Achieve the decant of the current bed occupancy in Gorseinon of approx. 6 beds per week.
Achieve the safe transfer of remaining patients of west ward over to Singleton Hospital from 1st October, subject to HB decision to transfer due 25.09r
Key deliverables / milestones
Established 01/09
Commenced 01/09
Scheduled 03/09
TBC
Commenced 02/09
Scheduled 07/09
Via OSG
Scheduled from 07/09
Commenced 02/09
By when
Establish Daily Operational Steering Group to oversee implementation and manage risk (EW)
Pause admissions to Gorseinon and implement bed reduction plan by 6 beds per week, over 4 weeks from Sept 1st. (EW)
Hold engagement meetings with all staff groups working in Gorseinon & Trade Unions (03/09/25) (MD)
Submit Proforma/Hold engagement meeting with Llais (10.09) (ED/JAD)
Review available bed/locker stock in Gorseinon to transfer to Singleton (23 beds required- if not available will go out to contract) (CD)
Commence patient profiling to identify the patients who will need to transfer and engage with families. (CD)
Agree patient transfer plan w/b 22nd Sept
Liaise with NEPS to ensure availability of transport for transfer plan.
Agree workforce model/Availability required to staff the wards using substantive staff (MD/LW)
Initial risk assessment (Critical 3)
Increased staff absence following communications around temporary closure; reduced availability
Reduced morale/disengagement, productivity; impact on patients
Increased financial costs of staff absence, operational delays as a result of staff unavailability
Acceptance of temporary USC from Llais
Mitigation
Authorisation for variable pay/agency spend in advance of staff engagement to support increased staff absence
Deployment of staff to cover Ward 3 from other hospital sites
Review of planned leave only if strictly necessary
Wellbeing support, additional peer support
Temp Transport for staff
Jessica.harris@wales.nhs.uk