Appendix E

Triple A Report- REGIONAL AND SPECIALISED SERVICES

|  | REGIONAL AND SPECIALISED SERVICES |  |
| --- | --- | --- |
| Date of update: |  | August 2025 |
| Key achievements/ highlights of the reporting period |  | - Received and endorsed the Specialised Infectious Diseases workshop implementation report, with agreement to escalate recommendations and risks to CEMT. - Provided an update on SAP management, including CVUHB’s letter to Health Boards proposing a temporary prior approval protocol until formal commissioning arrangements are established. - Approved amendments to the Memorandum of Understanding, reflecting updated governance arrangements. - Agreed to undertake a joint review of risks submitted to NWJCC for the 2025/26 IMTP to inform 2026/27 planning. - Received an update on the JACIE inspection of the South Wales BMT service and its potential implications. - Considered NWJCC’s request for a collaborative approach to immunophenotyping for acute leukaemia, and agreed to defer until LIMS 2 implementation is complete. |
| Key priorities for the forthcoming period |  | - Submit the Specialised Infectious Diseases report to CEMT and communicate implications of non-implementation. - Monitor progress on the implementation of the prior approval protocol for managing patients with SAP. - Coordinate the joint risk review to support NWJCC engagement for the 2026/27 IMTP. - Prepare both sites (CVUHB and SBUHB) for the JACIE inspection and assess contingency planning if accreditation is not secured. |
| Risks and mitigating actions |  | - Risk: Delay in implementing the Specialised Infectious Diseases service may impact on future service delivery. Mitigation: Escalate to CEMT with clear articulation of risks and recommendations. - Risk: Lack of formal commissioning for SAP services may compromise service sustainability. Mitigation: Temporary prior approval protocol proposed; further engagement with Health Boards underway. - Risk: Potential loss of JACIE accreditation for BMT service. Mitigation: Early identification of impacts and contingency planning initiated. - Risk: Immunophenotyping collaboration delayed due to LIMS 2 dependency. Mitigation: Clear communication with NWJCC; revisit once LIMS 2 is operational |
| Summary |  |  |
| Alert |  | - The BMT service faces significant risk if JACIE accreditation is not achieved, with potential implications for service continuity and patient care. |
| Advise |  | - Members are advised to ensure internal escalation of the SAP commissioning issue. - Members are advised to maintain oversight on the outcome of the JACIE inspection. - Continued engagement with NWJCC is recommended to align future commissioning priorities with organisational capacity |
| Assurance |  | - The RSSPPP continues to provide a structured forum for collaborative decision-making and oversight of specialised services. - Clear actions have been agreed to manage immediate risks and to progress strategic planning for sustainable service delivery |