DATED _______________________________________________

TRANSITIONAL

Memorandum of Understanding

between

SWANSEA BAY UNIVERSITY LOCAL HEALTH BOARD

and

HYWEL DDA UNIVERSITY LOCAL HEALTH BOARD

OPerational delivery network South-West Wales Regional Pathology 2024/2025

CONTENTS

____________________________________________________________________________

CLAUSE

1.	Background.	3

2.	Definitions……………………………………………………..………..……..………………… ….5

3.	Agreed Goals for the Programme	6

4.   Contributions……………………………………………………………...………………………  …6

5.	Principles of Collaboration	6

6.	Project Governance	7

7.  	Employment of Staff……………………………………………………………………………….10

8.	Escalation………..…………………………………………………….……….…………… …….11

9.	Risk Management………………………......……………………………….………………… …11

10.	Intellectual Property……………………..……………………………………………………… ..12

11.	Data Protection and Information Governance…………………..…………………………… ..12

12.	Term and Termination……………………………………….….………..……………………… .12

13.	Variation…………...………………………………...………………………………………… …..12

14.	Charges and Liabilities………………………..…………...……………..……………………… 12

15.	Ownership of Assets……………………………………..……………….……………… ………13

16.	Procurement…………………………..………………………………...……………………….. .13

17.	Host Health Board - Duty of Care…………….………...………………………………………..13

18.	Management of Concerns………………………..……………………….……………….……..14

19.	Audit…………………………..………………………………………………………………….…15

20.	Effect of ODN on SBUHB's Core Functions…………………...……..………………………...15

21.	Status of MoU………………………………..………………..……..………………….…………16

ANNEXTURES

ANNEX A - The Project	18

ANNEX B - Information Sharing Protocol	21

ANNEX C - Terms of Reference	22

ANNEX D - Contributions	23

This Transitional MoU is dated _____________________________

Parties

SWANSEA BAY UNIVERSITY LOCAL HEALTH BOARD of One Talbot Gateway, Baglan Energy Park, Baglan, Port Talbot, SA12 7BR (SBUHB)

HYWEL DDA UNIVERSITY LOCAL HEALTH BOARD of Second Floor, Block C, Government Buildings, Picton Terrace, Carmarthen SA31 3BT (HDUHB)

- Each a Health Board and together the Health Boards as the context requires.

Background

- 1.1	On 22nd November 2022, SBUHB and HDUHB submitted a Report to their respective Boards to take forward the development of an Operational Delivery Network (ODN) as the management model for South-West Regional Pathology Services (“Service”). The Report recommendations were approved in both public Board meetings, confirmed in minutes. HDUHB agreed to collaborate with SBUHB to establish the ODN. The re-designed regional pathology service (“Project”) will bring together two organisations; SBUHB and HDUHB laboratory-based services under one umbrella. In time, it is planned that the ODN will also lead on behalf of the organisations in the commissioning of:

- 1.1.1	a microbiology services for the region. Currently, these are provided in the majority of instances by Public Health Wales (PHW). This change will facilitate delivery of a new regionalised and co-located service model, supported by integrated management and a joint Health Board workforce; and

- 1.1.2	a regional pathology hub laboratory. The proposed hub laboratory will incorporate regional services for cellular pathology, laboratory medicine, microbiology, immunology and specialist reference units and precision medicine laboratories.

- The term “Laboratory Medicine” is used throughout the document to refer to the discipline known as Blood Sciences in Hywel Dda, as well as any equivalent service created by the amalgamation of SBUHBs Laboratory Medicine and HDUHB’s Blood Sciences services.

  - Major aspects of the case for change to develop the Project are based on workforce fragility (which has now reached a critical phase), future proofing for demand and developments in service delivery, financial efficiencies and estates with significant backlog maintenance and of a design that is not fit for purpose to deliver modern laboratory services in the majority of cases. The pathology service must be developed to meet service user’s changing expectations in respect of high quality, safe and efficient health care services and the delivery of these services as close to home as possible. The pathology service must embrace competitiveness and a commissioner-led focus. It requires strong local clinical leadership and a business orientated management infrastructure, focusing on productivity by matching the workforce to activity, workflow and the roles and functions that are needed to deliver the ODN, through improving systems and processes and realising the benefits of new technology. The ODN will be a partnership between participating organisations, working collaboratively to achieve its common goals and purpose.

This is a transitional Memorandum of Understanding (“Transitional MoU”) and its purpose is to outline the accountability arrangements and resulting responsibilities of the Health Boards in respect of the transitional ODN model, to act as the (transitional) hosting agreement between the Health Boards and to bridge the gap before the Health Boards enter into the MoU for the ODN which will come into effect after the transitional phase has completed, when the final details of the ODN have been agreed. This Transitional MoU should be read in conjunction with the Report to SBUHB’s Board dated 22nd November 2022. This Transitional MoU is between SBUHB and HDUHB only. It is envisaged that separate agreements (MoUs etc.) will be entered into by the Health Boards for commissioning arrangements pursuant to the MoU for the ODN after the transitional phase has completed.

The future ODN will be hosted and managed by SBUHB. This hosting role is entirely separate from the role of SBUHB as a provider of pathology services and all references to SBUHB throughout this Transitional MoU (unless otherwise stated) refer to SBUHB’s role as host of the ODN. SBUHB will ensure a clear distinction between its day-to-day operational responsibilities, as a health care provider for its local population and its responsibilities as the host of the ODN.

The Health Boards have agreed to work together on the Project detailed in Annex A.

The Health Boards wish to record the basis on which they will collaborate with each other on the Project. This Transitional MoU sets out:

the key objectives of the Project;

the principles of collaboration;

the governance structures the Health Boards will put in place; and

the respective roles and responsibilities the Health Boards will have during the Project.

Definitions

- “Data Protection Legislation” means all applicable data protection and privacy legislation in force from time to time in the UK including the retained EU law version of the General Data Protection Regulation ((EU) 2016/679) (UK GDPR); the Data Protection Act 2018 (DPA 2018) (and regulations made thereunder) and the Privacy and Electronic Communications Regulations 2003 (SI 2003/2426) as amended; and

"Intellectual Property Rights” means any and all patents, trade marks, service marks copyright, moral rights, rights in design, know-how, confidential information and all or any other intellectual or industrial property rights whether or not registered or capable of registration and whether now or in the future subsisting in the United Kingdom or any other part of the world together with all or any good will and accrued rights of action;

“Programme of Work” means the development of the Pathology ODN in its transition period (up to 31 March 2028). This includes;

The development of the leadership team and any associate staff changes to existing pathology leadership structures.

The process by which pathology staff transfer from existing employers to the ODN under the hosted arrangements.

The programme management of the development of the network via the existing programme management arrangements and resources.

- (iv)	Develop and agree a commissioning arrangement to include a service specification, commissioning method and financial consideration of investment and risk approach

- (v)	Ensuring the parallel production of the capital business case for the Hub Laboratory and spoke refurbishments continues to reflect the changing regional nature of pathology service provision and that the regional management team fully engage with the capital business case process to produce a robust, region OBC for the capital infrastructure to support the network in future years.

Agreed Goals for the programme

On 25 September 2025, the Health Boards agreed the following:

To develop a fully integrated regional cellular pathology service (Option 5) in a single facility for South West Wales.

To progress development of a NHS developed and managed regional service.

- (c)	To develop a business case to support the conversion of one of the two preferred site options for the development of a regional cellular pathology and through the development of that business case confirm the preferred option

    - The continued exploration of external partnership opportunities (e.g. reporting service, managed service contract for specialist laboratory equipment)

    - To develop a single regional service pathology hosted by Swansea Bay as outlined in the Transitional Memorandum of Understanding re-endorsed in

    - To review any pathology leadership vacancies that emerge in either organisation whilst the capital solution is being developed for regional replacements or alternative interim arrangements/consolidation.

    - To consider options to relieve pressure on Glangwili and implement a transitional plan to consolidate some services at Singleton (e.g. specialist services)

- 4.	Contributions

- 4.1	The Health Boards acknowledge that the current position with regard to the Project and the contributions already made or to be made (financial and otherwise) are as detailed in Annex D to this Transitional MoU.

- 5.	Principles of Collaboration

5.1	The Health Boards agree to adopt the following principles when carrying out the Project (Principles):

  - collaborate and co-operate. Establish and adhere to the governance structure set out in this Transitional MoU to ensure that activities are delivered and actions taken as required;

  - be accountable. Take on, manage and account to each other for performance of their respective roles and responsibilities set out in this Transitional MoU;

- (c)	be open and transparent. Communicate openly about major concerns, issues or opportunities relating to the Project to inform good decision-making and to minimise risk;

  - learn, develop and seek to achieve full potential. Share information, experience, materials and skills to learn from each other and develop effective working practices, work collaboratively to identify solutions, eliminate duplication of effort, mitigate risk and reduce cost;

- (e)	adopt a positive outlook. Behave in a positive, proactive manner;

- (f)	adhere to statutory requirements and best practice. Comply with applicable laws and standards including public procurement rules, data protection and freedom of information legislation. In particular, the Health Boards agree to comply with the requirements of the Information Sharing Protocol attached to this Transitional MoU in Annex B;

- (g)	act in a timely manner. Recognise the time-critical nature of the Project and respond accordingly to requests for support;

    - manage stakeholders effectively;

    - deploy appropriate resources. Ensure sufficient and appropriately qualified resources are available and authorised to fulfil the responsibilities set out in this Transitional MoU. In particular the parties agree to make the contributions detailed in Annex D to this Transitional MoU;

    - act in good faith to support achievement of the Key Objectives and compliance with these Principles;

    - be mutually supportive, respecting the statutory status and independence of all participating organisations; and

    - be valued at the highest levels within the ODN, with visible leadership, clear lines of accountability and a coherent collaborative approach.

- Project Governance

- 6.1	Overview

As a non-statutory organisation without legal identity, the ODN does not in itself possess constitutional rights, but rather it will fall under the governance arrangements of its host organisation, SBUHB. Commissioners will continue to be accountable for the commissioning of services and providers will continue to be accountable for the delivery of services. Each Health Board would either be separately or collectively accountable for the commissioning of services.

The Health Boards will have in place appropriate governance arrangements and Schemes of Delegation as may be necessary and required in order to carry out their respective functions within the ODN.

The ODN will be accountable to SBUHB for all arrangements pertaining to the running of the ODN. This will include, but not be limited to, employment of staff to work within the ODN, provision of all employment HR and corporate services, accommodation and training.

The governance structure defined below provides a structure for the development and delivery of the Project.

- 6.2	Guiding Principles

The following guiding principles are agreed. The Project's governance will:

    - provide strategic oversight and direction;

    - be based on clearly defined roles and responsibilities at organisation, group and, where necessary, individual level;

    - align decision-making authority with the criticality of the decisions required;

    - be aligned with Project scope (and may therefore require changes over time);

    - leverage existing organisational, group and user interfaces;

    - provide coherent, timely and efficient decision-making; and

    - correspond with the key features of the Project governance arrangements set out in this Transitional MoU.

- 6.3	Functions of ODN Leadership Team in connection with the Transitional ODN and Recruitment

- The ODN Leadership Team acts as a resource, co-ordinator and facilitator for all its stakeholders to achieve a collaborative approach to safe and equitable and effective specialised pathology services. It is envisaged that the Leadership Team will perform the following functions:

- To be operationally responsible for the delivery of the Pathology ODN and all of its associated services.

- To work alongside the Network Director to provide senior leadership, operational accountability and resource management.

- To lead on Quality and Safety for the Network.

- To take responsibility for the duties set out in Section 18 (Duty of the designated individual) of the Human Tissue Act 2004.

- To lead the operational running of Mortuary services in both Health Boards under the direction of the Mortuary services MOU.

- There will be recruitment into a fixed term post linked to the establishment of the Network. However, this fixed term post is not required for the recurrent running of the service once established and the senior leadership team is in place.

- 6.4	Provider Organisations within the Transitional ODN

- The following organisations shall perform the following ODN functions:

| - Organisation | - Function |
| --- | --- |
| - Swansea Bay University Health Board | - ODN host organisation, and - Commissioner of the ODN |
| - Hywel Dda University Health Board | - Commissioner of the ODN |
| - Public Health Wales | - Provider of majority microbiology services in region. Commissioned by HDUHB and SBUHB (not in scope for this phase, but potentially subject to later commissioning arrangements). |
| - Regional Joint Committee of Swansea Bay University Health Board and Hywel Dda University Health Board | - Hywel Dda University Health Board and Swansea University Health Board are joint members of the Regional Joint Committee leading the programme supporting change in service delivery i.e. the formation of the ODN. |

- 6.5		Governance Structure

- Governance is through the ODN Steering Group to provide overall strategic oversight and direction to the Project; the Terms of Reference (ToR) is provided in Annex C. The Terms of Reference of the RJC and Clinical Services Subgroups are also listed in Annex C – Appendix 1.

- 6.6	Each Health Board is a body corporate under s11 of the National Health Service (Wales) Act 2006. As such, each Health Board shall refer all matters in respect of this Transitional MoU[,to their respective Boards for decision-making.

- 7.	Employment of Staff

7.1	The working assumption is that  when the ODN takes effect (and not during the phase of this Transitional MoU) it is anticipated that there will be a “relevant transfer” for the purposes of the Transfer of Undertakings (Protection of Employment) Regulations 2006 (as amended) (“TUPE”) i.e. the ODN function for pathology services is formed by transferring existing staff into the ODN host organisation (SBUHB) and the assumption is that TUPE will apply to staff who are in scope to transfer under TUPE at the commencement of the provision of the pathology services. Any new posts are appointed to SBUHB as ODN posts and therefore, TUPE on commencement of services will not apply to these new posts.

In the event that the Transitional MoU proceeds to the MoU for the ODN, the existing employer, will be responsible for any TUPE arrangements (e.g. the obligation to inform and consult with appropriate representatives (where appropriate) and provide Employee Liability Information under regulation 11, TUPE) and in respect of re-tendering and the handover of services. If and when the provision of pathology services under the ODN expires or terminates pursuant to applicable contracts, SBUHB, as the employer under the ODN, will be responsible for the application of TUPE (e.g. the obligation to inform and consult with appropriate representatives (where appropriate) and provide Employee Liability Information under regulation 11, TUPE) and in respect of re-tendering and the handover of services.

As part of the transitional phase/this Transitional MoU, the Health Boards shall agree which services are to be transferred to the ODN and consequently, which staff are in scope to TUPE transfer. This information will be used to inform the MoU for the ODN and will be captured in the ODN Service Specification as and when developed.

- 7.2	SBUHB shall be responsible for the appointment of staff in line with the posts agreed through the Pathology ODN Operational Group.

7.3	New staff appointed to work within the ODN will be employed by SBUHB, they will be entitled to be treated as any other SBUHB employee.  They will be expected to abide by all SBUHB policies, procedures and guidance including, but not limited to, fire safety and health and safety procedures. ODN staff will benefit from access to all applicable policies and procedures including training and development.

7.4	The ODN staff will be accountable for their performance to the Service Group Director, who, for this role, is accountable to the ODN Senior Responsible Officer Director in SBUHB.

7.5	The ODN core team will work across the Network flexibly to meet the needs of the service and provide a visible presence in all sites.  Some posts in the Network will be regional roles, i.e. working across or being responsible for services across multiple sites. ODN staff will require practice rights in both Health Board organisations regardless of their normal ‘base’ site as they could be required to work across the network as part of their roles. In the transitional phase and prior to any TUPE transfer, those staff who have been identified as working across both Health Board sites will be given practice rights to practice within both sites. Such rights will be supplemental to the staffs’ existing contracts (via a collateral contract or “side letter”), which will bridge the gap prior to implementation of the MoU for the ODN and the TUPE transfer. On the relevant TUPE transfer date, the side letter will remain in force (for the duration of the contract or for as long as cross-site practice rights are necessary), to provide for cross-site practice rights where applicable to those staff who are required to practice within both Health Board sites.

7.6	ODN staff members will be expected to maintain professional CPD, complete all mandatory training and uphold competencies in line with the requirements of the role. New ODN staff will be subject to all SBUHB HR policies including annual appraisals/PADR and disciplinary processes ODN staff in training will be expected to work in the geographic areas of both Heath Boards, as part of their training.

- 8.	Escalation

- 8.1	If either Health Board has any issues, concerns or complaints about the Project, or any matter in this Transitional MoU, that Health Board shall notify the other Health Board and the Health Boards shall then seek to resolve the issue by a process of consultation. If the issue cannot be resolved within a reasonable time, the matter shall be escalated to the Cellular Pathology ODN Steering Group, which shall decide on the appropriate course of action to take. If the matter cannot be resolved, it will be escalated to the CEOs of both organisations.  If the CEOs cannot resolve the dispute, it will be escalated to Welsh Ministers for resolution.

- 9. 	Risk Management

- 9.1	A risk management arrangement and process will be established in the event of closure of the ODN. This will include an assurance process to ensure risks are identified, analysed, evaluated, controlled, monitored and communicated appropriately.

- 9.2 	A quality assurance process will be undertaken to ensure consistency of standards and quality of care across the ODN. This will include ODN facilitated external/internal peer review undertaken as appropriate.

- 9.3 	There will be an ODN escalation plan and structures established in the event of a major incident / surge with links to appropriate organisations for effective emergency preparedness, resilience and response arrangements.

- Intellectual Property

  - The Health Boards intend that notwithstanding any secondment, any Intellectual Property Rights created in the course of the Project shall vest in the Health Board whose employee created them (or in the case of any Intellectual Property Rights created jointly by employees of both Health Boards in the Health Board that was instrumental in  creating the Intellectual Property Right).

  - Where any Intellectual Property Right vests in either Health Board in accordance with the intention set out in clause 10.1 above, that Health Board shall grant an irrevocable licence free of charge to the other Health Board to use the Intellectual Property Rights for the purposes of the Project.

  - Each Health Board shall retain all title, right and interest in and to its respective Intellectual Property Rights.

  - Property Rights created prior to the effective date of, or outside the scope of, this Transitional MoU (“Background IP”).  Save as expressly granted under this clause 10 or as otherwise agreed herein, nothing in this Transitional MoU shall be construed as a transfer, licence and/or assignment from one Health Board to the other of ownership of, title, right or interest in and to its respective Background IP.

Data Protection and Information Governance

11.1	The Health Boards agree to comply with the requirements of the Information Sharing Protocol and to enter into a Data Sharing Agreement as applicable, as attached to this Transitional MoU in Annex B.

- 12.	Term and Termination

- 12.1	This Transitional MoU shall commence on the date of signature by both Health Boards, and subject to clause 12.3, shall expire on 31 March 2028 or on completion of the Project, whichever is the latest.

- 12.2	If the Project is not completed by 31 March 2028, the Cellular Pathology ODN Steering Group shall propose the time period of extension for the Transitional MOU for decision by both Health Boards in their Board meetings.

- 12.3	Either Health Board may terminate this Transitional MoU by giving at least six months' notice in writing to the other Health Board at any time.

- 13.	Variation

13.1	This Transitional MoU, including the Annexes, may only be varied by written agreement of the Cellular Pathology ODN Steering Group.

- Charges and Liabilities

  - Except as otherwise provided, the Health Boards shall each bear their own costs and expenses incurred in complying with their obligations under this Transitional MoU.

  - The Health Boards agree to share the costs and expenses arising in respect of the Project between them in accordance with the Contributions Schedule set out in Annex D to this Transitional MoU to be developed by the Cellular Pathology Steering Group within three months of the date of this Transitional MoU.

  - Both Health Boards shall remain liable for any losses or liabilities incurred due to their own or their employee's actions and neither Health Board intends that the other Health Board shall be liable for any loss it suffers as a result of this Transitional MoU.

Ownership of Assets

  - All assets (including intellectual property rights) acquired by SBUHB in connection with the ODN shall belong to SBUHB but be held upon trust for the ODN.

  - SBUHB shall, to the extent it is legally entitled to do so, transfer ownership and any other rights in such assets to such party or body as a commissioner shall require and within such timescales as are reasonably required.

  - In the event that any income is derived from such assets or from their disposal, such revenues shall be regarded as part of the ODN income and accounted for accordingly.

Procurement

16.1	When existing contracts, which have been entered into separately by each Health Board, have expired, it is envisaged that new contracts will be entered into for the benefit of the ODN by adopting a joint approach, for example, SBUHB will act as the lead procurer for goods, services and works that are required by the Health Boards.

16.2	Existing (separate) contracts entered into by the Health Boards will remain in force until their expiry date (unless such contracts may be lawfully terminated, for example, because of contractor default, insolvency etc. or where the Health Boards have a right to terminate at will on written notice). Upon expiry, the approach in clause 16.1 above will be adopted.

16.3	Where contract terms permit and subject to the public procurement rules in force at the time, in order to be in a position to re-procure jointly, a Health Board may extend (or not, as the case may be) any existing contract to align its expiry date with a corresponding contract entered into by the other Health Board.

Host Health Board - Duty of Care

  - SBUHB shall be responsible for ensuring that all reasonable skill, care and diligence are exercised in carrying out those services which it is required to perform under the ODN as the host Health Board, properly and efficiently in accordance with this Transitional MoU and its overall responsibilities under the National Health Service (Wales) Act 2006 and all other appropriate legislation.

  - SBUHB shall keep the ODN informed of any reasonably foreseeable or actual changes in circumstances which are likely to affect its ability to comply with the terms of this Transitional MoU as the Host Health Board.

Management of Concerns

- 18.1	Where a matter is received into the ODN and is regarded as an individual concern (as defined in The National Health Service (Concerns, Complaints and Redress Arrangements) (Wales) Regulations 2011 (“Redress Regulations”)), SBUHB will only be responsible for the management of those concerns where qualifying liability (as defined in the Redress Regulations) in tort is established, which relates to its geographical area of responsibility and arises from its own resident population. In such circumstances, the Chief Executive of SBUHB will be responsible for investigating and responding to the concern in accordance with the Redress Regulations. For the avoidance of doubt, complaints or matters which are not Concerns or Complaints (as defined in the Regress Regulations) but which otherwise relate to the performance of this Transitional MoU, are dealt with under clauses 18.5 and 18.6 of this Transitional MoU.

- 18.2 	Individual Concerns or Complaints received into the ODN and relating to patients resident outside SBUHB’s geographical area of responsibility will be referred to the Chief Executive of the health board in the appropriate geographical area no later than two (2) Working Days of becoming aware of that Concern or Complaint.

- 18.3	Where a Concern or Complaint involves the exercise of functions by both SBUHB and HDUHB, the Health Boards shall co-operate for the purposes of co-ordinating the handling and consideration of the Concern or Complaint in accordance with the Redress Regulations and shall ensure that the person who notified the Concern or Complaint receives a co-ordinated response to the Concern or Complaint that he or she has notified. This duty to cooperate includes a duty for each Health Board to:

    - agree which Health Board shall take the lead in:

          - co-ordinating the handling and consideration of the Concern or Complaint; and

          - communicating with the person who notified the Concern or Complaint;

    - provide information relevant to the handling and consideration of the Concern or Complaint which is reasonably requested by the other Health Board; and

    - to ensure that it is represented at any meeting reasonably required in connection with the handling and consideration of the Concern or Complaint.

- 18.4	In respect of the performance of this Transitional MoU, both Health Boards shall and shall procure that their staff shall be required to comply with the duty of candour introduced pursuant to the Health and Social Care (Quality and Engagement) (Wales) Act 2020 and any Guidance issued in relation to the implementation of this duty and the 2020 Act, where an outcome triggers the duty of candour procedure.

- 18.5	Where a matter is considered to be a review of funding decisions it will be dealt with in accordance with the Review Process set out in the All Wales Policy for Making Decisions on Individual Patient Funding Requests.

- 18.6	If either Health Board receives any formal inquiry, complaint, claim or threat of action (which is not a Concern or Complaint (as defined in the Regress Regulations) from a third party (including, but not limited to, claims made by a supplier or requests for information made under the Freedom of Information Act 2000) or under the Data Protection Legislation in relation to the Project (“Receiving Health Board”), such inquiry, complaint, claim or threat of action shall be dealt with by that Receiving Health Board, having regard to its internal policies and procedures and all relevant law. Where either Health Board receives a formal inquiry, complaint, claim or threat of action from a third party which requires information from the other Health Board prior to responding, the other Health Board shall assist and cooperate in a timely manner to enable the requesting Health Board to comply with its information and other disclosure obligations. If the Health Board providing the information to assist the other Health Board considers that the information is confidential or otherwise not in its interests or in the public interest to disclose, it shall have the opportunity to make representations to the requesting Health Board and both Health Boards shall attempt to reach agreement as to what information is disclosable. The requesting Health Board shall have absolute discretion as to what information, provided by the other Health Board, may be disclosed when responding to a formal inquiry, complaint, claim or threat of action from a third party. In all cases, the Receiving Health Board shall report the matter to the Pathology ODN Operational Group.

Audit

  - SBUHB will provide an effective independent internal audit function as a key source of its internal assurance arrangements. This will be in accordance with NHS Wales Internal Auditing Standards and any other requirements determined by the Welsh Government.

  - SBUHB will ensure that relevant external audit arrangements are in place which give due regard to the functions of the ODN.

Effect of ODN on SBUHB’s Core Functions

  - In the event of SBUHB’s determining (acting reasonably) that the performance by SBUHB of its obligations under this Transitional MoU is having a detrimental effect on SBUHB’s ability to fulfil its core functions, SBUHB may instruct the ODN Senior Responsible Officer and SBUHB’s Chief Executive to review the operation of this Transitional MoU.

  - In carrying out a review of this Transitional MoU further to clause 20.1 above, the ODN Senior Responsible Officer and SBUHB’s Chief Executive shall consider the source and manner of any detriment identified by SBUHB’s Board further to clause 20.1 and shall put forward such amendments and variations to this Transitional MoU and the associated governance arrangements between the ODN and SBUHB as they may consider appropriate.

  - SBUHB’s Board shall consider the recommendations made further to clause 20.2 and may recommend to the ODN Senior Responsible Officer and the Chief Executive of SBUHB that this Transitional MoU and the associated governance arrangements are amended accordingly.

Status of MoU

  - This Transitional MoU is not intended to be legally binding, and no legal obligations or legal rights shall arise between the Health Boards from this Transitional MoU. The Health Boards enter into the Transitional MoU intending to honour all their obligations.

  - Nothing in this Transitional MoU is intended to, or shall be deemed to, establish any partnership or joint venture between the Health Board, constitute either Health Board as the agent of the other Health Board, nor authorise either of the Health Board to make or enter into any commitments for or on behalf of the other Health Board.

| Signed for and on behalf of SWANSEA BAY UNIVERSITY LOCAL HEALTH BOARD |  |
| --- | --- |
| Signature: | ............................................ |
| Name: | ............................................ |
| Position: | ............................................ |
| Date: | ............................................ |
| Signed for and on behalf of HYWEL DDA UNIVERSITY LOCAL HEALTH BOARD |  |
| Signature: | ............................................ |
| Name: | ............................................ |
| Position: | ............................................ |
| Date: | ............................................ |

- ANNEX A - The Project

Project overview

The South-West Wales Pathology Programme has two key components:

- The development of a single Regional Pathology service via an Operational Delivery Network (ODN) approach, with Swansea Bay as the host organisation.

- The development of a Hub Laboratory Centre of Excellence to provide fit for purpose modern laboratory service for the region and local laboratory refurbishments via Welsh Government Capital investment processes. Three sites are being considered and will be the subject of an Options Appraisal paper.

This MOU focusses on the development of the Operational Delivery Network (ODN). The Business Case for development of the Hub building and local laboratory refurbishments has separate governance led by SBUHB.

The development of the ODN aims to provide stability and sustainability to pathology service across the region. Developing critical mass of service delivery, joint training and quality management systems, single digital information systems and collective recruitment for hard to recruit to roles will all contribute to decreasing risk with current service delivery methods. The balance of risk between the organisations does need to be considered as part of the establishment of the network and arrangements with regard for example capital investment in retained local laboratory services outside of any investment secured by the capital process will need to be considered i.e. significant backlog maintenance to existing buildings.

One of the key aims of the network is to ensure consistency of service delivery to the regional population regardless of their location. This will be achieved through the implementation of digital pathology solutions where possible, the development of a robust regional transport and logistics network and the timely analysis and reporting of investigations. Developing consistent service models and equipment and processes in all laboratories will also shore up business continuity through the movement of samples in the event of any laboratory down time in any site.

Background

To progress the transformation plan for Pathology services in South-West Wales, the Health Boards agreed the need to create a Regional Pathology service model. This approach, new for NHS Wales but not across the United Kingdom would enable joint recruitment, collaborative development of service plans, standardisation of approach, equipment and facilities and the benefits of consolidation. A number of possible options of how a regional management model could operate that would be underpinned by a strong governance framework and an agreed set of principles were considered.

A Joint Executive meeting between SBUHB and HDUHB was held on 24th November 2021; these points were discussed and a subsequent visioning workshop was held on 29th November 2021, chaired by the then CEO of Swansea Bay UHB.

A Regional Pathology Task and Finish (T&F) Group convened in 2022, chaired by the COO from HDUHB, and supported by the Director of Therapies at SBUHB as SRO for the ARCH Regional Pathology Transformation Programme. The group considered their options for the management model and undertook an appraisal and sought advice from NHS Wales Legal and Risk services. The detail of the decision-making process is covered in the November 2022 paper considered by both Health Boards (see Appendix). The conclusion was the development of an Operational Delivery Network (ODN) for Pathology services with an aim to be operational by Q4 2022/23,

Following the establishment of the ARCH Pathology team in early 2023/24 the task of delivering the ODN model moved forward at pace. The terms of reference of the T&F group were revised to form an ODN Transition Board and subgroups established to consider implications for Finance and Commissioning, Workforce and Digital services. In addition, Legal & Risk advice has been retained to work with both HB governance teams on the Memorandum of Understanding and legal agreements required to deliver the network.

To date the following developments have been agreed:

- Development and agreement of a Mortuary MOU for the Region. This has facilitated closer working between the mortuaries and the appointment of a regional mortuary team, joint training processes and rotations.

- Development and agreement of joint regional management structure and job descriptions and person specifications for those roles

- Baseline assessment of performance, resources, quality/accreditation, compliance and workforce for the region

- Review of existing logistics and transport arrangements

- Continued development of regional Digital Cellular Pathology pilot in the region

- Staff engagement in all laboratories in the region to develop the identity and culture of the regional service and understand the current strengths and challenges on each individual site.

- Appointment of a single Designated Individual (DI) for the regional mortuary service following the retirement of the current HDUHB post holder. This has been achieved by appointment of the same individual to take responsibility for both Health Board licenses, although licenses still remain separate.

Current work is focussing on:

- Development of a regional ‘compliance’ team structure to combine functions in both organisations in pathology, IT, Quality, Health and Safety and Training

- LIMS 2.0 roll out regionally by February 2025. To ensure that the region has a consistent pathology digital system with replicable supporting processes in both health boards

- Consideration of the regional recruitment and training of non-consultant medical staff to histopathology

- Development of a Transitional Pathology Regional MOU for consideration by both Boards to support the development of the regional management team and integrated service change

- Development of the Service Specification and commissioning arrangements for the Pathology service for consideration by both organisations.

The proposal therefore is to continue to regionalise the service via the Transition Board but also move into the territory over the next 12 months of harmonising workforce arrangements. Once the commencement date of the Network is agreed by both Boards the process of appointing into the senior leadership team and subsequent TUPE transfer of staff into the new service model will commence.

Transitional MOU

This transitional MOU has been developed by a task and finish group established under the leadership of the then ARCH Programme Director with input from NHS Wales Shared Services – Legal and Risk, and SBU and HDUHB Governance Teams. The group has met monthly to develop the attached draft MOU for the transition period.

The Transitional MOU takes the same form as the proposed final MOU but with the following differences:

- Transitional MOU covers the period to 31 March 2028, or to the point at which the ODN is delivered, whichever is first. It has no permanence as the organisations will need to agree to the formal MOU once developed for the recurrent networked service

- The ToR for the ODN will be developed during the transition period and therefore this annex and others are under development through the transition period

The Transitional MOU seeks to support:

- Development of the Service Specification for the Pathology ODN

- Development of Commissioning arrangements including quality management and assurance

- Support to start implementing the leadership team for the regional service

- Information and data sharing of staff information and clinical service information

- ANNEX B - Information Sharing Protocol

The Health Board Information Governance Teams will work with the RJC PMO and Cellular Pathology ODN Steering Group to develop and approve an Information Sharing protocol between the organisations.

This is already in place for the separate Mortuary MOU and will form the basis of the overall Pathology Protocol.

A DPIA has been undertaken to assist in the development of the protocol.

- Annex C - Terms of Reference

See Appendix 1

- ODN Steering Group ToR	 		Page 1-4

- Regional Joint Committee ToR		Page 5-12

- Regional Clinical Services Group		Page 13-18

- ANNEX D – Contributions

The Finance and Commissioning Sub-Group is tasked with developing the Service Specification and Commissioning arrangements for the ODN. The ODN Steering Group will have to approve these in transition prior to any decision to fully establish the ODN. This will confirm the resource responsibilities and risk sharing on commencement of the ODN and assurance and monitoring arrangements.