| Meeting Date | 27 March 2025 |  | Agenda Item |  |  | 1.5 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Risk Management Report |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance Len Cozens, Head of Compliance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to provide the Board with an update on progress to re set the Board Assurance Framework (BAF) following the Board, in November, agreeing the Risk Management Strategy. The report also presents the Health Board Risk Register (HBRR) for review and assurance. |  |  |  |  |  |
| Key Issues | - Progress is being made in developing the Strategic Risk Register. Meetings with Executive Directors to develop the register have been held and conclude early April and the Strategic Risk Register will then be reported to the May Board. - The Board last received the current Health Board Risk Register (HBRR) at its November 2024 meeting. - This report presents the February 2025 HBRR. - As at March 2025, the HBRR contains 30 risks, of which 20 have risk scores at, or above, the Board’s risk appetite threshold. Four of these have risk scores of 25. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - RECEIVE the Health Board Risk Register (HBRR) and update on progress with the development of the strategic risk register. - CONSIDER whether the Board needs further assurance over risks and associated actions & controls – In particular over those risks exceeding the Board’s stated appetite levels. |  |  |  |  |  |

BOARD ASSURANCE REPORT

- Introduction

The purpose of this report is to provide the Board with an update on progress to re set the Board Assurance Framework (BAF) following the Board, in November, agreeing the Risk Management Strategy.  The report also presents the Health Board Risk Register (HBRR) for review and assurance.

- Review of Board Assurance Arrangements

The Board agreed the Risk Strategy in its November 2024 meeting, supporting the ‘review & reset’ actions of the framework which underpinned the ways in which the Board gained assurance on delivery of its strategic objectives and its risk management arrangements. Discussions at the Risk Management Group, Risk Scrutiny Panel and with Management Board members, resulted in the development of a revised Board Assurance Framework (a description of the governance structures and processes through which the Board gains assurance on delivery of its objectives) and a Strategic Risk Register template, to support the recording & monitoring of the principal risks to the achievement of its strategic objectives.

  - Strategic Risk Register

- The Board considered its strategic risks at a development session in December 2024;

- The Audit Committee and Board subsequently received a Strategic Risk Register template, with Executive Directors to progressing the population of the template;

- The Executive Directors deliberations were supported by a review of arrangements in place at other health organisations within NHS Wales, NHS England and NHS Scotland, including through the identification of risk register entries made by organisations with similar objectives and risks;

- Relevant risks already captured in the current SBUHB Health Board Risk Register were also provided for comparison, as was information on common strategic risk themes, and sample descriptions, to stimulate thought;

- The Director of Corporate Governance presented this at a meeting of the Executive Team for initial discussion;

- Following this meeting, the Head of Compliance and Assistant Head of Risk & Assurance arranged to meet individually with Executive Directors (or their deputies/senior leads) to discuss risks within their portfolios and more widely, and to facilitate completion;

- Executive Directors also received additional information sources for consideration, including thematic risk information about operational service risks.

This work is ongoing, with discussions to date including with:

- Acting Deputy Executive Director of Nursing & Patient Experience

- Associate Director of Population Health

- Interim Director of Workforce & Organisational Development

- Assistant Director of Insight, Engagement & Fundraising

- Executive Medical Director

Meetings in March and the first weeks of April are scheduled with:

- Deputy Director of Finance and Director of Capital Planning & Estates

- Director of Digital

- Director of Allied Health Professions and Health Sciences

- Chief Operating Officer

- Director of Planning & Partnership

2.2 Risk Management Reporting Arrangements

Following a review of risk reporting arrangements at corporate level, the Management board approved the Terms of Reference for the Risk Management Group.  This Group now encompasses the role and function of both the previous Risk Management Group and Risk Scrutiny Panel Group; chaired by the Deputy CEO/Executive Medical Director.  It will meet monthly and report into the Management Board.

Every six months, the Group will complete gateway reviews of Service Group operational risks. It will also oversee the reporting and escalation of risks to the Corporate Risk Register and reporting to the Committees of the Board and the Board.

The first meeting of the Group is scheduled for April 2025.

- Health Board Risk Register (HBRR) Summary Position

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing SBUHB and the actions being taken to mitigate them.

Each Health Board risk has an assigned Executive Director, responsible for ensuring that there are mechanisms in place to identify, manage and alert the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the full Board.

For the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’; risks assessed at or above a risk level of 20 will be subject to oversight at Board Committee level as a minimum, on a quarterly basis. However, for compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high-quality care, or the health and safety of the staff and public, there will be an ‘open’ appetite, indicating lower threshold, with risks scoring 16 or above subject to committee level oversight.

As at March 2025, the HBRR includes 30 risks, of which 20 have risk scores at, or above, the Board’s risk appetite threshold. Four of these had risk scores of 25.

The HBRR is as attached at Appendix 1, with the most recent updates highlighted in red font. In addition to risks presented there, the following sensitive risks are subject to oversight in private session of Board and/or Committees:

- HBR 60	Cyber Security

- HBR 101	Industrial Action

The profile of risk scores within the HBRR is as follows:

| Risk Analysis | Number of Risks |  |
| --- | --- | --- |
|  | Oct 2024 HBRR | Feb 2025 HBRR |
| Risk Score of 25 | 3 | 4 |
| Risk Score of 20 | 14 | 14 |
| Risk Score of 16 | 9 | 4 |
| Risk Score 9-15 | 7 | 8 |
| Risk Score of 5-8 | 0 | 0 |
| Risk Score of 1-4 | 0 | 0 |
| Total | 33 | 30 |

3.1 	Risk Changes

3.1.1	Key movements are:

| New risks | Nil |
| --- | --- |
| Risks with increased scores | 4 |
| Risks with reduced scores | 2 |
| Risks de-escalated / closed | 3 |

Details are set out in the following sections.

3.1.2 The risk(s) with increased scores is/are:

| Risk Ref | Increased Risks | Lead Exec Director | Previous Risk Score | Current Risk Score |
| --- | --- | --- | --- | --- |
| 43 | Deprivation of Liberty Safeguards (DoLS) Due to a limited resources within the Mental Capacity Act (MCA) /DoLS service (lack of Best Interest Assessor resource and signatory approval) there is a risk of failure to complete and authorise the assessments associated with Deprivation of Liberty within the legally required timescales, exposing the health board to potential legal challenge and reputational damage. Notes: Breaches reported for Q2 were 17. • An increase in DoLS referrals following wider HB staff awareness of MCA/DoLS following implementation of Level 3 training • Additional support to Managing Authorities providing wider MCA/DoLS awareness • Insufficient signatory resource Breaches reported for Q3 were 58. • There was a 35% increase in referrals. • 1 Best Interest Assessor (BIA) on long term leave • Staff requests for bespoke mental capacity assessment training impacting on BIA and senior staff capacity to undertake core DoLS assessments. This risk has been considered at the Mental Health Legislation Committee. | Executive Director of Nursing | 16 | 20 |
| 64 | Health & Safety Infrastructure Insufficient resource and capacity of the health, safety and fire function within SBUHB to maintain legal and regulatory compliance for the workforce and for the sites across SBUHB. Notes: Due to retirement resources in the team has reduced and the risk level increased to 20. With the senior structure portfolio changes (the merger of the Assistant Director of Health & Safety and Capital Planning roles), an updated structural plan for health & safety (H&S) was submitted as part of the senior structure review, with the adoption of a phased approach to implement. This risk will be continually reviewed and adjusted as the phased approach on resources is implemented. It is envisaged that 4 posts will be advertised in the new financial year and with successful recruitment these could be in place by Q1/Q2 2025/26 financial year, with further reviews taking place for the phased implementation. | Director of Finance & Performance | 16 | 20 |
| 66 | Access to Systemic Anti-Cancer Therapy (SACT) (Cancer Services) The demand & complexity of planned treatment regime for cancer patients requiring chemotherapy currently exceed the available chair capacity, risking unacceptable delays in access to SACT treatment in Chemotherapy Day Unit with impact on targets and patient outcomes. Notes: Due to staff sickness across the Multi-Disciplinary Team, and the demands for SACT outstripping capacity the risk has increased to 25. There are continuing workforce challenges and patient waiting times and the number of patients breaching SACT targets have increased. A demand and capacity options paper has been shared with the Service Group Senior Leadership Team and agreed in principle. A paper is going to Executive Board in March 2025 for approval. | Executive Medical Director | 20 | 25 |
| 90 | Non-compliance with UK-GDPR Article 15 regarding Subject Access Requests (SARs), along with other health records requests for disclosure of personal data If the Health Board is non-compliant with the UK-GDPR, then there is a risk of Information Commissioner’s Office (ICO) enforcement action being taken against SBUHB, reputational damage and the potential for claims (Risk description extract – see HBRR for fuller description). Notes: Contributory causes include: sustained increase in numbers & complexity of subject access requests; limited resources corporately and clinically, including those required for effective redaction & checking; information held across multiple systems and media. A benchmarking exercise has been completed to compare the risk in SBU with other Health Boards and a paper is going to the Information Governance & Cyber Assurance Group for review in April 2025. An action plan is to be developed following that discussion. | Director of Digital | 16 | 20 |

3.1.3 The risk(s) with reduced scores is/are:

| Risk Ref | Reduced Risks | Lead Exec Director | Previous Risk Score | Current Risk Score |
| --- | --- | --- | --- | --- |
| 93 | Reduced Capital Funds Reduced discretionary capital funds and reduced National NHS funds requiring a restricted Capital Plan for 2024/25. | Director of Finance & Performance | 20 | 12 |
| 101 | Industrial Action (Healthcare Support Workers) Detail presented in Private Session | Director of Workforce & OD | 20 | 15 |

3.1.4 The risk(s) closed within the HBRR is/are:

| Risk Ref | Closed & De-escalated Risks | Lead Exec Director | Commentary |
| --- | --- | --- | --- |
| 63 | Screening for Fetal Growth Assessment in line with Gap-Grow There is not enough Ultrasound scanning & clinic capacity within Swansea Bay UHB to offer all women serial ultrasound scan screening in the third trimester in line with the UK perinatal Institute Growth Assessment Programme (GAP). Welsh Government mandate fetal growth screening in line with the GAP programme, which states serial ultrasound growth scans should be performed at three weekly intervals. There is significant evidence of the increased risk for stillbirth or neonatal mortality/morbidity (hypoxic ischaemic encephalopathy) HIE, where a fetus is growth restricted (Intrauterine Growth Restriction - IUGR) and/or small for gestational age fetus (SGA). | Executive Director of Nursing & Patient Experience | This risk had achieved its target following: - Introduction of Midwifery sonography service in Singleton. - Implementation of Midwifery sonography service in NPT. - All women with low PAPP-A receive serial scans. - Serial scans performed 3-weekly in line with GAP Grow. - GAP grow training compliance >95% for Midwives and Obstetricians. Consequently, the risk was agreed for de-escalation from the HBRR by its Executive Director in February 2025, for ongoing management within the service operational risk register. |
| 102 | Inability to maintain Birthrate Plus® compliant rosters There is a risk non-compliance with roster templates due to increased acuity, unplanned staff absence and vacancies. The potential impact of this may be reduced staffing levels against the agreed Birthrate Plus® staffing template resulting in poor patient outcomes and experience, and potential suspension of services. | Executive Director of Nursing & Patient Experience | Score was reduced in light of: - Birthrate Plus® compliance and establishment having no vacancies. - Minimal turnover in the department. - Bank and agency usage only for short term sickness. Consequently, this risk was reduced and approved by its Executive Director for de-escalation from the HBRR in February 2025, for management within the service operational risk register. |
| 103 | High Quality Choices in Place of Birth There is a risk of not being able to provide high quality choices in place of birth (via appropriately staffed and resourced community midwifery teams, the freestanding midwifery unit at Neath Port Talbot Hospital, the alongside midwifery unit and obstetric unit at Singleton Hospital). The potential impact of this is poor patient experience and birth outcomes, poor staff morale and increased attrition of community midwives, increased acuity within obstetric services at Singleton Hospital, and the reduction of services could impact on organisational reputation. | Executive Director of Nursing & Patient Experience | This risk was reduced in light of: - Birth place options having been in place for a period of 3-4 months respectively for NPT Birth Centre and Home Birth options. - This has been a sustained service without interruption or impact on staffing, acuity and safety of the Obstetric Unit in Singleton. - The Escalation Policy business continuity options have been used in line with guidance intermittently and not for sustained periods. - The on-boarding of the Newly Qualified Midwives, no longer supernumerary since December 2024, has further supported staffing and acuity on the Singleton Hospital site. Consequently, the risk was reduced and approved by the Executive Director of Nursing for de-escalation from the HBRR in February 2025, for management within the service operational risk register. |

3.2 Risks Above the Board Risk Appetite

There are 20 risks that are assessed as reaching the Board’s risk appetite threshold:

| Risk Ref | Risk Title & Description | Current Score | Executive Lead & Nominated Board Committee |
| --- | --- | --- | --- |
| 1 | Access to Unscheduled Care | 25 | - Chief Operating Officer - Performance & Finance Committee |
| 3 | Workforce Recruitment (Medical & Dental) | 20 | - Director of Workforce & OD - Workforce & OD Committee |
| 4 | Infection Prevention & Control | 20 | - Executive Director of Nursing & Patient Experience - Quality & Safety Committee |
| 16 | Access to Planned Care | 20 | - Chief Operating Officer - Performance & Finance Committee |
| 43 | Deprivation of Liberty Safeguards | 20 | - Executive Director of Nursing & Patient Experience - Quality & Safety Committee |
| 50 | Access to Cancer Services | 25 | - Chief Operating Officer - Performance & Finance Committee |
| 52 | Impact Assessment Requirements | 16 | - Director of Insight, Communication & Engagement - Performance & Finance Committee |
| 60 | Cyber Security | 20 | - Director of Digital - Digital, Data, Research and Innovation Committee |
| 61 | Paediatric Dental GA Service (Parkway) | 16 | - Chief Operating Officer - Quality & Safety Committee |
| 64 | Health & Safety Infrastructure | 20 | - Director of Finance & Performance - Quality & Safety Committee |
| 66 | Access to SACT (Cancer Services) | 25 | - Executive Medical Director - Quality & Safety Committee |
| 69 | Safeguarding: Adolescents on Adult Mental Health Wards | 20 | - Chief Operating Officer - Quality & Safety Committee |
| 80 | Inability to Transfer Patients | 20 | - Chief Operating Officer - Quality & Safety Committee |
| 85 | Non-Compliance with ALN Act | 20 | - Director of Allied Health Professionals & Health Science - Quality & Safety Committee |
| 89 | Healthcare Nursing Staff Level (HMPS) | 20 | - Executive Director of Nursing & Patient Experience - Quality & Safety Committee |
| 90 | Non-compliance with UK-GDPR Article 15 regarding Subject Access Requests | 20 | - Director of Digital - Digital, Data, Research and Innovation Committee |
| 92 | Finance – Forecast Deficit | 25 | - Director of Finance & Performance - Performance & Finance Committee |
| 96 | Develop an Approvable IMTP (statutory compliance) | 20 | - Director of Strategy - Performance & Finance Committee |
| 98 | Overall condition/compliance and suitability of Health Board Estate | 20 | - Director of Finance & Performance - Performance & Finance Committee |
| 99 | Failure to implement the population health strategy approaches at the required scale | 20 | - Director of Public Health - Population Health & Partnerships Committee |

The full HBRR at Appendix 1 details key controls in place to manage these risks and actions being taken to address them further. The Board’s Committees receive regular reports on their allocated risks highlighting key steps taken to manage risk to an acceptable level. Reports also include updates on those risks below appetite, in recognition of the Board’s aspiration to reduce risks further.

- FINANCIAL IMPLICATIONS

This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement/treatment of risks entered on the HBRR. Where this is the case, they are highlighted within individual risk register entries or dedicated Board/Committee papers for information.

- RECOMMENDATIONS

Members are asked to:

- RECEIVE the Health Board Risk Register (HBRR) and update on progress with the development of the strategic risk register.

- CONSIDER whether the Board needs further assurance on risks and associated actions & controls – In particular on those risks exceeding the Board’s stated appetite levels.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case, they are highlighted within individual risk register entries for information. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | This report updates on risk matters received in November 2024. |  |
| Appendices |  | Appendix 1 - Health Board Risk Register (HBRR) Risks |  |