| Meeting Date | 27th May 2025 |  | Agenda Item |  |  |
| --- | --- | --- | --- | --- | --- |
| Report Title | Welsh Government Escalation Update |  |  |  |  |
| Report Author | Meghann Protheroe, Head of Health Board Performance |  |  |  |  |
| Report Sponsor | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention Darren Griffiths, Director of Finance and Performance |  |  |  |  |
| Presented by | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |
| Purpose of the Report | To provide the Board with a summary of the performance and outcomes issues for the services escalated as part of Welsh Governments Oversight and Escalation Framework. This report is received and considered by the Performance and Finance Committee. |  |  |  |  |
| Key Issues | Following the Welsh Government’s tripartite meeting in February 2025, the Health Board was de-escalated for the following areas previously at Targeted Intervention level 4 for Performance and Outcomes: - Child and Adolescent Mental Health Services will be de-escalated to level 3 (enhanced monitoring) and - Planned care will be de-escalated to level 3 (enhanced monitoring). All other areas of escalation remain unchanged and the summary is as follows: - Level 4 for finance, strategy and planning. - Level 4 for performance and outcomes relating to cancer, urgent and emergency care and quality of care related to HCAIs. - Level 3 for maternity and neonatal services. - Level 3 for performance and outcomes relating to planned care and CAMHS. - Level 2 for Mental Health and Learning Disabilities This report provides an update against performance measures following the previous oversight and assurance of the programme. |  |  |  |  |
| Specific Action Required (Please choose one only) | Information | Discussion | Assurance | Approval |  |
|  | ☒ | ☐ | ☒ | ☐ |  |
| Recommendations | Members are asked to: - CONSIDER the monthly update in respect of performance against escalation measures and de-escalation criteria. |  |  |  |  |

WELSH GOVERNMENT ESCALATION UPDATE

- INTRODUCTION

The previous reports have described the actions and longer-term proposals being developed and implemented in response to services who were escalated to targeted intervention status. The report provided an update on the operational programme to manage the delivery of improved performance and outcomes for services under targeted intervention.

This report is received and considered by the Performance and Finance Committee.

The current report will provide an update against all levels of Oversight and Escalation of services within Swansea Bay University Health Board and will include;

Performance against Areas of concern (Level 2)

- Adult Mental Health and Learning Disabilities

Performance against Areas of Enhanced Monitoring (Level 3)

- Planned Care

- Maternity and Neonatal Services

- Child and Adolescent Mental Health

Performance against Areas of Targeted Intervention (Level 4)

- Cancer

- Urgent & Emergency Care

- Quality of Care related to Healthcare Acquired Infections

- Finance

- Strategy and Planning

- BACKGROUND

Following Welsh Government’s tripartite meeting in December 2023, the Health Board was notified of an escalation of performance monitoring for performance and outcomes from enhanced monitoring to Targeted Intervention.  The services listed in the introduction of this report were specifically included in the escalation.

On 12th April 2024, the Health Board had its inception meeting with Welsh Government colleagues and on 24th April 2024 the first quarterly meeting was held with the Chief Executive of NHS Wales.  Quarterly meetings subsequently alternate with formal Joint Executive Team (JET) meetings.  Monthly review meetings are with WG officers focussing on key updates against the escalated areas.  The Chief Operating Officer is the Senior Responsible Officer (SRO) for targeted invention and each work programme is supported by senior management and clinical leads. Summarised updates against the escalation levels will be provided throughout this report.

Following the Tripartite meeting in February 2025, the levels of escalation have been revised and updated as follows: -

- Child and Adolescent Mental Health Services de-escalated from level 4 (targeted intervention) to level 3 (enhanced monitoring).

- Planned care de-escalated from level 4 (targeted intervention) to level 3 (enhanced monitoring).

Updated de-escalation criteria was provided by Welsh Government in April 2025 which provided updated targets for several areas within Level 3 Enhanced Monitoring. The updated de-escalation criteria can be seen throughout the paper.

- PERFORMANCE AGAINST THE AREAS OF CONCERN

Mental Health and Learning Disabilities

Welsh Government has identified Mental Health and Learning Disabilities (MH&LD) as an area of concern, with regards to the oversight and escalation. Assurance has been sought with regards to the key areas of concern within the Service Group and are outlined below: -

- The Service Group continues to work with the NHS Executive Mental Health leads as part of the Level 2 support. The work is ongoing and is now at the stage of updating the review following the various site visits and reviewing the shared data and documentation provided.

- The Health Board has commenced work in advance of the receipt of the report and is setting up a Transformation Programme. This has been informed by a review of the service by an external advisor. Findings were presented to an in-committee meeting of the Board in February 2025 and the recommendations were approved. There were some recommendations which were considered urgent by the Board and these have been completed or are in progress. The Transformation Programme will be led by a Programme Board with supporting reporting structures including workforce, IT/digital, service redesign, Quality and Safety and estates. The recommendations of the review by NHS Executive MH and LD leads will form part of the work programme. Elements of the programme (such as estates) have already commenced. It is anticipated that all other elements will begin in June 2025.  A Programme Initiation Document has been developed which describes the overall Programme in more detail with the deliverables from each of the workstreams and the expected benefits of the Programme. The Board will receive an update in the June Board.

- PERFORMANCE AGAINST THE ENHANCED MONITORING SERVICES

4.1 Planned Care

| Criteria to Achieve | Current Performance (April 25) |
| --- | --- |
| - 100% of open outpatient pathways to be waiting less than 52 weeks and maintained for 3 months. | - 100% |
| - Continuous improvement towards 75% of all open outpatient pathways waiting less than 26 weeks. (NEW Measure) | - 56.94% |
| - 100% of open pathways to be waiting less than 104 weeks and maintained for 3 months. | - 100% |
| - Continuous improvement towards 80% of all open pathways waiting less than 36 weeks. (NEW Measure) | - 73.03% |
| - 12% reduction in the number of patients delayed by 100% for their follow up appointment in three consecutive months and maintained for 3 months (Based on the November 2024 baseline). | - 4.23% increase against baseline |
| - 68% R1 ophthalmology patient pathways to be waiting within or no longer than 25% of their target date for an outpatient appointment and maintained for 3 months. | - 75.19% - meets de-escalation criteria |
| - 85% of patients waiting for a diagnostic test to be waiting less than 8 weeks and maintained for 3 months. | - 82.24% |
| - 85% of patients waiting for a diagnostic endoscopy to be waiting less than 8 weeks and maintained for 3 months. | - 38.03% |
| - 85% of patients waiting for a NOUS and non-cardiac MRI to be waiting less than 8 weeks and maintained for 3 months. | - 99.88% |
| - 90% of patients waiting for therapies to be waiting less than 14 weeks and maintained for 3 months. | - 99.94% |

Actions being taken to improve include:

- Robust monitoring via live dashboards

- Weekly monitoring meetings chaired by Service Group Directors

- Bi-weekly oversight meeting chaired by the Chief Operating Officer

- Specific support commissioned for Gynaecology improvement plans

- Regional orthopaedics programme ongoing to provide capacity for patients not suitable for surgery at NPTH to reduce demand for Morriston Hospital services.

4.2 Maternity and Neonatal Services

On 12th December 2023, the maternity and neonatal services within Swansea Bay University Health Board were escalated to level 3 (enhanced monitoring) following an assessment of issues and concerns

related to staffing levels, quality and safety issues, the issues within the HIW unannounced inspection at Singleton as set out in the report published on the 15th December 2023.

In order to appropriately scrutinise and seek assurance of the work being undertaken in Maternity and Neonatal services, a Gold command structure was established. The main areas of focus for the group are enhanced monitoring, inspection action plans, open incidents, national reports and horizon scanning.

Detailed progress against these areas have been outlined in the Maternity and Neonatal update report.

4.3 CAMHS

| Criteria to Achieve | Current Performance |
| --- | --- |
| - 80% of LPMHSS mental health assessments undertaken within 28 days from the date of receipt of referral. | - January – 42% - February – 74% - March – 75% |
| - 70% of therapeutic interventions started within 28 days following an assessment by LPMHSS. | - January – 100% - February – 100% - March – 100% |
| - 85% of HB residents in receipt of secondary mental health services who have a valid care and treatment plan. | - February – 98% - March – 98% - April – 98% |

Actions being taken to improve include:

- Substantive recruitment is ongoing for three permanent band six post to improve the workforce for this part of the service

- PERFORMANCE AGAINST THE TARGETED INTERVENTION SERVICES

5.1 Cancer

| Criteria to Achieve | Current Performance |
| --- | --- |
| - 60% performance maintained for 3 months against the Single Cancer Pathway (SCP) target. | - January – 52% - February – 56% - March – 62% |

Actions being taken to improve include:

- Continued focus on front end of pathway for all specialties

- Continued focus on cellular pathology, HCSE team working with the service and workforce gaps going through vacancy control process.

- Weekly performance reviews with all tumour site leads, chaired by the Deputy Chief Operating Officer and/or Cancer Performance and Information Manager.

- Identify additional surgical (Upper GI in particular), robotic (urology) and chemotherapy capacity; business case for an additional 2 chairs agreed.

- Further actions/improvement in Skin, particularly to mitigate increased seasonal demand; LGI, to decision to treat and pre-assessment; Urology diagnostics and increasing robotic capacity; and Lung.  Progress against actions to be monitored through CPIG

5.2 Urgent and Emergency Care

| Criteria to Achieve | Current Performance |
| --- | --- |
| - A continuous reduction of ambulance handovers over an hour of at least 11% in three consecutive months and maintained for 3 months (Based on quarter 2 and 3 2023 baseline). | - February – 554 - March – 555 - April - 629 |
| - Continuous improvement towards no more than 7% of patients waiting over 12 hours at each individual site and across the health board. | - February – 12.4% - March – 11.3% - April – 12.87% |
| - Median time from arrival at an emergency department to assessment by a clinical decision maker should not exceed 60 minutes. | - February -84.6% - March – 82.21% - April – 83.26% |
| - A continuous reduction in delayed pathways of care of 5% for three consecutive months and then maintained for three months (based on Oct-Dec 23 baseline). | - February – 273 - March – 219 - April - 211 |
| - Assessment of declared BCIs, including reasons why, actions taken, and lessons learnt. | - BCI declared 10th – 13th February 2025 |

Actions being taken to improve include:

- Full implementation of D2RA model – Executive agreement between Health & Social Care CEO’S to deliver a D2RA model with a externally facilitated workshop planned for 18th March 2025.  A 7-day test of change Multi Agency Discharge Event took place based at the Morriston Hospital site between the 11th and 17th April. The success of the PDSA and interim model has continued as sponsored by the communities and older persons board and a work programme has been established to develop a sustainable model.

- Grip & control operational management – Full Capacity protocol and zero tolerance on chair and trolley waits in full operation with additional 3:30 huddle now in situ at Morriston Hospital.

- UEC Care co-ordination Hub – Funding application submitted to Six Goals to extend the role and function of the UEC care coordination hub over the seven-day period.

- Review of community capacity and operating models – workstream established, led by Director of Nursing, PCT, reporting into community and older persons board.

- Senior decision makers at front door services

- Rota proposals shared with Acute Physicians

- Recruitment to ACP/COTE posts ongoing, one recent appointment made

- Plan to introduce an interim rota 1st June 2025.

- Pathway of Care Delays (PoCD) – Focus on the delivery of actions to reduce PoCDs, COP deep dives and the recording of D2RA pathways on our SIGNAL digital system to enable increased understanding of bottlenecks within the system. Escalation to COO / Directors of Social Services on a weekly basis.

- Revised flow operating model: with consistent tactical command at Level 4 and introduction of revised internal escalation processes. External facilitated workshop held in March and Centralised flow proposal approved in principle. Will require application of OCP policy.

- Falls Pathway – Plan to commence February 2025 – enhanced opportunity via the Care Co-ordination Hub PDSA above linked to Hub

- UEC capital redesign – Two capital plans currently in progress, viability of the demountable option awaiting Executive decision with alternative plan currently with architects.

- Anglesey Ward – Opening on 2nd June 2025 for a period of six weeks as a key enabler to run six PDSA tests of change across the UEC pathway.

5.3 HCAI Improvements

| Criteria to Achieve | Current Performance |
| --- | --- |
| - Stabilisation of the increased trajectory of cases of HCAI and evidence of continuous improvement accompanied by a strong QI approach and plan that has oversight and monitoring by board Quality Safety (Q&S) Committee and Board. | - Embedded Quality Improvement approach in this area, monitored closely via Q&S Committee and Board. |
| - The Health Board to have a clear improvement plan based on a root cause analysis to address the issue of hospital onset HCAIs. | - In place |
| - C-Diff: reduce the number of hospital onset infections by 40% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 10 cases to no more than 6 per month) | - February – 11 - March – 15 - April - 11 |
| - Staph aureus: reduce the number of hospital onset infections by 25% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 4 cases to no more than 3 per month) | - February -5 - March – 3 - April - 4 |
| - E-coli: reduce the number of hospital onset infections by 20% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 5 cases to no more than 4 per month) | - February -8 - March – 4 - April - 6 |
| - Klebsiella: reduce the number of hospital onset infections by 10% and maintain for 3 months based on 2017/18 figures (baseline – 54 cases in 2017/18, reduce to average of at most 4 per month) | - February -3 - March – 5 - April - 4 |

Actions being taken to improve include:

- Gold C. difficile High Incidence Management Group continues, with Silver Groups reporting into Gold.

- The C. difficile risk stratification project work continues.

- Continued focus on improving antimicrobial stewardship, in particular the outcomes of antimicrobial review.

- Collaboration with Domestic Services and Infection Prevention & Control on improving processes and governance for enhanced cleaning during Periods of Increased Incidence.

- Collaboration with Digital intelligence to standardise and centralise recording of scrutiny panel outcomes and learning.

5.4 Finance

The Annual Plan submitted to Welsh Government on 31st March 2025 for assessment and scrutiny included a financial assessment, as summarised in the table below:

Whilst the Health Board acknowledges the Welsh Government Target Control Total of £17m, the Health Board has to firstly deliver the plan submitted at the end of March 2025, through the identification of £55.4m of savings and stabilise the expenditure growth to the value within the plan, before it can look for reduce the planned deficit. The Health Board’s actual performance against the three components (Operational Pressure, Savings Target, and Planned Deficit) are provided in the table below. This table shows that at the end of Month 1 the reported deficit was £9.003m, which is £4.11m above the planned deficit. As you will note from the table the key driver of the £4.11m deficit over plan is the non-delivery of savings in Month 1.

To achieve the £58.7m plan the Health Board needs to recover the £4.11m during 2025/26 by delivering more savings or reducing expenditure below plan in future months. A briefing was provided to the Independent Members on the 13th May 2025 where some of the options to address the situation were discussed. These options will be a key element of the discussions at the Recovery &Sustainability Board, throughout May 2025.

5.5 Planning

Updates against the de-escalation criteria outlined by Welsh Government can be found below;

| De-escalation Criteria | Actions – Updated April 2025 |
| --- | --- |
| Submission of a balanced and credible three-year medium-term plan or acceptable annual plan in line with the current planning framework. | Submission of a balanced and credible three-year medium-term plan or acceptable annual plan in line with the current planning framework. |
| Evidence of a clear roadmap and implementation of the health board’s Clinical Services Plan. | Current CSP rolled over as the agreed road map. Refreshed CSP agreed for development in 25/26 Detailed timelines in development, with DPP/COO/EMD to as tripartite lead. |
| Welsh Government’s confidence in delivery based on an assessment against an agreed planning maturity matrix | Planning Maturity Matrix update to Board Development in July 2025, and will be reported to Board in July via DPP |
| Progress made with regional planning | Next RJC meeting took place 7th May 2025 to agree programme of work, including Clinical Services and Capital Planning, Data & Digital, Workforce and OD |

- RECOMMENDATION

Members are asked to:

- CONSIDER the monthly update in respect of performance against oversight and escalation measures and de-escalation criteria.

| Governance and Assurance |  |  |
| --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |
|  | Partnerships for Improving Health and Wellbeing | ☐ |
|  | Co-Production and Health Literacy | ☐ |
|  | Digitally Enabled Health and Wellbeing | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |
|  | Best Value Outcomes and High Quality Care | ☒ |
|  | Partnerships for Care | ☒ |
|  | Excellent Staff | ☐ |
|  | Digitally Enabled Care | ☐ |
|  | Outstanding Research, Innovation, Education and Learning | ☐ |
| Health and Care Standards |  |  |
| (please choose) | Staying Healthy | ☐ |
|  | Safe Care | ☒ |
|  | Effective Care | ☒ |
|  | Dignified Care | ☐ |
|  | Timely Care | ☒ |
|  | Individual Care | ☐ |
|  | Staff and Resources | ☒ |
| Quality, Safety and Patient Experience |  |  |

Outlined within the body of the paper but in summary considerable backlog of patients awaiting a diagnostic and treatment services across a range of services. Issues of harm in relation to high levels of HCAIs noted.

Financial Implications

Funding not yet agreed for 24/25

Legal Implications (including equality and diversity assessment)

Delay to diagnosis and treatment potential.in service delivery

Staffing Implications

Additional support staffing required to deliver the programme

| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |
| --- | --- |
| Report History | First comprehensive update presented. |
| Appendices | No Appendices |