| Meeting Date | 28 November 2024 |  | Agenda Item |  |  | 5.4 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Maternity & Neonatal Independent External Review Update Report |  |  |  |  |  |
| Report Author | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of the paper is to provide the Board with an update on progress of the external review of maternity and neonatal services. |  |  |  |  |  |
| Key Issues | Key issues include: - Self-referral process remains open and has been widened to be inclusive. - letters to families to notify them of the planned review of cases have all been sent and 25% of the clinical case reviews have been completed. To date, from the families contacted, there have been no opt outs of the clinical review process; - Timeline of the review is dependent on a number of factors and at present it is anticipated the report will be available in the summer of 2025. - New appointment has been made to the Oversight Panel, who will oversee the engagement strand of the review and provide support to the Oversight Panel Chair. - Confidential Psychology support is available for services users to access via Ty Elis Counselling Services. - Website for the review continues to be updated Swansea Bay Independent Maternity and Neonatal Review |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - Take ASSURANCE from the update provided and progress made of the review. |  |  |  |  |  |

Maternity & Neonatal Independent Review Update Report

- Introduction

The purpose of the paper is to provide the Board with an update on progress of the external review of maternity and neonatal services.

- Background

In November 2023 the Board agreed to commission an external review of maternity and neonatal services to provide: assurance to the Health Board; reassurance to families, in respect of services delivered, and to identify opportunities for service improvement.  The Board also agreed to the establishment of an Oversight Panel reporting directly to Board.  Key stages are idenitfied below:

- September 2023 Healthcare Inspectorate Wales unannounced visit to maternity services, Singelton Hospital.

- December 2023 – Independent review announced, and Chair of Oversight Panel appointed, focused on 3 areas:

  - Clinical Outcomes

  - Patient and staff experience

  - Leadership and governance

- December 2023 – Healthcare Inspectorate Wales (HIW) unannounced inspection report published and Maternity and Neonatal services escalated into enhanced monitoring by Welsh Government.

- January 2024 – Board receives HIW Maternity Services inspection report.

- March 2024 – Board informed that Oversight Panel Chair has now appointed members of Panel and that a listening period  is taking place on the terms of reference for the review.

- June 2024 – Board informed that Oversight Panel have signed off Terms of Reference for the review (and published them) following feedback received from the public and staff members.  The self-referral process was widened, following feedback from service users, to allow service users (regardless of the date of their care) to be reviewed.

- June 2023 - Oversight Panel Chair resigned and agreed that Denise Chaffer would be appointed as Interim Oversight Panel Chair for three months while a substantive appointment was made (June-September 2024).

- July 2024 – Board receives HIW report into unannounced visit in April 2024.

- August – Board agrees to the interim arrangement for the oversight Panel Chair to be extended to end of December 2024 with a review of arrangements in November 2024.

- Key Updates

3.1 Review Timeline

The Oversight Panel is an important part of the Governance that ensures the independence of the review.  The Oversight Panel have set out the project plan timeline of the review in three parts with the review aiming to conclude in June 2025.  It is important to note that these are indicative timescales and may vary depending on the self-referrals.

- June to November 2024 - Setting up safe and controlled fieldwork

• Develop GDPR compliant and safe communication methods

- Develop clinical review and triage protocols

• Agree escalation principles

• Establish family engagement and self-referral portals

• Establish key stakeholder steering group

• Start to reach out to seldom heard groups

• Develop and send out first tranche of letters to families

• Establish psychological support processes for families accessing the review

• Commence clinical reviews

• Extensive information gathering

• Governance Review and report on current safety

- June to March 2025 – Fieldwork

Clinical case reviews and case studies

• Self-referral reviews / women/family experience

• Data analysis / demographic and contextual data

• Thematic review of feedback

• Staff surveys / interviews / focus groups

• Analysis and triangulation

- Report drafting

- Reporting – March to June 2025

• Draft report checks / legal review / comments

• Feedback on final report and any amendments

• Drafting of abridged, translated and easy read versions

• Final report publication (estimate)

3.2 Engagement

The Oversight Panel Chair has made a new appointment to the Oversight Panel, Ken Sutton, to provide additional oversight of the family engagement work.  Ken has a long and distinguished track record in policy and operational delivery rising to become a Senior Director at the Home Office.  After a period on secondment to Marie Curie Cancer Care, Ken specialised in engaging bereaved and other families affected by public tragedy and in independent investigations. He established the Hillsborough Independent Panel and worked closely with its chair Bishop James Jones on that inquiry and their follow up Report, " The Patronising Disposition of Unaccountable Power ".  Ken was Secretary to the independent investigation into Maternity and Neonatal Services at East Kent and is currently working to secure improvements in maternity care in England.

The family engagement team have been strengthened and are now supported by a communication company (Pinch Point) who are supporting the family engagement plan and the reach of the review via a range of communication routes to families using the maternity and neonatal services.  There has been a gradual increase in direct family contacts to the engagement team and also contacts made through the self-referral route.

In October 2024 the family engagement team had contact with around 250 service users, following presence at shopping centres in the Swansea Bay area.  This work has been undertaken in parallel with the work of Llais.

Llais is the independent patient advocate body, who have independently engaged with families via a variety of means leading to 465 contacts.  Llais will now collate its findings as part of its own work, “Having a Baby Project” which ran in the summer and the outcomes will also be shared with the Independent Review via a consolidated report.

The Family and Voices Steering Group (FCVSG) has been set up to oversee the engagement plan and continuous discussion at the meetings, providing assurance that it reflects what families want.  The FCVSG is a co-production group that discusses engagement options, how to connect with families and encourage them to make a difference to make sure their voices are heard.

Posters for co-chairs/representatives have been put on the website and sent to Directorate of Insight, Communications and Engagement (DICE) team at Health Board.  DICE have circulated this to all their contacts e.g. community groups, places/groups where families, mums and babies meet to support community engagement.   This has resulted in family members coming forward who are planning to attend the next meeting planned for end of November.  The FCVSG will discuss and consider whether to send text message to families that have used Swansea maternity and neonatal services and the approach to be taken.

The family engagement team are currently planning three webinars scheduled to take place on 27/11.  The webinar will explain the review process, discuss how their input can help shape the future of maternity and neonatal care and answer questions.  The webinar details will be published by Pinch Point and Maternity Voices Partnership Chair has agreed to circulate the poster advertising the webinar on their social media and other platforms they use.

Short videos providing information on the review and how to find out more and engage are being added to the review website and will be promoted through posters/videos via contacts on social media, including schools, GP practices and community groups.

The Family Engagement team will be exploring options to reach out to seldom heard groups and have already reached out to: Sketty Mosque and Muslim Community Centre; the African Community Centre and playgroups in the area.

  - Clinical Review Team – Issuing of Letters

All review letters have been sent to individuals and families involved in 2022, 2021 and 2020 cases.   The letters were written sensitively with a covering letter explaining why they were being contacted with a separate letter included within a separate sealed envelope.  The covering letter acknowledged that it might be upsetting to be contacted and suggested that individuals only open the second, sealed envelope when they felt ready and able to.  The second letter outlined in detail the process and made it clear how to contact the review should they need any form of support.  At present, 25% of the clinical case reviews have been completed and it is anticipated that approximately 40% of the clinical case reviews will be completed by the end of January 2025.

  - Psychological Support

In terms of bereavement and emotional / psychological support, this is available to families who would like to access this support through Ty Elis Counselling Services which is a confidential service, independent of the Health Board and can be accessed directly by families via:

Tel: 01656 786486

E-mail: OFFICE@TYELIS.ORG.UK

  - Self referral

The review self-referral has been widened to make it more inclusive to service users to support the review being inclusive rather than exclusive.  Self Referral – link  There is no timespan for self-referral as we recognise how important it is to give individuals an opportunity to revisit their care when they feel it necessary and appropriate, and we are committed to enabling them to do that.

- Governance

In terms of the expected cost of the independent review, this is difficult to predict with any certainty as it will depend on the number of case reviews and how many service users self-refer for a review of their experience of care.  A sum of £700,000 has been set aside for 2024/25 which will include costs for:

- Oversight Panel members;

- Clinical Reviews;

- Engagement with service users and staff;

- Governance and leadership;

- Wellbeing / psychological support for families;

- Legal advice;

- Resource within the health board to support the request for information for the review teams.

Monitoring of expenditure against the budget will be overseen by the Board’s Performance and Finance Committee.  The current spend totals £427,967.

- Recommendation

Members are asked to:

- Take ASSURANCE from the update provided and progress made of the review.