| Meeting Date | 25 September 2024 |  | Agenda Item |  | 3.2 |
| --- | --- | --- | --- | --- | --- |
| Report Title | Alteration of Two Theatres at Neath Port Talbot Hospital Business Case |  |  |  |  |
| Report Author | Cherri Douglas, Directorate Manager Head, Neck & Urology Sue Moore, Service Group Director, Morriston |  |  |  |  |
| Report Sponsor | Deb Lewis, Chief Operating Officer |  |  |  |  |
| Presented by | Darren Griffiths, Executive Director of Finance & Performance, Acting Deputy Chief Executive |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |
| Purpose of the Report | This report presents the Business Case which seeks approval from the Welsh Government (WG) for £4.285m (including non-recoverable VAT) capital funding to upgrade theatres 4 and 5 at Neath Port Talbot Hospital (NPTH) into OR1 theatres. OR1 theatres provide integrated laparoscopic technology that is essential for many High Volume, Low Complexity (HVLC) procedures, and currently these theatres are currently only available at Morriston. OR1 theatres at NPTH provide the infrastructure to facilitate the movement of a significant volume of elective surgical procedures from Morriston to NPTH to support the Health Board strategy for its Centres of Excellence. This case has been supported by Management Board and recommended for Approval by Performance and Finance Committee. |  |  |  |  |
| Key Issues | A central proposal of ‘Changing for the Future’ was the evolution of NPTH as a centre of excellence for the delivery of HVLC procedures across several surgical specialties. This business case details a proposal for investment into the existing Health Board estate which will directly contribute to the realisation of this strategic response, in recognition of the essential infrastructure required at NPTH to facilitate a significant element of the necessary reconfiguration of surgical services for sustainable service delivery. The alteration of two existing theatres at NPTH to introduce two OR1 theatres is recognised as a pivotal action that will facilitate the movement of activity away from Morriston, will increase efficiency of funded capacity and lay a robust foundation for the commissioning of any future additional capacity for HVLC work, ensuring this is as efficient as possible. The timescale for completion of works is 20 weeks, and the proposal is based on theatres being fully operational Q2 2025/26. The recommended option is investment in developing two OR1 theatres, which will provide the infrastructure required to: - - introduce a regional High Volume Low Complexity (HVLC) centre of excellence at Neath Port Talbot Hospital (NPTH), supporting the major theatre infrastructure plans to deliver our three Centres of Excellence model and plans for urgent and planned care services, a set out in our strategic plan ‘Changing for the Future’; - Facilitate the movement of elective work from Morriston to NPTH, improving access for other surgical specialties requiring the acute support of Morriston Hospital, both electively and non-electively. This would also provide capacity for SBUHB to provide reliable, ongoing support to BCUHB for the provision of robotic cystectomies, providing an immediate income stream; - Support a resilient, efficient and improvement focussed service model that is future-proofed to sustain the delivery of increased demand from across South-West Wales, supporting the Health Board to meet ongoing Welsh Government planned care targets by increasing the HVLC capacity of the service by over 1,500 patients per year (subject to future business cases to commission the additional activity). The case requires capital funding of £4.285 to be supported by Welsh Government. Additional revenue costs of £0.158m are indicated and these will be mitigate by provision of additional capacity to other Health Boards. |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion | Assurance | Approval |  |
|  | ☐ | ☐ | ☐ | ☒ |  |
| Recommendations | Members are asked to: - APPROVE the submission of the business case to WG for capital funding support of for £4.285m; - NOTE the requirement for future business cases to address the capacity requirements of surgical services, acknowledging that further work needs to be undertaken across the Health Board to understand the funding and commissioning requirements to remedy capacity shortfalls |  |  |  |  |

ALTERATION OF TWO THEATRES AT NEATH PORT TALBOT HOSPITAL BUSINESS CASE

- INTRODUCTION

The Health Board is asked to support the business case for the Alteration of Two Theatres at Neath Port Talbot Hospital prior to submission to Welsh Government (WG).

- BACKGROUND

A fundamental element of successful recovery from the damage caused to pathways, service models and capacity by COVID, is the acknowledgement of the shortcomings in the pre-COVID model (central to which was an over-reliance on undertaking activity at Morriston Hospital) and the recognition of the opportunity to rebuild in an improved way, remodelling and transforming a service to future proof the needs of the population. Fundamental to achieving this is the delivery of high-volume elective activity in a ‘protected’ environment from the demands of emergency care to enable optimal throughput of elective capacity. This would provide benefits not merely to Swansea’s catchment population but would also enable the development of a regional centre of excellence.

In an OR1, the operating theatre is a fully integrated and incorporates a wide range of equipment and technology to facilitate minimal access endoscopic surgery. The integrated laparoscopic theatre is a state-of-the-art system in which the laparoscopic equipment and multiple monitors are permanently installed to be operational on demand inside the theatre.

The systems focus is on improved workflows, an ergonomic and efficient workplace design, and future-proof technologies. OR1 theatres are not interchangeable with other theatres due to the significantly higher specification of the OR1 theatre. Clinical benefits of OR1 compared to a standard laparoscopic stack are well established, with OR1 theatres embedded as the UK standard for most laparoscopic surgery for over 15 years.

The streamlined, integrated nature of OR1 theatres mean that this creates the ideal environment for high volume, fast turnaround procedures. The setup means that they are perfectly setup to facilitate innovative delivery models such as High Intensity operating lists, where one surgical team manages two theatres, resulting in very high efficiency and throughput for lower costs. Two adjacent OR1 theatres are the ideal model for a HVLC hub, which can focus on developing and honing these high-volume delivery models. There are a significant number of HVLC surgical procedures that either require OR1 facilities to undertake, or are significantly more efficient with OR1 facilities.

The creation of an environment to enable the achievement of the required surgical standard of efficiency and productivity is one of the most significant factors outstanding in the ability to attain a HVLC hub service model. The primary obstacle to the delivery of this volume of procedures is access to adequate OR1 facilities on a site that can support a high volume of patients.

HVLC hub working requires investment in, or re-siting of, equipment to enable to full range of HVLC procedures to be undertaken in a location that not only can support a high throughput of patients, but one that is protected from the competing pressures of acute hospitals. At present, SBUHB has three OR1 theatres, all based at Morriston Hospital. This means that all procedures requiring OR1 facilities must be admitted and operated on at this very acute site. For most of these procedures, this is the only reason that these patients require Morriston, and with the right facilities could be operated on at a different site.

By their nature, the presence of these procedures on theatre lists at Morriston add significant additional footfall and bed demand to the site, reiterating on a weekly basis the rationale for the strategic drive to relocate as much elective surgical activity away from Morriston to be delivered at NPTH and Singleton. Meanwhile, NPTH site lends itself to the admission pressures of high-volume elective activity, avoiding many of the competing demands of more acute sites. However, specialties are limited as to the nature of the procedures that can be undertaken on the site due to the specification of the theatres.

By the removal of other constraining factors such as competing demands for bed capacity, movement of funded capacity from Morriston to NPTH would allow for greater throughput to be achieved, therefore achieving a greater operational efficiency for this capacity. The average number of high-volume low complexity (HVLC) cases per session at NPTH is 2.4 cases whilst the average HVLC cases per session at Morriston is 1.7 cases. However, with one OR1 the average HVLC that can be achieved is 2.9 cases per session, with this increasing to 3.5 cases per session if there are two adjacent OR1 theatres, due to the flexibility this offers.

|  | Morriston OR1 | NPTH non-OR1 | NPTH OR1 | NPTH 2 x OR1 |
| --- | --- | --- | --- | --- |
| HVLC Cases per session | 1.7 | 2.4 | 2.9 | 3.5 |
| Operational Efficiency Gain | Baseline | 41% increase | 70% increase | 105% increase |

This demonstrates the extent to which the benefits of OR1 capacity at Morriston are being curtailed due to other constraining factors. By creating the environment to get more activity out of existing capacity, the OR1 investment will create essential increases in capacity, as well as laying the foundation for cases to be made to further expand the available capacity.

The underutilisation of Morriston sessions for these HVLC procedures due to limitations in access means that keeping HVLC sessions at Morriston would maintain the incumbent inefficiency and ultimately require a higher number of additional sessions to meet demand.

The proposed NPTH development would allow the release of at least one of the Morriston OR1 theatres. Theatre 10 at Morriston has OR1 specification, but is also the most appropriate theatre to house the new surgical robot. Theatre 10 does not need to maintain its OR1 status in order to operate the robot. With plans to expand the use of the surgical robot to 5 days a week, this theatre would no longer be available to provide OR1 capabilities during the week. Based on the current Morriston activity, accurate scheduling would mean that two OR1 theatres would be sufficient to support those complex procedures that require OR1 technology as well as Morriston’s support.

- GOVERNANCE AND RISK ISSUES

A shortfall in theatre capacity across several surgical specialties creates a demonstratable impact on performance, with RTT waits of over 2 years and slower than optimal USC pathway times. The mismatch of resources leading to inefficiencies contributes to this shortfall, and this should be rectified before any wider assessment of capacity shortfalls is undertaken to ensure that the best possible value for money is obtained. Morriston capacity remains oversubscribed with many procedures that could safely be relocated to alternative sites with the correct theatre capabilities available. The current model presents a considerable risk to patient access. This precludes any ability to support regional working and benefit from the income that this generates.

- OPTIONS

The shortlisted options were agreed as follows:

| Option | Reason for Acceptance or Rejection for further consideration | Finding |
| --- | --- | --- |
| Option 1: Business as Usual: No change to the theatre specification or configuration – Morriston retains the only OR1 capability for the Health Board and continues to manage the resulting, avoidable, competing demands. | Fails to deliver strategic direction of Health Board or operational necessity of relocating activity away from Morriston, leading to a continuation of unnecessary pressures on Morriston capacity. Retains underutilisation of funded capacity and incumbent inefficiencies. Continues to have a small theatre at NPTH that has limited functionality. | Discounted (retained as Baseline Comparator) |
| Option 2: Do Minimum: Provide some limited efficiency gains but retain the activity at Morriston and not future proofing surgical delivery by investing in one OR1 theatre at NPTH. | Allows some efficiency gains by introducing this type of theatre type to NPTH, facilitating some additional capacity by moving some existing NPTH activity into this theatre. However, there is limited scope to facilitate movement away from Morriston. This does not provide the infrastructure to future-proof surgical services for SBUHB. | Discounted |
| Option 3: Do Maximum: Provide a future-proofed infrastructure to facilitate gains in operational efficiency significant enough to represent capacity increases, allowing relocation of activity by developing two OR1 theatres at NPTH. | Provides the infrastructure to deliver significant operational efficiency gains and therefore the opportunity to optimise funded capacity. Facilitates the implementation of Health Board strategy to relocate activity away from Morriston, support the decompression of the site to provide the best care to patients who require the support of the site. Future-proofs the surgical footprint by introducing a HVLC hub that can deliver regional work, innovate and train others in its model. | Preferred |

Following evaluation, the preferred option and optimum clinically supported solution was confirmed as Option 3 (Do Maximum – develop two OR1 theatres at Neath Port Talbot).

- BENEFITS

This investment supports clinical and skills sustainability benefits by delivering safer and more sustainable theatre services and by facilitating high standards of patient care. For example, on average, OR1 theatres are 20% more efficient than regular theatres (for Urology HVLC procedures) by creating the infrastructure to undertake the same amount of activity with less theatre resource. In practice, this means that moving 6 existing NPTH sessions at NPTH into OR1s will allow the same amount of activity to be achieved through an estimated 4.8 sessions.

Furthermore, access to future-proofed infrastructure will allow development of regional HVLC services following recovery of local services and, by operating more efficiently, will facilitate potential income generation opportunities (which could be utilised for offsetting maintenance costs) that we otherwise cannot support. Specifically, at present, Welsh Government have requested support to assist Betsi Cadwaladr University Health Board (BCUHB) in delivering cystectomy surgery for its population. We are in the process of converting our cystectomy surgery from open to robotic, reducing post operative lengths of stay and improving outcomes.

The investment proposed here would allow the Health Board to free up the physical capacity at Morriston to accept a regular number of BCUHB cystectomy patients without adversely impacting on other surgical activity, creating an income stream as well as a reliable pathway to support BCUHB patients with bladder cancer.

- COMMISSIONING & FINANCIAL IMPLICATIONS

### Capital Costs

The building works are estimated.

This will require estimated capital funding support from WG through the All Wales Capital Programme (AWCP).

Capital Requirements (£000 incl. recoverable VAT)

|  | Option 3 Preferred Option |
| --- | --- |
| Works Costs | 1,362 |
| Non-Works | 40 |
| Fees | 608 |
| OR1 Equipment | 829 |
| General Equipment Costs | 859 |
| Risk Contingency | 201 |
| Total (excl VAT) | 3,899 |
| VAT | 780 |
| Less Recoverable VAT | -394 |
| Outturn Cost | 4,285 |

Revenue Costs

The only revenue costs included in this case are those related to the capital above. Given the current financial environment and considering the complexities involved in the commissioning of theatre activity post-COVID, any considerations of the specifics of theatre capacity, service performance and recovery need to be considered separately from the development of the infrastructure, which is considered to only be strengthened by this separation.

The assumption underpinning this case is that allocated theatre capacity and funding will remain at the current levels until such time as a future business case is put forward, or alternative commissioning mechanism as determined by the Theatre Board and its governance structure, to support the commissioning of additional capacity above these levels.

Revenue Requirements (£000 incl. VAT)

|  | Option 3 Preferred Option |
| --- | --- |
| Works – PFI Lifecycle | 10 |
| OR1 Maintenance | 38 |
| Equipment Maintenance | 103 |
| Project Cost | 151 |

- INDICATIVE PROGRAMME

| Milestone Activity | Date |
| --- | --- |
| Health Board signs off BJC | Sept 2024 |
| Submit BJC to WGov for scrutiny and approval | Sept 2024 |
| Enter Contract | Jan 2025 |
| Works | April – August 2025 |
| Technical & Clinical Commissioning | September 2025 |
| Operational | September 2025 |

- RECOMMENDATION

Members are asked to:

  - APPROVE the submission of the business case to WG for capital funding support of for £4.285m;

  - NOTE the requirement for future business cases to address the capacity requirements of surgical services, acknowledging that further work needs to be undertaken across the Health Board to understand the funding and commissioning requirements to remedy capacity shortfalls

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| - Improves Equity of Access within the region to high-quality, timely treatment - Creates the infrastructure for increased surgical capacity - Reduces risk to patients and staff in theatre - Reduces risk to patients by improving access - Improves patient experience – outpatient clinics are held at NPTH, patients will be returning to the same site for their surgery. Lower likelihood of cancellations. Elective focussed environment. |  |  |  |
| Financial Implications |  |  |  |
| - Capital funding required from WG for £4.285m - The current revenue associated with this is £151k |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| N/A |  |  |  |
| Staffing Implications |  |  |  |
| ### N/A |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| By facilitating the timely treatment of patients requiring urological intervention, for both benign and malignant disease, this change supports the population of SBUHB to achieve all the wellbeing goals set out by the Act. This change is also pursuant to the future-proofing and longevity of the service. Principle; Comment. Long Term; This proposal provides significant future proofing for both the service and the NPTH site in enabling endoscopic surgery on the site. Prevention; This proposal prevents the deterioration of the ongoing pressures on Morriston Hospital from elective admissions, by providing a viable alternative location for surgery for a high-volume specialty. Integration; This proposal supports population health by facilitating the timely treatment of urological conditions and cancers. Collaboration; This proposal requires the collaborative working of a number of different service areas across the Health Board in order to maximise all opportunities created, as well as mitigate risks. Involvement; All relevant parties are involved in the proposal and implementation. |
| Report History |  | BCSG 8/02/24 BCAG 14/05/24 Management Board 21/08/24 Performance & Finance Committee 27/08/24 |  |
| Appendices |  | Full BJC and associated appendices are included as Board member resources |  |