| Meeting Date | 25th September 2024 |  | Agenda Item |  | 4.4 |
| --- | --- | --- | --- | --- | --- |
| Report Title | Targeted Intervention Update |  |  |  |  |
| Report Author | Craige Wilson, Deputy Chief Operating Officer |  |  |  |  |
| Report Sponsor | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention |  |  |  |  |
| Presented by | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention Anjula Mehta, Interim Medical Director / Medical Lead for Targeted Intervention |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |
| Purpose of the Report | To provide the Board with a summary of the performance and outcomes issues for the services escalated to Targeted Intervention level of performance monitoring by Welsh Government, namely: - Urgent and Emergency Care (UEC) - Cancer - Planned Care - Healthcare Acquired Infections (HCAIs) - Child and Adolescent Mental Health (CAMHs) |  |  |  |  |
| Key Issues | Following the Welsh Government’s tripartite meeting in December 2023, the Health Board was escalated to Targeted Intervention for performance and outcomes in the areas noted above. A comprehensive work-programme has been put in place across the Health Board to monitor progress. This report provides an update against performance measures following the previous oversight and assurance of the programme. |  |  |  |  |
| Specific Action Required (Please choose one only) | Information | Discussion | Assurance | Approval |  |
|  | ☒ | ☐ | ☒ | ☐ |  |
| Recommendations | Members are asked to: - CONSIDER the monthly update in respect of performance against Targeted Intervention measures and de-escalation criteria. |  |  |  |  |

- INTRODUCTION

The previous report described the actions and longer-term proposals being developed and implemented in response to escalated performance monitoring arrangements by Wales Government. The report provided an update on the operational programme to manage the delivery of improved performance and outcomes for services under targeted intervention, namely:

- Urgent and Emergency Care (UEC)

- Cancer

- Planned Care

- Healthcare Acquired Infections (HCAIs)

- Child and Adolescent Mental Health (CAMHs)

- BACKGROUND

Following Welsh Government’s tripartite meeting in December 2023, the Health Board was notified of an escalation of performance monitoring for performance and outcomes from enhanced monitoring to Targeted Intervention.  The services listed in the introduction of this report were specifically included in the escalation.  On 12th April 2024, the Health Board had its inception meeting with Welsh Government colleagues and on 24th April the first quarterly meeting was held with the Chief Executive of NHS Wales.  Quarterly meeting will subsequently alternate with formal Joint Executive Team (JET) meetings.  Monthly review meetings will be held with WG officers.  The Chief Operating Officer has been appointed as the Senior Responsible Officer (SRO) for targeted invention and each work programme is supported by senior management and clinical leads.

- PERFORMANCE AGAINST THE TARGETED INTERVENTION SERVICES

The escalation is managed formally via an escalation framework, which was shared in the previous report.  For services to move from targeted intervention back to enhanced monitoring, a set of de-escalation criteria must be achieved and maintained for at least three months.  The criteria to achieve and maintain is set out in each section below, together with the current performance for the services and actions being taken to progress improvement to achieve the criteria.  The Health Boards financial position is a factor in terms of what the Health Board can achieve and this is considered as part of the discussions when considering the actions to improve performance.

3.1 Cancer

| Criteria to Achieve | Current Performance |
| --- | --- |
| - 60% performance maintained for 3 months against the Single Cancer Pathway (SCP) target. | - May 57% - June 58% - July 59% Trajectory to achieve 60% by end of Sept (Will not be reported on until 1st week of November). |

Actions being taken to improve include:

- Daily review of referrals to ensure priority booking within 10 days.  Initiated within Breast and Gynaecology, resulting in significant improvement and now being rolled out to dermatology, plastic surgery, ENT and oral maxillofacial surgery w/c September 9th .

- Continued focus on Pathology turnaround time to support achieving a decision to treat (DTT) by day 31.

- Weekly performance reviews with all tumour site leads, chaired by the Deputy Chief Operating Officer.

3.2 Planned Care

| Criteria to Achieve | Current Performance (July-24) |
| --- | --- |
| - 100% of open outpatient pathways to be waiting less than 52 weeks and maintained for 3 months. | - 100% - meets de-escalation criteria |
| - 100% of open pathways to be waiting less than 104 weeks and maintained for 3 months. | - 98.64% - slight improvement |
| - 80% of open pathways to be waiting less than 52 weeks and maintained for 3 months. | - 85.4% - meets de-escalation criteria |
| - 15% reduction in the number of patients delayed by 100% for their follow up appointment in three consecutive months and maintained for 3 months (Based on the November 2023 baseline.) | - 2.6% reduction – very slight improvement NOTE – there is a data issue affecting the reporting in this area. HB is working with partners to resolve. |
| - 65% R1 ophthalmology patient pathways to be waiting within or no longer than 25% of their target date for an outpatient appointment and maintained for 3 months. | - 72% - meets de-escalation criteria |
| - 80% of patients waiting for a diagnostic test to be waiting less than 8 weeks and maintained for 3 months. | - 72.06% improvement but still impacted upon by long endoscopy waiting times |
| - 80% of patients waiting for a diagnostic endoscopy to be waiting less than 8 weeks and maintained for 3 months. | - 27.58% - slight improvement |
| - 80% of patients waiting for a NOUS and non-cardiac MRI to be waiting less than 8 weeks and maintained for 3 months. | - 100% - meets de-escalation criteria |
| - 85% of patients waiting for therapies to be waiting less than 14 weeks and maintained for 3 months. | - 99.91% - meets de-escalation criteria |

Actions being taken to improve include:

- Robust monitoring via live dashboards

- Weekly monitoring meetings chaired by Service Group Directors

- Bi-weekly oversight meeting chaired by the Chief Operating Officer

- Specific support commissioned for Gynaecology improvement plans

- Regional orthopaedics programme ongoing to provide capacity for patients not suitable for surgery at NPTH to reduce demand for Morriston Hospital services.

3.3 Urgent and Emergency Care

| - A continuous reduction of ambulance handovers over an hour of at least 11% in three consecutive months and maintained for 3 months (Based on quarter 2 and 3 2023 baseline). | - 15.1% - June - 18.36% - July - 5.37% - August |
| --- | --- |
| - Continuous improvement towards no more than 7% of patients waiting over 12 hours at each individual site and across the health board. | - 8.4% - - June - 8.1% - July - 10.2% - August |
| - Median time from arrival at an emergency department to assessment by a clinical decision maker should not exceed 60 minutes. | - 76.8% - June - 83.9% - July - 77% - August |
| - A continuous reduction in delayed pathways of care of 5% for three consecutive months and then maintained for three months (based on Oct-Dec 23 baseline). | - Slight reduction (219 for July) |
| - Assessment of declared BCIs, including reasons why, actions taken, and lessons learnt. | - Only one BCI declared so far in 24/25 |

Despite improvements in all performance metrics in July and August has seen a deterioration in performance due to peak leave and a challenging IPC position across all Hospital sites in the Health Board

Actions being taken to improve include:

- Frailty strategy – approved via Management Board – phase two coming on line in September

- Grip & control operational management – Full Capacity protocol and zero tolerance on chair and trolley waits planned for launch in October 2024

  - Review of community capacity and operating models: ACT & Virtual Wards

- Senior decision makers at front door services

  - Rota proposals shared with Acute Physicians

  - Recruitment drive commenced for x5 Acute Geriatricians and x5 Acute Physicians

  - Plan to implement new interim rota in October 2024 whilst recruitment takes place

- Pathway of Care Delays (PoCD) – Multi Agency Discharge Event (MADE) undertaken in August and 6A’s audit follow up took place to improve discharge and transfer processes.

  - Singleton & Morriston COP capacity under redesign for October 2024

- Reconfiguration of Emergency Dept – funding received to develop reconfiguration plans – lead by Capital Planning.

- Revised flow operating model: with consistent tactical command at Level 4 and introduction of revised internal escalation processes

3.4 CAMHS

| Criteria to Achieve | Current Performance (May- July24) |
| --- | --- |
| - 80% of LPMHSS mental health assessments undertaken within 28 days from the date of receipt of referral. | - May 41% - June 62% - July 72% |
| - 65% of therapeutic interventions started within 28 days following an assessment by LPMHSS. | - May 98% - June 100% - meets the de-escalation criteria |
| - 80% of HB residents in receipt of secondary mental health services who have a valid care and treatment plan. | - May 97% - June 95% - meets the de-escalation criteria |

Actions being taken to improve include:

- Substantive recruitment is ongoing for three permanent band six post to improve the workforce for this part of the service

3.5 HCAI Improvements

| Criteria to Achieve | Current Performance (Jun-24) |
| --- | --- |
| - Stabilisation of the increased trajectory of cases of HCAI and evidence of continuous improvement accompanied by a strong QI approach and plan that has oversight and monitoring by board Quality Safety (Q&S) Committee and Board. | - Embedded Quality Improvement approach in this area, monitored closely via Q&S Committee and Board. |
| - The health board to have a clear improvement plan based on a root cause analysis to address the issue of hospital onset HCAIs. | - In place |
| - C-Diff: reduce the number of hospital onset infections by 40% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 10 cases to no more than 6 per month) | - June - 9 - July - 5 - August - 18 |
| - Staph aureus: reduce the number of hospital onset infections by 25% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 4 cases to no more than 3 per month) | - June - 4 - July - 4 - August - 8 |
| - E-coli: reduce the number of hospital onset infections by 20% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 5 cases to no more than 4 per month) | - June - 6 - July - 4 - August - 6 |
| - Klebsiella: reduce the number of hospital onset infections by 10% and maintain for 3 months based on 2017/18 figures (baseline – 54 cases in 2017/18, reduce to average of at most 4 per month) | - 6 (from 3 in May) |

Actions being taken to improve include:

- Gold C. difficile High Incidence Management Group established.

- Pilot to commence at the end of September 2024 on AMU to convert IV antibiotics to oral using a checklist at board rounds. A junior doctor will use this to either speak to the board round lead separately or to raise as each relevant patient is discussed in order to agree whether the switch can be made.

- Review availability and evidence regarding cleaning products effective against C. difficile.

In addition the criteria set out in the tables, Welsh Government will also undertake a review of:

- Patient experience surveys and evidence of use of Datix and CIVICA data to inform quality improvement processes and the experience of patients and their families in these targeted intervention services; and

- Assessment of health board response and handling of concerns, complaints, incidents and patient experience feedback related to planned care.

RECOMMENDATION

Members are asked to:

- CONSIDER the monthly update in respect of performance against targeted intervention measures and de-escalation criteria.

| Governance and Assurance |  |  |
| --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |
|  | Partnerships for Improving Health and Wellbeing | ☐ |
|  | Co-Production and Health Literacy | ☐ |
|  | Digitally Enabled Health and Wellbeing | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |
|  | Best Value Outcomes and High Quality Care | ☒ |
|  | Partnerships for Care | ☒ |
|  | Excellent Staff | ☐ |
|  | Digitally Enabled Care | ☐ |
|  | Outstanding Research, Innovation, Education and Learning | ☐ |
| Health and Care Standards |  |  |
| (please choose) | Staying Healthy | ☐ |
|  | Safe Care | ☒ |
|  | Effective Care | ☒ |
|  | Dignified Care | ☐ |
|  | Timely Care | ☒ |
|  | Individual Care | ☐ |
|  | Staff and Resources | ☒ |
| Quality, Safety and Patient Experience |  |  |

Outlined within the body of the paper but in summary considerable backlog of patients awaiting a diagnostic and treatment services across a range of services. Issues of harm in relation to high levels of HCAIs noted.

Financial Implications

Funding not yet agreed for 24/25

Legal Implications (including equality and diversity assessment)

Delay to diagnosis and treatment potential.in service delivery

Staffing Implications

Additional support staffing required to deliver the programme

| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |
| --- | --- |
| Report History | First comprehensive update presented. |
| Appendices | N/A |