| Meeting Date | 23/07/2024 |  | Agenda Item |  |  | 3.3 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Controlled Drug Governance and Assurance (Progress Report) |  |  |  |  |  |
| Report Author | Rhys Howell (Advanced Pharmacist – Governance, Improvement and Transformation) |  |  |  |  |  |
| Report Sponsor | Judith Vincent (Clinical Director for Pharmacy & Medicines Management & Controlled Drugs Accountable Officer) |  |  |  |  |  |
| Presented by | Rhys Howell (Advanced Pharmacist – Governance, Improvement and Transformation) |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | This paper provides a progress report on the strengthening of controlled drug governance arrangements across the Health Board. |  |  |  |  |  |
| Key Issues | The Controlled Drugs (Supervision of Management and Use) (Wales) Regulations 2008 place a statutory responsibility on the Health Board and its Controlled Drug Accountable Officer to ensure the safe management and use of controlled drugs. As previously noted, controlled drug governance requires strengthening across the Health Board in order to provide the necessary assurance regarding compliance with this legislation. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to receive this progress report detailing the actions taken to strengthen controlled drug governance across the Health Board. |  |  |  |  |  |

Controlled Drug Governance and Assurance (Progress Report)

- INTRODUCTION

The Controlled Drugs (Supervision of Management and Use) (Wales) Regulations 2008 place a statutory responsibility on the Health Board and its Controlled Drug Accountable Officer (CDAO) to ensure the safe management and use of Controlled Drugs (CDs). It has been identified by the CDAO that CD governance needs to be strengthened across the Health Board in order to provide the Board with the necessary assurance regarding compliance with this legislation. This paper documents progress made to date.

- BACKGROUND

  - Formalising the structure of controlled drug governance

As reported previously, there has been a gradual devolution over recent years of responsibilities for ensuring safe and effective management of controlled drugs from the CDAO alone, to the four Service Groups. This process of change, deliberately designed to be incremental and to allow maximum flexibility for Service Groups has seen an alignment of controlled drug governance to the Health Board’s wider structure of governance. Though punctuated with competing service pressures, not least the covid pandemic, Service Groups have made progress to strengthen controlled drug governance.

Acknowledging this significant work by Service Groups, the CDAO, working in close collaboration with the Acting Executive Medical Director, now seeks to formalise these arrangements to ensure a robust and consistent approach to controlled drug governance across the Health Board. It is envisaged that this will both support Service Group CD Leads whilst also providing assurance to the CDAO and the Board of safe and appropriate controlled drug management.

Agreement has been sought and received from Service Groups regarding an outline controlled drug governance structure that will provide consistency of approach yet maintain flexibility to ensure implementation can align closely with existing Service Group governance and reporting mechanisms.

Arrangements for onward reporting of controlled drug related matters corporately within the organisation are being scoped and will be finalised in due course.

  - Internal Audit Report of Controlled Drug Governance (November 2022)

In November 2022, following an audit comprising of ward/theatre visits and meetings with Service Group CD Leads, Internal Audit produced a report of ‘reasonable assurance’ overall.

As previously reported, it was not possible to meet the initial deadlines for action in response to the audit’s three recommendations. This was largely because it took longer than originally anticipated to identify the best way forward regarding potential CD policy and standard operating procedure changes. Teams involved in the delivery of this action plan have also had to manage competing priorities with limited resource to progress this work.

Following finalisation of the updated actions required to meet the recommendations of the audit towards the end of last year, Pharmacy and Service Group colleagues have been working to ensure required action is taken.

It is anticipated that the work described above in section 2.1 will support attainment of assurance required that the internal audit recommendations have been successfully completed.

- GOVERNANCE AND RISK ISSUES

The Controlled Drugs (Supervision of Management and Use) (Wales) Regulations 2008 place a statutory responsibility on the Health Board and its CDAO to ensure the safe management and use of CDs. Strengthening of CD governance is required across the Health Board in order to move towards a fully compliant position against these statutory responsibilities. The actions taken to date and future plans outlined in this paper aim to mitigate this risk of non-compliance through strengthening the Health Board’s CD governance.

- FINANCIAL IMPLICATIONS

Strengthening CD governance requires a significant amount of time from both staff supporting the CDAO, Service Groups and corporate colleagues. In recognition of this, the phased approach to implementing strengthened CD governance is designed to deliver improved governance within a context of existing service pressures and competing priorities.

- RECOMMENDATION

Members are asked to receive this progress report detailing the actions taken to strengthen controlled drug governance across the Health Board.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☐ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Action taken to strengthen CD governance across the Health Board will include improvements in the quality and safety of care provided, as it relates to CDs and hence the patient experience. |  |  |  |
| Financial Implications |  |  |  |
| Strengthening CD governance will require a significant amount of time from both staff supporting the CDAO, Service Groups and corporate colleagues. In recognition of this, the phased approach being taken is designed to deliver improved CD governance within a context of existing service pressures and competing priorities. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| The Controlled Drugs (Supervision of Management and Use) (Wales) Regulations 2008 place a statutory responsibility on the Health Board and its CDAO to ensure the safe management and use of CDs. Strengthening of CD governance is required across the Health Board in order to move towards a fully compliant position against these statutory responsibilities. |  |  |  |
| Staffing Implications |  |  |  |
| The strengthening of CD governance will require a significant amount of time from both staff supporting the CDAO, Service Groups and corporate colleagues. In recognition of this, the phased approach being taken is designed to deliver improved CD governance within a context of existing service pressures and competing priorities. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| - Long Term – The Health Board will have strengthened CD governance in line with requirements of, ‘The Controlled Drugs (Supervision of Management and Use) (Wales) Regulations 2008.’ - Prevention – Strengthened CD governance will help to prevent CD incidents. - Integration – Integrating the requirements of, ‘The Controlled Drugs (Supervision of Management and Use) (Wales) Regulations 2008,’ with the existing governance mechanisms of the Health Board will strengthen overall CD governance. - Collaboration – The approach being taken will encourage collaboration between Service Groups in the development of strengthened CD governance. - Involvement – Health Board wide involvement in the development of strengthened CD governance will produce a synergistic effect at a whole system level. |  |  |  |
| Report History |  | - Presentation made to the SLT in March 2019 regarding concerns about controlled drug governance. - Paper presented to SLT on the 6th November 2019 entitled ‘Controlled Drug Governance: Update Report’ – this paper outlined the previous concept of a Health Board CD Governance Framework. - Paper presented to SLT on the 5th November 2020 entitled, ‘Controlled Drug Governance and Assurance’ – This paper set out the new phased approach to strengthening CD governance. - Paper presented to Quality & Safety Committee on 27th April 2021 entitled ‘Controlled Drug Governance and Assurance (Progress Report) - Paper presented to Quality & Safety Committee on 23rd November 2021 entitled ‘Controlled Drug Governance and Assurance (Progress Report) - Paper presented to Quality & Safety Committee on 24th May 2022 entitled ‘Controlled Drug Governance and Assurance (Progress Report) - Paper presented to Quality & Safety Committee on 25th October 2022 entitled ‘Controlled Drug Governance and Assurance (Progress Report) - Paper presented to Quality & Safety Committee on 25th July 2023 entitled ‘Controlled Drug Governance and Assurance (Progress Report) - Paper presented to Quality & Safety Committee on 23rd January 2024 entitled ‘Controlled Drug Governance and Assurance (Progress Report) |  |
| Appendices |  | N/A |  |