
[image: image1.jpg]


                                 [image: image2.jpg]Bwrdd lechyd Prifysgol
Bae Abertawe

Swansea Bay University
Health Board



                   [image: image3.jpg]


                                     
Audit Committee Action Log
	Open Actions

	Action No.
	Minute Ref.
	Date
	Agreed Action
	Lead
	Timescale
	Status

	1. 
	91/23
	13.07.2023
	STA/SQA Report

A referral be made to the Workforce, OD and Digital Committee issues relating to managers’ awareness of key budgetary functions such as raising purchase orders, staff change forms and rostering effectively
	Committee Chair
	February 2024
	It was agreed to keep this item on the agenda until all referrals had completed. 

	2. 
	120/23
	14.09.2023
	Complaint Handling 

Hazel Lloyd agreed to look at complaint handling as part of the learning from cases report to Quality and Safety Committee.
	Director of Corporate Governance
	January 2024
	The report went to the November 2023 quality and safety committee – Hazel Lloyd to provide confirmation at the January 2024 committee.  

	3. 
	136/23
	9.11.2023
	Hazel Lloyd agreed to link in with the executive lead of the Equality Impact Assessment Process and would feedback to the committee in January 2024.
	Director of Corporate Governance 
	January 2024
	A verbal update be provided at the January 2024 committee. 

	4. 
	136/23
	9.11.2023
	Access to cancer services’ 
An update on the overdue actions of the access to cancer services’ be provided to the January 2024 committee.
	Medical Director/Chief Operating Officer
	January 2024 since deferred to March 2024
	A written update on the overdue actions be provided at the March 2024 committee. 

	5. 
	136/23
	9.11.2023
	Swansea Wellness Centre 
An update on the Swansea Wellness Centre be provided to the March 2024 committee.
	Director of Finance and Performance 
	March 2024
	A written update on the overdue actions be provided at the March 2024 committee. 

	6. 
	137/23
	9.11.2023
	Risk Register 
Neil Thomas agreed to link in with the executive lead regarding the risk score rating of 16 for the Mental Health Capacity Act Assessments.
	Head of Risk/Director of Corporate Governance
	March 2024
	Update to be provided in the next iteration of the risk register report. 

	7. 
	138/23
	9.11.2023
	Regulatory Bodies 

To develop a report in terms of the regulatory compliance reporting and would bring a report to the March 2024 committee setting out timescales.
	Head of Risk/Director of Corporate Governance
	March 2024
	To be added to the March 2024 agenda. 

	8. 
	143/23
	9.11.2023
	Internal Audit Reports – Referrals 

Estates, Limited assurance report and Stroke Action Plan, Reasonable assurance report be referred to the Performance and Finance Committee
	Chair/Director of Corporate Governance 
	February 2024
	To be added to the February 2024 Performance and Finance agenda. 

	Closed Actions

	Action No.
	Minute Ref.
	Date
	Agreed Action
	Lead
	Timescale
	Status

	1. 
	117/23
	14.09.2023
	Audit Wales

To provide clarity around the charitable funds accounts timetable
	Director of Corporate Governance/Audit Wales
	November 2023
	The audit was confirmed to commence on 20th November 2023.  


3 | Page
Audit Committee – January 2024

