| Meeting Date | 18 January 2024 |  | Agenda Item |  |  | 2.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Quality Management Framework Stock-Take |  |  |  |  |  |
| Report Author | Angharad Higgins, Head of Quality and Safety |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance Raj Krishnan, Executive Medical Director Gareth Howells, Director of Nursing and Patient Experience Debbie Eyitayo, Director of Workforce and OD |  |  |  |  |  |
| Presented by | Hazel Lloyd, Director of Corporate Governance Raj Krishnan, Executive Medical Director Gareth Howells, Director of Nursing and Patient Experience Debbie Eyitayo, Director of Workforce and OD |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of the report is to set out the progress to develop a quality management framework. |  |  |  |  |  |
| Key Issues | The Duty of Quality came into effect in April 2023 and requires the organisation to place quality at the core of our decision making and to have in place an effective quality management system. Quality comprises patient safety, experience, clinical effectiveness, outcomes and access within health services. Considerable work has been undertaken across the organisation to strengthen our quality management system, following internal and external review of our governance systems. Part of the work to address the recommendations of the reviews was to establish a quality management system. To support the work needed, a task and finish group was set up to agree the actions to take forward and monitor progress, chaired by the previous Chief Executive. A stock-take was presented to the meeting in March 2023 and the decision made that sufficient progress had been made and the work could now be part of the Management Board going forward. Further to this, work was undertaken to create the vision and One Bay Way for the organisation to create a clinically-led, high quality organisation which will further drive forward the work for a quality management framework. A self-assessment and action plan was developed in response to the launch of the Speaking up Safely framework. The majority of the initial actions identified through the review process in 2023 have been completed. A follow up internal audit of our quality management system will be reported in May 2024. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the progress against the actions to develop a quality management system and that this work will now been overseen by the Management Board. |  |  |  |  |  |

QUALITY MANAGEMENT FRAMEWORK STOCK-TAKE

- INTRODUCTION

The purpose of the report is to provide an updated position on the embedding of our quality management system.

- BACKGROUND

Quality comprises patient safety, experience, clinical effectiveness, outcomes and access within health services. The Duty of Quality came into effect in April 2023 and this placed a duty of all health boards to ensure that their actions and decisions promote quality in line with the Institute of Health Improvement Principles of quality care, namely care that is:

- Safe

- Timely

- Effective

- Equitable

- Efficient

- Person-care

In the last 12 months, a number of reviews, both internally and externally have taken place of quality governance:

- Internal review of the quality governance arrangements in the service groups;

- Audit Wales review of quality governance;

- Internal audit of the quality governance framework and a subsequent follow-up review

The reviews provided a clear baseline of the current quality system within the health board. They were followed by two externally facilitated quality workshops with the Management Board and a Health Board development session to discuss the requirements for a quality management system and the wider organisational culture. The findings of which were shared with the Management Board, Audit Committee and Board.

In June 2023, the Institute for Health Care Improvement and Improvement Cymru undertook a quality review, the report for which has been shared with the Management Board and board members. The main areas for improvement included data, lineation of aims and trajectories and improvement methodologies, including training for staff.

Work to develop a robust quality management system was led by the previous Chief Executive and supported by the Director of Nursing and Patient Experience as the executive lead for quality along with the Medical Director, Director of Therapies and Health Science, Director of Workforce and OD and Director of Corporate Governance. However, it is recognised that everyone has a role in improving quality and that the culture is an intrinsic component of helping to drive the reset for quality improvement.

Further to this, work was undertaken to create the vision and One Bay Way for the organisation to create a clinically-led, high quality organisation which will further drive forward the work for a quality management framework.

In October 2023 the Health Board undertook a self-assessment review against the Speaking up Safely Framework to support our vision of being an organisation with a culture of openness and honesty. This work is being taken forward by the Director of Workforce and Organisational Development.

- GOVERNANCE AND RISK ISSUES

To support this work, a quality task and finish group was established, chaired by the previous Chief Executive. A stock-take was presented to the meeting in March 2023 and the decision made that sufficient progress had been made and the work could now be part of the Management Board going forward.  Progress to date is outlined below.

| Governance |  |  |
| --- | --- | --- |
| Action | Lead | Status |
| Identify clear leads in each service group triumvirate for patient experience, clinical outcomes and effectiveness, compliance and safety; | Service Groups | Completed: Work has been undertaken by the Director of Corporate Governance to ensure that service group structures are now broadly in-line with corporate structures and that these area implemented. Audit Wales review undertaken in October 2023, final report awaited. Revised Quality Framework approved in November, reflecting the Duty of Quality and to describing responsibilities for quality at service group and corporate level. |
| Service groups to have a standardised lists of quality areas to discuss in their quality governance structures throughout a 12-month cycle in a clear work programme; | Service Groups |  |
| Develop proposals for a central quality hub for approval by the Patient Safety Group; | Director of Nursing and Patient Experience | Completed: Quality Hub now in place supported by dedicated intranet pages: Quality, Safety & Improvement Hub - Home (sharepoint.com) |
| Clarity be set as to whom the governance function within the service groups (complaints, concerns, patient experience) reports and this be a standard approach for all service groups as line management is currently different across all. | Director of Nursing and Patient Experience/Director of Corporate Governance | Review of resources across the health board has taken place and is being benchmarked against foundation trusts in NHS England. Full report was taken to Management Board in July 2023. Following this, Welsh Risk Pool have agreed to undertake a review of our internal quality and safety structures, reporting to Quality Management Board by April 2024 |

| Quality |  |  |
| --- | --- | --- |
| Action | Lead | Status |
| First draft of quality strategy be shared with the Management Board for discussion | Director of Nursing and Patient Experience | Completed. Quality strategy was approved by the board in January 2023 and launched on 2nd March 2023. |
| Identify, through a multi-disciplinary approach with the service groups and based on evidence, three to five priorities to focus on improving | Director of Nursing and Patient Experience | Completed: HB-wide priorities for 2023/24 have been agreed and governance arrangements put in place through bi-monthly Quality Priorities Programme Board which reports to the Quality and Safety Group. Process for agreeing future priorities set out within the Quality Strategy |
| Tools and techniques be created for staff to measure staff and patient experience understand their services to identify problem areas | Director of Insight, Communications and Engagement/Director of Workforce and OD | All Wales staff survey results due in quarter 4 and this information will be used within a task and finish group to triangulate staff and patient experience |
| External facilitator be commissioned to develop the patient and stakeholder experience and engagement sub-group to expand areas of focus from ‘friends and family’ | Director of Nursing and Patient Experience/Director of Corporate Governance | An externally facilitated workshop has not been held, as we had been awaiting national work on patient engagement. However the Department for Insight Communication and Engagement provides regular reports to the Patient and Stakeholder Experience Group, which support triangulation of information from patient feedback and community engagement. |
| Develop a new style ‘complaint’ report | Director of Nursing and Patient Experience/Director of Corporate Governance | Completed and shared with the Quality and Safety Committee in July 2022. |
| A baseline review of quality resources within the health board to determine what should be corporate and what should be devolved to the service groups | Director of Nursing and Patient Experience/Director of Corporate Governance | Full report was taken to Management Board in July 2023. External review being conducted by Welsh Risk Pool, to report to Management Board by April 2024. |
| Development of a communications plan to set out the work being undertaken, why and expectations | Director of Insight, Communications and Engagement | Communication process in place to support quality priorities. Plan to support ‘Always on’ quality reporting to be developed by Director of Insight, Communication and Engagement. |

| Outcomes |  |  |
| --- | --- | --- |
| Action | Lead | Status |
| Mortality reduction plans across primary and secondary care | Executive Medical Director | The Deputy Medical Director has created a mortality dashboard for medical examiner to review, crude and condition speciality mortality ratio with a condition specific mortality dashboard. The data is reviewed monthly and triangulated to identify outliers and themes which are brought to attention of the clinical team and the Clinical Outcomes and Effectiveness and the Patient Safety groups. The clinical team undertake a thematic analysis for outliers from the medical examiner reviews to develop a quality improvement programme, the outcome of which is reported to the Clinical Outcomes and Effectiveness group and the Patient safety groups. This action is closed from a secondary care perspective, but work is required to develop a process within Primary Care and we are awaiting national guidance on this. |
| Management system to implement and monitor compliance with NICE (National Institute for Clinical Excellence) guidance | Executive Medical Director | Completed and shared with the Audit Committee in September 2022. |

| Creating a Learning Organisation |  |  |
| --- | --- | --- |
| Action | Lead | Status |
| Big Conversation process be undertaken to staff’s views on the culture of the organisation, staff experience and quality of services | Director of Workforce and OD | Completed: The programme had three phases: - Identifying the current perception of staff and stakeholders of where we are, what we want the future to look like, how we want to work and what we stand for; - Engagement on the potential and broad vision for a quality driven organisation and to get there; - Setting a compelling vision for our organisation. Phase one, two and three are now complete and the vision document has been launched across the organisation. |
| Creation of a quality improvement academy | Director of Nursing and Patient Experience | Completed: Revised training programme launched October 2023. QI Community of Practice established. Team based training being developed for roll out by March 2023. Quarterly reporting schedule established on QI Academy to Quality and Safety Group. |
| Development of a reward/recognition structure | Director of Workforce and OD | Completed: #Livingourvalues have been extended to include additional categories. |
| Establishment of quarterly conferences and monthly ‘scale and spread’ events | Director of Nursing and Patient Experience | Completed: Quarterly congress events held throughout 2023 and in the diary for 2024. |
| Create a list of those with IQT silver training | Director of Nursing and Patient Experience | Completed in September 2022 and database of staff to support quality improvement programmes in place. |

Good progress has been made in the majority of areas, with regular updates provided through Quality and Safety Group and its sub-groups. There remain some outstanding actions and the current actions will be reviewed upon receipt of the final Audit Wales Structured Assessment report.

- FINANCIAL IMPLICATIONS

Additional investment sought through the annual planning process to support the functions of the quality hub, including

- Continuation funding for the Digital Nurse role and project support for the role out of the AMAT audit software

- Patient story teller role to support increased opportunities for patient engagement within our quality systems

- Development of a ‘quality internship’ role for clinical leaders from quality ‘hot spot’ areas

- RECOMMENDATION

Members are asked to:

- NOTE the progress against the actions to develop a quality management system and that this work will now been overseen by the Management Board.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Quality, safety and experience should be the core components of all that the health board does as it is here first and foremost for patients. Having a robust quality management system will ensure that a high-level of care is being provided times when people need it most. |  |  |  |
| Financial Implications |  |  |  |
| Request for infrastructure support for the Quality Hub included as part of annual planning discussions. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| Duty of Quality through the Quality and Engagement Act (Wales). |  |  |  |
| Staffing Implications |  |  |  |
| Additional staffing required to further develop Quality Hub. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| In order to develop the organisation to be a sustainable one for the longer-term, a quality management system is critical in creating an expectation of the public that they deserve, and should receive, care that is of the highest quality. |  |  |  |
| Report History |  | Regular update to the Management Board, Quality and Safety Committee and Board. |  |
| Appendices |  | No appendices |  |