| Meeting Date | 18 January 2024 |  | Agenda Item |  |  | 2.3 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Board Effectiveness Action Plan |  |  |  |  |  |
| Report Authors | Len Cozens, Head of Compliance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Len Cozens, Head of Compliance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to provide an update on progress against the Board Effectiveness Action Plan. |  |  |  |  |  |
| Key Issues | - At the time of reporting, a total of 40 of the 42 actions contained within the 2022/23 Action Plan (Appendix 1) were identified as closed by the relevant lead executive. This represents an increase of 2 since the last report. It has not been possible to close the remaining 2 actions. - With regard to the four actions carried forward from the previous year’s plan (Appendix 2), three of these are now reported as closed. - Going forward, a comprehensive 2024 Action Plan has been developed based on the findings of the following reviews: - An external review of board effectiveness - Structured Assessment 2023 - Reporting on progress against the 2024 Action Plan will commence in the next cycle of reporting. This will also incorporate reporting on progress against any outstanding actions carried forward from previous years. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☐ | ☐ |  |
| Recommendations | Members are asked to: - NOTE progress made as detailed within the updated Board Effectiveness Action Plans included at Appendix 1 and Appendix 2 - AGREE any specific areas where members feel that further assurance is required, in order that these can be taken forward with the relevant Lead. - NOTE the approach taken to the production of the 2024 Action Plan, and AGREE to monitor progress against its delivery on behalf of the Board. |  |  |  |  |  |

BOARD EFFECTIVENESS ACTION PLAN

- INTRODUCTION

1.1	The purpose of this report is to provide an update on progress against the Board Effectiveness Action Plan.

2.	BACKGROUND AND CONTEXT

2.1	As part of the annual governance statement, the board is required to undertake an assessment of its effectiveness throughout the year in terms of governance and internal controls.

2.2	The findings of the 2021/22 self-assessment process were presented to the September 2022 meeting of the Board, along with an action plan (the 2022/23 Action Plan) for improvement. Progress against this action plan has been reported periodically to the Audit Committee thereafter, with the most recent position being received at the November 2023 meeting. This report provides a further update.

3.	STATUS UPDATE

3.1	Since the last meeting of the Committee, the 2022/23 Action Plan has again been circulated to all lead executives with a request that they provide updates on the actions assigned to them. A copy of the updated action plan has been included at Appendix 1 for information.

3.2	At the time of reporting, 40 of the 42 actions contained within the current plan were identified as closed by the relevant Lead Executive, and these have been highlighted green in the Appendix. The following two actions have been reported as closed since the last update to the Committee:

| No | Action | Progress |
| --- | --- | --- |
| 33 | Update SLA with NWSSP in respect of the provision of procurement services. | NWSSP Management have been approached by the Health Board, and on our behalf by the Head of Procurement, on a number of occasions in order to progress a review of the SLA for the provision of Procurement Services by NWSSP to SBU. The issue was raised again at the October 2023 National Heads of Procurement meeting. During this meeting, NWSSP confirmed that whilst such a review is to take place, there is a need for this work to align with the review of other SLAs and changes to service provision. As such, a date for completion has still not been set. Given this undertaking, coupled with the fact that further action to influence the timing of the SLA review is beyond the influence or control of the Health Board, it is felt this action should be closed at this point. |
| 39 | Develop a greater third party opinion of board effectiveness through engagement in interviews and surveys for a repertoire of key stakeholders in 2022. | It was agreed that for 2022/23, an external review of board effectiveness would be commissioned, which has now been completed. A comprehensive action plan has been developed based on the findings, which has been further strengthened by the inclusion of recommendations made by Audit Wales following their most recent Structured Assessment review. Management responses will now be added to the action plan, and it will be presented to the January 2024 meeting of the Audit Committee. Delivery against the plan will now be monitored by the Audit Committee as part of normal business. |

3.3	There are a further two instances where it has not been possible to close actions within the original target dates. These are highlighted red in the Action Plan.

3.4	In addition to the above, four ongoing actions were carried over from the previous year’s plan. Three of these have now been completed, with positive progress reported in respect of the fourth. An update has been included at Appendix 2 for information.

4.	BOARD EFFECTIVENESS ACTION PLAN 2024

4.1	It was agreed that for 2022/23, an external review of board effectiveness would be commissioned, to compare the results with those of the previous internal processes, as well as to set come robust recommendations to take the board forward.

4.2	Deloitte were commissioned to undertake the review, with work taking place during May and June 2023. It comprised a combination of interviews with board members, senior staff, service groups and external stakeholders, a survey, documentation review and meeting observations. The initial feedback was shared with the board in July 2023 and the draft report received for comments in August 2023. Feedback was incorporated and included in the final version.

4.3	A comprehensive 2024 Action Plan has been developed based on the findings of the report, which has been further strengthened by the inclusion of recommendations made by Audit Wales following their most recent Structured Assessment review.

4.4	Reporting on progress against the 2024 Action Plan will commence in the next cycle of reporting.  This will also incorporate reporting on progress against any outstanding actions carried forward from previous years.

5. FINANCIAL IMPLICATIONS

5.1	There are no direct financial implications arising from the recommendations in this report.

6.	RECOMMENDATIONS

6.1	Members are asked to:

- NOTE progress made as detailed within the updated Board Effectiveness Action Plans included at Appendix 1 and Appendix 2

- AGREE any specific areas where members feel that further assurance is required, in order that these can be taken forward with the relevant Lead.

- NOTE the approach taken to the production of the 2024 Action Plan, and AGREE to monitor progress against its delivery on behalf of the Board.

| Governance and Assurance |  |  |  |  |
| --- | --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |  |
|  | Partnerships for Improving Health and Wellbeing |  |  | ☐ |
|  | Co-Production and Health Literacy |  |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |  |
|  | Best Value Outcomes and High Quality Care |  |  | ☐ |
|  | Partnerships for Care |  |  | ☐ |
|  | Excellent Staff |  |  | ☐ |
|  | Digitally Enabled Care |  |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  |  | ☐ |
| Health and Care Standards |  |  |  |  |
| (please choose) | Staying Healthy |  |  | ☐ |
|  | Safe Care |  |  | ☐ |
|  | Effective Care |  |  | ☐ |
|  | Dignified Care |  |  | ☐ |
|  | Timely Care |  |  | ☐ |
|  | Individual Care |  |  | ☐ |
|  | Staff and Resources |  |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |  |
| Ensuring the board carries out its business appropriately and aligned with standing orders is a key factor in the quality, safety and experience of patients receiving care. |  |  |  |  |
| Financial Implications |  |  |  |  |
| There are no direct financial implications arising from this paper |  |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |  |
| There are no direct legal implications arising from this paper |  |  |  |  |
| Staffing Implications |  |  |  |  |
| There are no direct staffing implications arising from this paper |  |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |  |
| The development of the board will provide a robust and sustainable organisation to support the communities it services. |  |  |  |  |
| Report History |  | N/A |  |  |
| Appendices |  | Appendix 1: Appendix 2: | Board Effectiveness Action Plan 2022/23 Board Effectiveness Action Plan 2021/22 Carried Over Actions |  |