[image: image4.png]Bwrdd lechyd Prifysgol
Bae Abertawe

Swansea Bay University
Health Board



   SHAPE  \* MERGEFORMAT 


  [image: image3.jpg]



	Meeting Date
	18th January 2024
	Agenda Item
	5.4

	Report Title
	Annual Accounts Update and Closure Plan 2023/24

	Report Author
	Alison McLennan, Assistant Director of Finance (Accounting & Governance)

	Report Sponsor
	Darren Griffiths, Executive Director of Finance and Performance. Acting Deputy Chief Executive

	Presented by
	Alison McLennan, Assistant Director of Finance (Accounting & Governance) 

	Freedom of Information 
	Open 

	Purpose of the Report
	To inform the Audit Committee of the annual accounts timetable and closure plans for the financial year ending 31st March 2024. 


	Key Issues


	Welsh Government issued the draft manual for accounts on 14th December 2023 which will be discussed by the All Wales Technical Accounting Group at its meeting on the 24th January 2024.
The draft manual for accounts requires draft accounts to be submitted to Welsh Government by midday on 3rd May 2024. The date for audited accounts has yet to be agreed with Audit Wales and so the provisional date of midday on 31st July 2024 has been included in the draft manual. It is likely that this extension from the typical mid-June deadline will be required by the Auditor General for Wales due to a revision of auditing standard ISA315, as was the situation for the 2022/23 process. This has been estimated to be the 31st July 2024 in the draft manual for accounts.
Interim audit work has not yet commenced due to resource issues at Audit Wales and the health board has not been able to confirm with Audit Wales a timescale for the interim audit work, although they have confirmed they intend to undertake an interim audit.
It is intended that the detailed closure plan for the year end accounts will be shared with Audit Wales by mid-February 2024 as well as across the Finance Directorate and with all other departments providing information to the accounts closure process.

Several Teams meetings will be arranged to cover the whole Finance function during February and March 2024 to go through the detailed year end closure plan and associated guidance.

There are, however, some risks to the accounts closedown process and these are as follows: -
· The ability of clinical staff to undertake physical stock counts due operational pressures on the services. 

· The ability to obtain timely information from the NHS Pensions Agency with regards to the details of clinical staff who have taken up the scheme pays option implemented by Welsh Government as a solution to the Pensions Tax issue for NHS staff.
· The impact of staff and role changes in the Finance team as a result of the implementation of the new Finance team structure.  



	Specific Action Required 

(please ( one only)
	Information
	Discussion
	Assurance
	Approval

	
	
	
	
	√

	Recommendations


	Members are asked to:
· APPROVE the year-end accounts timetable and closure plan


ANNUAL ACCOUNTS UPDATE AND CLOSURE PLAN 2023/24
1. INTRODUCTION
1.1. In order to ensure that the annual accounts for the health board for the 2023/24 financial year are submitted in accordance with the deadline issued by Welsh Government, it is necessary to put in place a detailed year-end timetable and associated guidance. This paper provides an update to the Committee on the annual accounts timetable and the closure plans being put in place to ensure that the accounts submission deadline is achieved.
2. BACKGROUND
2.1
The Welsh Government (WG) issued the draft manual for accounts and the draft accounts proforma statements on 14th December 2023. Both the draft manual and the accounts proforma statements will be discussed in detail by the all Wales Technical Accounting Group at its meeting on 24th January 2024.
2.2

To assist in ensuring a smooth year-end closedown, activities have already commenced within the health board and on an all Wales basis. These activities include an interim agreement of inter NHS debtor/creditor and income/expenditure balances across NHS Wales (excluding Welsh Government) as at month 9 which will be  completed by 19th January 2024. For Welsh Government, the agreement of balances exercise has already been undertaken at Month 7. A further informal process is planned to take place as at the end of January for Month 9 with inter NHS debtor/creditor statements being issued across NHS Wales in order to try to resolve any disagreements before the end of the financial year.  
2.3 
Due to resourcing issues at Audit Wales, the interim audit which normally commences at the beginning of January has not yet commenced. At this stage the health board has been unable to obtain any indication from Audit Wales as to when the interim audit will commence and what work Audit Wales intend to undertake. This is a concern for the Finance team as if this work does not commence until February 2022, it may be difficult to accommodate this work at the same time as undertaking detailed preparation work for year-end. 
2.4  
Work has commenced on the detailed closure plan for the annual accounts and it is intended that that this will be shared with Audit Wales by mid February 2024. The timetable and closure plan will also be sent to all Finance staff and those departments providing information to support the accounts closedown process, together with associated guidance notes. Several Teams meetings will be arranged with the whole Finance function during February and March 2024, to go through the closedown process and guidance in detail. 
2.5 
The key year-end timetable dates are detailed in the table below which include the WG deadlines prescribed in the draft manual for accounts, with the key dates agreed with colleagues across Finance and with Shared Services being based on the manual for accounts submission dates.
2.6 The draft accounts for 2023/24 are to be submitted by noon on Friday 3rd  May 2024. The draft manual for accounts has the date of 31st July for submission of audited accounts (the same as in 2022/23). The health board understands that Audit Wales will continue to be subject to a revision of auditing standard ISA315 during 2023/24 which requires additional testing. The impact of this revision as in 2022/23 will impact on auditing deadlines. A date of 31st July 2024 for completion of audited accounts will result in a small number of Finance staff being tied up on the year-end accounts for 2023/24 for the first 4 months of 2024/25 which may prove problematical.
	Annual Accounts Task
	Date for Completion

	Issue debtor balances to other NHS Wales bodies
	 4th April 2024

	Sign off date for agreement of NHS Wales debtors and creditors
	 9th April 2024

	Finalise Health Board outturn financial position
	11th April 2024

	Close health board old year financial ledger
	12th April 2024

	Issue income transactions to other NHS Wales bodies
	11th April 2024

	Sign off date for agreement of NHS Wales income and  expenditure
	17th April 2024

	Draft accounts available for senior finance team review
	25th April 2024 

	Submission of draft accounts 
	3rd May 2024 (noon)

	Submission of audited accounts 
	31st July 2024 (noon - tbc)


3. GOVERNANCE AND RISK ISSUES
3.1
There are a small number of risk and governance issues surrounding the completion of the annual accounts which are detailed below together with the mitigating actions being taken to minimise the risk to the accounts completion process.
3.2 
The first key risk relates to the availability of clinical staff to undertake stock counts in the event of significant operational pressures. 
3.3 The second issue relates to the availability of information from the NHS Pensions Agency for staff who have taken up the option of Scheme Pays through NHS Pensions as allowed for under the Welsh Government scheme as a solution to pension tax issues. This was received late in April 2023 or the 2022/23 financial year, and could cause delays again in closing the health Board’s financial ledger, reducing the time available to complete accounts notes which cannot begin until the ledger has closed.
3.4 Following the introduction of the new IFRS 16 Leasing standard on 2022/23, UK Treasury has issued guidance for implementation on 2023/24 to update the historical approach to PFI liability measurement. This only impacts the Neath Port Talbot PFI contract and work will be undertaken in January and February to apply the changes to the existing PFI accounting model.
3.5 A further risk to be managed through the accounts process is the impact of the Finance Department restructure. Due to retirement in July 2023 of Andrew Biston as Assistant Director of Finance, and departure of his replacement Nia Morgan, the accounts closedown process will be managed by Alison McLennan, the replacement Assistant Director of Finance with the accounts preparation being led by Claire Jenkins, Head of Accounting & Governance. A number of Finance staff will be completing accounts notes in their new roles for the first time and full training and support will be provided to those staff. 
3.6 Audit Wales have confirmed their team leader appointed to lead the Audit in 2022/23 will also lead the Audit process for 2023/24 which is pleasing to note for consistency purposes. 
3.7 As was the case in previous years, for the 2022/23 accounts audit, direct ledger access and access to the health board’s Qlikview reporting tool will be provided to Audit Wales staff. This access has been agreed by all Welsh health bodies.
4. FINANCIAL IMPLICATIONS

4.1 There are no financial implications arising from this report. 
5. RECOMMENDATIONS
Members are asked to:

•
APPROVE the year-end accounts timetable and closure plan
	Governance and Assurance



	Link to Enabling Objectives

(please choose)
	Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities

	
	Partnerships for Improving Health and Wellbeing
	☐

	
	Co-Production and Health Literacy
	☐

	
	Digitally Enabled Health and Wellbeing
	☐

	
	Deliver better care through excellent health and care services achieving the outcomes that matter most to people 

	
	Best Value Outcomes and High Quality Care
	☒

	
	Partnerships for Care
	☐

	
	Excellent Staff
	☒

	
	Digitally Enabled Care
	☐

	
	Outstanding Research, Innovation, Education and Learning
	☐

	Health and Care Standards

	(please choose)
	Staying Healthy
	☒

	
	Safe Care
	☒

	
	Effective  Care
	☒

	
	Dignified Care
	☒

	
	Timely Care
	☒

	
	Individual Care
	☒

	
	Staff and Resources
	☒

	Quality, Safety and Patient Experience

	There are no direct quality, safety and patient experience issues associated with this report.


	Financial Implications

	There are no direct financial implications associated with this report.


	Legal Implications (including equality and diversity assessment)

	There are no direct legal implications associated with this report.    



	Staffing Implications

	The annual accounts preparation process is an intense period for Finance staff and as in previous years in order to ensure that the accounts are completed in accordance with the deadline there may be a requirement for staff to work overtime and/or over the Easter bank holidays.    


	Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015)

	None 


	Report History
	This is an annual report to the Audit Committee. The previous report was presented to Audit Committee in January 2023.

	Appendices
	There are no appendices to this report.


2
Audit Committee – Thursday, 18th January 2024 


[image: image1.jpg]


