| Meeting Date | 15 January 2026 |  | Agenda Item |  |  | 2.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Audit Committee |  |  |  |  |  |
| Report Title | Audit Tracker – Status of Agreed Action |  |  |  |  |  |
| Report Author | Len Cozens, Head of Compliance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Len Cozens, Head of Compliance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to provide the Committee with an update on performance in the delivery of actions agreed as a result of the findings of audit reviews undertaken by NWSSP Audit & Assurance and Audit Wales. The report also provides an update on the AMaT system and the plan to transition to using the system in 2026/2027 for the monitoring and reporting of all audit actions. |  |  |  |  |  |
| Key Issues | This report includes all updates entered onto the Tracker since the last report, up to and including the 12/12/2025. Audit Wales There are currently 13 actions overdue, which represents a decrease of 5 when compared to the last report. A total of 1 new action became overdue during the reporting period; however, this has been more than offset by the closure of other actions which had previously been reported as overdue. In total, 9 actions were closed during the reporting period. NWSSP A&A There are currently 87 actions overdue, which represents a decrease of 2 when compared to the last report. A total of 19 new actions became overdue during the reporting period, however, this figure has been more than offset by the closure of other actions which had previously been reported as overdue. A total of 47 actions were closed during the period. AMaT All Audit Wales open actions have been added to the systems and all final NWSSP reports produced in 2024/25 and 2025/26 have been entered on the system. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - CONSIDER the current position of the Audit Tracker and the status of the agreed actions therein. - CONSIDER the update on progress to the AMaT system. - AGREE any specific areas where the Committee feel that further assurance is required in order that these may be addressed with the relevant Lead Director(s). |  |  |  |  |  |

AUDIT TRACKER AND

STATUS OF AGREED ACTIONS

- INTRODUCTION

  - The purpose of this report is to provide the Committee with an update on performance in the delivery of actions agreed as a result of the findings of audit reviews undertaken by NWSSP Audit & Assurance and Audit Wales.

  - The report also provides an update on the AMaT system and the plan to transition to using the system in 2026/2027 for the monitoring and reporting of all audit actions.

- BACKGROUND AND CONTEXT

2.1	The Audit Committee receives and considers reports as part of normal business, which provide information and assurance in respect of:

- The delivery of Audit Plans;

- Receipt of draft and final reports; and

- Health Board management responses to the findings contained therein

2.2	This report is intended to provide assurance in respect of performance in implementing agreed actions across all reports received from both NWSSP Audit & Assurance, and Audit Wales.

2.3	Action plans in respect of all final audit reports are available on the Finance Portal through SharePoint for Directors and managers to access and update throughout the year, with the deadlines for the reporting periods to the Audit Committee clearly set out within the file set up. In addition, the Head of Compliance has produced and distributed guidance notes to assist users in the review and update of the Tracker.

2.4	It should be noted that the charts and tables within this report relate to all reports where outstanding actions remain, regardless of their age. When all actions within a given report are marked closed, the report is archived and will no longer be included as part of this update.

2.5	Where actions or findings have been superseded by the content of later reports, then the original has been closed and does not form part of the following.

3.	STATUS UPDATE – AUDIT WALES REPORTS

3.1	The figure overleaf sets out the current position in respect of performance in implementing agreed actions stemming from Audit Wales findings, when measured against the original deadlines agreed by management at the time the reports were finalised.

Fig 1: Audit Wales Reports

3.2	Just 1 new action became overdue during the reporting period, relating to the 2024 Structured Assessment. The total number of overdue actions currently stands at 13.

3.3	A summary of all overdue Audit Wales actions is set out in the table below, with a more detailed breakdown included at Appendix A for information.

| Report Title | Number of Overdue Actions |  |  |
| --- | --- | --- | --- |
|  | High Priority | Medium Priority | Other |
| Lead: Chief Operating Officer | 0 | 0 | 4 |
| Primary Care Follow-Up | - | - | 3 |
| Operational Governance COO | - | - | 1 |
| Lead: Director of Corp. Gov. | 1 | 0 | 7 |
| Quality Governance Arrangements | - | - | 1 |
| Operational Governance DoCG | - | - | 5 |
| Structured Assessment 2024 | - | - | 1 |
| Exec Lead: Director of Digital | 0 | 0 | 1 |
| Operational Governance DoD | - | - | 1 |
| Lead: Director of Finance & Perf. | 0 | 0 | 1 |
| Structured Assessment 2022 | - | - | 1 |
| Total | 0 | 0 | 13 |

3.4	Where agreed actions have become overdue, lead Directors and/or their teams are asked to provide targets/milestones for completion or further update as part of their progress reporting. These are included in the narrative update provided at Appendix A for information.

3.5	A total of 9 actions were closed during the reporting period. A table detailing all closed actions, including any comments made by the lead Directors or their teams in closing them, can be found at Appendix B. In the instances highlighted below, changes to circumstances since the audit review have meant that it is not possible to deliver the actions as stated in the original responses. The foregoing notwithstanding, management feel it is reasonable to close these actions at this time given the current position and all other circumstances:

Follow Up Outpatient Services

Agreed Action

The HB acknowledges that further work is required in this area to ensure clinical risks are understood and reported appropriately. We currently report into QS committee on the eye care measures targets showing by sub speciality the follow up waits for patients. The main system we use for recording harm is Datix and currently clinical staff record on Datix any incidents that they feel that the delay in being seen resulted in harm to the patient. These are investigated and depending on outcome of the investigation actions taken. We plan to review as part of the follow up WL project the areas with the longest delays and as part of this work will scope up how we are able to report on outcome/harm potentially in a similar way to the eye care measures into management board and into QS committee.

Comments On Closure

Incidents of harm are logged into the DATIX system by Service Groups. All patient safety incidents, including those identified to be the result of delayed follow-ups, are assessed by Service Groups to identify the severity of harm as a result of healthcare. The Service Group Directors and Quality & Patient Safety Team engages with senior clinicians to conduct rapid harm reviews to assess potential harm, and to determine necessary actions, including the scope and parameters of the proportionality of an investigation. If the rapid review determines the health board has caused or contributed to the long term/permanent severe harm or death of a patient, the incident will be investigated by the corporate Patient Safety Incident Investigation Team. SBU have reported 3 Nationally Reportable Incidents to NHS Wales Performance & Improvement since July 2024 relating to delayed FU’s. The Health Board conducts thorough harm reviews for all incidents, from which themes and trends can be assessed and acted upon, and to determine whether escalation is appropriate. NRIs are reported to the in-Committee sessions of the Quality & Safety Committee meetings as part of the Nationally Reported Incidents / Early Warning Notifications report.

Equality Impact Assessments

Agreed Action

The newly formed Directorate of Insight, Communications and Engagement is planning to appoint a Head of Equality, Diversity and Inclusion in Quarter 3 of 2022-23. It is also proposing the establishment of a Strategic Equality Group to oversee all EDI matters, including the EIA process.

Comments On Closure

The Health Board’s financial position has resulted in proposals to strengthen the engagement function not being taken forward at this time. The matter will be progressed as part of the Organised for Success programme where a key focus will be on prioritisation. In terms of the EIA, this has now been evolved into an Integrated Impact Assessment. The IIA approach was used for the urgent and temporary closure of the Gorseinon inpatient ward.

4.	STATUS UPDATE – NWSSP AUDIT & ASSURANCE REPORTS

4.1	The following sets out the current position in respect of performance in implementing agreed actions stemming from NWSSP Audit & Assurance findings, when measured against the original deadlines agreed by management at the time the reports were finalised.

Fig 2: NWSSP Audit & Assurance Reports

4.2	A total of 19 new actions became overdue during the reporting period. However, this figure has been more than offset by the closure of other previously overdue actions. The total overall number of overdue actions has decreased by 2. The 19 new overdue actions are spread across a number of reports, but can be primarily attributed to the following:

- AMSR – Benefits Realisation			6

- Estate Condition Governance 			3

- Learning – Incidents & Concerns		5

4.3	A summary table of all overdue actions is set out at Appendix C, with a more detailed breakdown included at Appendix D for information.

4.4	Where agreed actions have become overdue, lead directors and/or their teams are asked to provide targets/milestones for completion or further update as part of their progress reporting. These are included in the detailed narrative update provided at Appendix D for information.

4.5	A total of 47 actions have been closed during the reporting period. A table detailing all of these, including any comments made by the lead director(s) or their teams in doing so, is included at Appendix E.

5.	THEMATIC ASSESSMENT

5.1	This report has historically presented the Committee with details on overdue actions sorted in a variety of ways, for example:

- Thematically by key finding priority

- Thematically by Director portfolio

- Individually by report

5.2	At the request of committee members, a further thematic assessment of overdue actions has been carried out, utilising the eight areas of Health Board activity used by NWSSP Audit & Assurance Services to structure their strategic and one-year operational plans. The results of this assessment have been included at Appendix F.

6.	AMaT

A decision has been made to use AMaT for the recording, monitoring and reporting of all audit actions.  Meetings have been held with members of staff of the Director of Corporate Governance’s team and other Health Boards to understand how the system can be utilised to its full potential and any limitations.

As at 19th December all open Audit Wales actions have been entered on AMaT.  In relation to the NWSSP reports all final NWSSP reports produced in 2024/25 and 2025/26 have been entered on the system.   Any new, final, Audit Wales of NWSSP report will be entered onto AMaT.

During Q4 of 2025/26 the current system and AMaT will run in parallel as the AMaT system will be tested and staff will support the Executive Directors to transition to AMaT in Q1 of 2026/27.

7. FINANCIAL IMPLICATIONS

7.1	There are no direct financial implications arising from this report.

8.	RECOMMENDATIONS

7.1	Members are asked to:

- CONSIDER the current position of the Audit Tracker and the status of the agreed actions therein.

- AGREE any specific areas where the Committee feel that further assurance is required in order that these may be addressed with the relevant Lead Director(s).

| Governance and Assurance |  |  |  |  |
| --- | --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |  |
|  | Partnerships for Improving Health and Wellbeing |  |  | ☐ |
|  | Co-Production and Health Literacy |  |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |  |
|  | Best Value Outcomes and High Quality Care |  |  | ☐ |
|  | Partnerships for Care |  |  | ☐ |
|  | Excellent Staff |  |  | ☐ |
|  | Digitally Enabled Care |  |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  |  | ☐ |
| Health and Care Standards |  |  |  |  |
| (please choose) | Staying Healthy |  |  | ☒ |
|  | Safe Care |  |  | ☒ |
|  | Effective Care |  |  | ☒ |
|  | Dignified Care |  |  | ☒ |
|  | Timely Care |  |  | ☒ |
|  | Individual Care |  |  | ☒ |
|  | Staff and Resources |  |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |  |
| Outstanding audit recommendations may affect quality, safety and patient experience. It is essential that where audit recommendations are made, they are acted upon with leadership from the relevant Director. Reports addressing Q&S issues are discussed in more detail in the Q&S Committee. |  |  |  |  |
| Financial Implications |  |  |  |  |
| Whilst there are no direct financial implications that need to be highlighted in this report, such may arise from individual audit reports or recommendations made. |  |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |  |
| Failure to address audit actions relating to areas such as staff and/or patient safety, or legislative compliance, may lead to action being taken against the health board. |  |  |  |  |
| Staffing Implications |  |  |  |  |
| Whilst there are no direct staffing implications that need to be highlighted in this report, there may be issues arising from individual audit reports or recommendations made which have staffing implications for the Health Board. |  |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |  |
| A robust Governance Work Programme will assist the Board in assessing risk and gathering assurance across all corporate objectives, which span the five ways of working, and the wellbeing goals identified in the Act. |  |  |  |  |
| Report History |  | The Committee receives this report as a minimum three times a year. |  |  |
| Appendices |  | Appendix A | Overdue Actions – Audit Wales |  |
|  |  | Appendix B | Closed Actions – Audit Wales |  |
|  |  | Appendix C | Overdue Actions – NWSSP A&A (Summary) |  |
|  |  | Appendix D | Overdue Actions – NWSSP A&A (Detail) |  |
|  |  | Appendix E | Closed Actions – NWSSP A&A |  |
|  |  | Appendix F | Thematic Assessment |  |