| Meeting Date | 15 January 2026 |  | Agenda Item |  |  | 5.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Audit Committee |  |  |  |  |  |
| Report Title | Annual Accounts Update and Closure Plan 2025/26 |  |  |  |  |  |
| Report Author | Alison McLennan, Assistant Director of Finance (Accounting & Governance) |  |  |  |  |  |
| Report Sponsor | Darren Griffiths, Director of Finance and Performance |  |  |  |  |  |
| Presented by | Alison McLennan, Assistant Director of Finance (Accounting & Governance) |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | To inform the Audit Committee of the annual accounts timetable and closure plans for the financial year ending 31 March 2026. |  |  |  |  |  |
| Key Issues | Welsh Government issued the draft manual for accounts on 19 December 2025 which will be discussed by the All-Wales Technical Accounting Group at its meeting on the 28 January 2026. The draft manual for accounts requires draft accounts to be submitted to Welsh Government by midday on 1 May 2026. The date for audited accounts has been set at midday on 30 June 2026 in the draft manual, which is consistent with the deadline set for the 24-25 accounts. Interim audit work has not yet commenced, but Audit Wales have confirmed their intention to undertake an interim audit beginning on the 12 January 2026, with preparatory work already underway. It is intended that the detailed closure plan for the year end accounts will be shared with Audit Wales by mid-February 2026 as well as across the Finance Directorate and with all other departments providing information to the accounts closure process. Several Teams meetings will be arranged to cover the whole Finance function during February and March 2026 to go through the detailed year end closure plan and associated guidance, and ensure all staff are comfortable with tasks assigned and deadlines set. There is the regular risk to the accounts closedown process to highlight as follows: The impact on staff in the Finance team as they endeavour to complete the year end process alongside maintaining their routine work. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☐ | ☒ |  |
| Recommendations | Members are asked to: - APPROVE the year-end accounts timetable and closure plan |  |  |  |  |  |

ANNUAL ACCOUNTS UPDATE AND CLOSURE PLAN 2025/26

- INTRODUCTION

1.1	In order to ensure that the annual accounts for the health board for the 2025/26 financial year are submitted in accordance with the deadlines issued by Welsh Government, it is necessary to put in place a detailed year-end timetable and associated guidance. This paper provides an update to the Committee on the annual accounts timetable and the closure plans being put in place to ensure that the accounts submission deadline is achieved.

- BACKGROUND

  - The Welsh Government issued the draft manual for accounts and the draft accounts proforma statements on 19th December 2025. Both the draft manual and the accounts proforma statements will be discussed in detail by the all Wales Technical Accounting Group (TAG) at its meeting on 28th January 2026.

  - To assist in ensuring a smooth year-end closedown, activities have already commenced within the Health Board and on an all Wales basis. These activities include an interim agreement of inter NHS debtor/creditor and income/expenditure balances across NHS Wales (excluding Welsh Government) as at month 9, which will be completed by 23 January 2026. For Welsh Government, the agreement of balances exercise has already been undertaken at Month 6. A further informal process is planned to take place as at the end of January for Month 9 with inter NHS debtor/creditor statements being issued across NHS Wales in order to try to resolve any disagreements before the end of the financial year.  It will also be proposed at the TAG group on 28th January 2026, that all organisations pay all NHS invoices immediately to facilitate and reduce the agreement of any outstanding balances at year end, and to minimise any organisational cash shortages.

  - An interim audit has not yet commenced, but Audit Wales have confirmed their intention to undertake an interim audit beginning on the 12 January 2026. Preparatory work has already commenced, and Audit Wales will do as much as possible in the background to enable staff to plan and prepare for year end.

  - Work has commenced on the detailed closure plan for the annual accounts and it is intended that that this will be shared with Audit Wales by mid-February 2026. The timetable and closure plan will also be sent to all Finance staff and those departments providing information to support the accounts closedown process, together with associated guidance notes. Several Teams meetings will be arranged with the whole Finance function during February and March 2026, to go through the closedown process and guidance in detail.

  - The key year-end timetable dates are detailed in the table below which include the Welsh Government deadlines prescribed in the draft manual for accounts, with the key dates agreed with colleagues across Finance and with Shared Services being based on the manual for accounts submission dates.

  - The draft accounts for 2025/26 are to be submitted by noon on Friday 1 May 2026. The draft manual for accounts has the date of 30 June 2026 for submission of audited accounts (in line with the deadline set for the 2024/25 accounts). A date of 30 June for completion of audited accounts will result in a small number of Finance staff being tied up on the year-end accounts for 2025/26 for the first 3-4 months of 2026-27 which may be an issue for the first few months of the new financial year.

| Annual Accounts Task | Date for Completion |
| --- | --- |
| Issue debtor balances to other NHS Wales bodies | 2 April 2026 |
| Sign off date for agreement of NHS Wales debtors and creditors | 10 April 2026 |
| Finalise Health Board outturn financial position | 9 April 2026 |
| Close health board old year financial ledger | 13 April 2026 |
| Issue income transactions to other NHS Wales bodies | 13 April 2026 |
| Sign off date for agreement of NHS Wales income and expenditure | 20 April 2026 |
| Draft accounts available for senior finance team review | 27 April 2026 |
| Submission of draft accounts | 1 May 2026 (noon) |
| Submission of audited accounts | 30 June 2026 (noon) |

- GOVERNANCE AND RISK ISSUES

  - There are a small number of risk and governance issues surrounding the completion of the annual accounts which are detailed below together with the mitigating actions being taken to minimise the risk to the accounts completion process.

  - A risk to be managed through the accounts process is the impact on the Finance Department of the additional workload generated by the year end process. A number of Finance staff will be completing accounts notes alongside maintaining their regular roles, and many will be working on the accounts for the first 3-4 months of 2026-27.

  - Audit Wales have confirmed their team leader appointed to lead the Audit for 2023-24 and 2024-25 will also lead the Audit process for 2025-26 which is pleasing to note for consistency purposes.

  - Audit Wales will have direct ledger access and access to the Health Board’s Qliksense reporting tool.

- FINANCIAL IMPLICATIONS

4.1 	There are no direct financial implications associated with this report to the Audit Committee.

- RECOMMENDATION

  - Members are asked to:

APPROVE the year-end accounts timetable and closure plan

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| There are no direct quality, safety and patient experience issues associated with this report. |  |  |  |
| Financial Implications |  |  |  |
| There are no direct financial implications associated with this report. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| There are no direct legal implications associated with this report |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| None |  |  |  |
| Report History |  | This is an annual report to the Audit Committee. The previous report was presented to Audit Committee in January 2025. |  |
| Appendices |  | There are no appendices to this report. |  |