| Meeting Date | 20 March 2025 |  | Agenda Item |  |  | 2.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Audit Committee |  |  |  |  |  |
| Report Title | Audit Tracker – Status of Agreed Action |  |  |  |  |  |
| Report Author | Len Cozens, Head of Compliance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Len Cozens, Head of Compliance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to provide the Audit Committee with an update regarding performance in the delivery of actions agreed as a result of audit reviews (NWSSP Audit & Assurance and Audit Wales), and the resulting recommendations. |  |  |  |  |  |
| Key Issues | This report includes all updates entered onto the Tracker since the last report, up to and including the 30th October 2024. Audit Wales There are currently 24 actions overdue, which represents an increase of 11 when compared to the last report. A total of 12 new actions became overdue during the reporting period, however, this figure has been partially offset by the closure of a separate action which had previously been reported as overdue. In total, 24 actions were closed during the reporting period. NWSSP A&A There are currently 99 actions overdue, which represents a decrease of 14 when compared to the last report. A total of 34 new actions became overdue during the reporting period, however, this figure has been partially offset by the closure of 48 other actions which had previously been reported as overdue. In total, 75 actions were closed during the reporting period. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☐ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the current position of the Audit Tracker and the status of the agreed actions therein. - AGREE any specific areas where the Committee feel that further assurance is required in order that these may be addressed with the relevant Lead Director(s). |  |  |  |  |  |

AUDIT TRACKER AND

STATUS OF AGREED ACTIONS

- INTRODUCTION

1.1	The purpose of this report is to provide the Audit Committee with an update regarding performance in the delivery of actions agreed as a result of the findings of audit reviews (NWSSP Audit & Assurance and Audit Wales), and the resulting recommendations.

- BACKGROUND AND CONTEXT

2.1	The Audit Committee receives and considers reports as part of normal business, which provide information and assurance in respect of:

- The delivery of Audit Plans;

- Receipt of draft and final reports; and

- Health Board management responses to recommendations contained therein

2.2	This report is intended to provide assurance in respect of performance in implementing agreed actions across all reports received from both NWSSP Audit & Assurance, and Audit Wales.

2.3	Action plans in respect of all final audit reports are available on the Finance Portal through SharePoint for Directors and managers to access and update throughout the year, with the deadlines for the reporting periods to the Audit Committee clearly set out within the file set up. In addition, the Head of Compliance has produced and distributed guidance notes to assist users in the review and update of the Tracker.

2.4	It should be noted that the charts and tables within this report relate to all reports where outstanding actions remain, regardless of their age. When all actions within a given report are marked closed, the report is archived, and will no longer be included as part of this update.

2.5	Where actions or recommendations have been superseded by the content of later reports, then the original has been closed and does not form part of the following.

3.	STATUS UPDATE – AUDIT WALES REPORTS

3.1	The figure overleaf sets out the current position in respect of performance in implementing agreed actions stemming from Audit Wales recommendations, when measured against the original deadlines agreed by management at the time the reports were finalised.

Fig 1: Audit Wales Reports

3.2	A total of 12 new actions became overdue during the reporting period, the vast majority of which relate to the Review of Operational Governance. The total number of overdue actions currently stands at 24.

3.3	A summary of all overdue Audit Wales actions is set out in the table below, with a more detailed breakdown included at Appendix A for information.

| Report Title | Number of Overdue Actions |  |  |
| --- | --- | --- | --- |
|  | High Priority | Medium Priority | Other |
| Lead: Chief Operating Officer | 0 | 0 | 5 |
| Primary Care Follow-Up | - | - | 3 |
| Operational Governance COO |  |  | 2 |
| Lead: Director of Corp. Gov. | 3 | 0 | 8 |
| Quality Governance Arrangements | - | - | 1 |
| Structured Assessment 2022 | - | - | 1 |
| Structured Assessment 2023 | 3 | - | - |
| Operational Governance DoCG | - | - | 6 |
| Exec Lead: Director of Digital | 0 | 0 | 2 |
| Operational Governance DoD | - | - | 2 |
| Exec Lead: Director of Workforce & OD | 0 | 0 | 2 |
| Workforce Planning Arrangements | - | - | 2 |
| Exec Lead: Director of ICE | 0 | 0 | 3 |
| Equality Impact Assessments | - | - | 3 |
| Lead: Director of Finance & Perf. | 0 | 0 | 1 |
| Structured Assessment 2022 | - | - | 1 |
| Total | 3 | 0 | 21 |

3.4	Where agreed actions have become overdue, lead Directors and/or their teams are asked to provide targets/milestones for completion or further update as part of their progress reporting. These are included in the narrative update provided at Appendix A for information.

3.5	A total of twenty-four actions were closed during the reporting period. Of these, one action relating to primary care performance reporting has been closed as it duplicates a recommendation made in a separate report. A second action relating to Cost Improvement Plan (CIP) processes has been closed due to a change in circumstances since the audit was completed. Detail on both of these actions has been included at Appendix F for information.

3.6	A table detailing all close actions, including any comments made by the lead Directors or their teams in closing them, can be found at Appendix B.

4.	STATUS UPDATE – NWSSP AUDIT & ASSURANCE REPORTS

4.1	The following sets out the current position in respect of performance in implementing agreed actions stemming from NWSSP Audit & Assurance recommendations, when measured against the original deadlines agreed by management at the time the reports were finalised.

Fig 2: NWSSP Audit & Assurance Reports

4.2	The following table represents the number of complete, in progress and overdue actions as a percentage of the total number of actions arising from the reports.

| Complete | In Progress | Overdue |
| --- | --- | --- |
| 50.8% | 30.8% | 18.4% |

4.3	A total of 34 new actions became overdue during the reporting period. However, this figure has been partially offset by the closure of 48 other previously overdue actions. The total overall number of overdue actions has therefore decreased by 14. The 34 new overdue actions are spread across a number of reports, but can be primarily attributed to the following:

- Primary Care Cluster Plans

- Records Management

- CAMHS Transition

- Risk Management & Assurance

4.4	Reporting against all 7 overdue actions relating to the audit of the Swansea Wellness Centre continues to be suspended due to the fact that this project has been paused, pending a review of its overall scope. Once this review has been completed and a way forward agreed, all actions will be revisited and addressed in the context of the revised arrangements.

4.5	With reference to the outstanding/overdue actions stemming from the 2020/21 review of discharge planning, these have now all be superseded by the findings of the 2024/25 review. A new action plan has now been created to monitor and report on progress against these.

4.6	A summary table of all overdue actions is set out at Appendix C, with a more detailed breakdown included at Appendix D for information.

4.7	Where agreed actions have become overdue, lead directors and/or their teams are asked to provide targets/milestones for completion or further update as part of their progress reporting. These are included in the detailed narrative update provided at Appendix D for information.

4.8	A total of 75 actions have been closed during the reporting period. In some instances, changes to circumstances since the audit review have meant that the action taken differs to that outlined in the original report. The foregoing notwithstanding, management feel it is reasonable to close these recommendations at this time given the action taken to date and all other circumstances. Details are included at Appendix F.

4.9	A table detailing all actions closed since the last report, including any comments made by the lead director(s) or their teams in doing so, is included at Appendix E.

5.	FINANCIAL IMPLICATIONS

5.1	There are no direct financial implications arising from this report.

6.	RECOMMENDATIONS

6.1	Members are asked to:

- NOTE the current position of the Audit Tracker and the status of the agreed actions therein.

- AGREE any specific areas where the Committee feel that further assurance is required in order that these may be addressed with the relevant Lead Executive(s).

| Governance and Assurance |  |  |  |  |
| --- | --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |  |
|  | Partnerships for Improving Health and Wellbeing |  |  | ☐ |
|  | Co-Production and Health Literacy |  |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |  |
|  | Best Value Outcomes and High Quality Care |  |  | ☐ |
|  | Partnerships for Care |  |  | ☐ |
|  | Excellent Staff |  |  | ☐ |
|  | Digitally Enabled Care |  |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  |  | ☐ |
| Health and Care Standards |  |  |  |  |
| (please choose) | Staying Healthy |  |  | ☒ |
|  | Safe Care |  |  | ☒ |
|  | Effective Care |  |  | ☒ |
|  | Dignified Care |  |  | ☒ |
|  | Timely Care |  |  | ☒ |
|  | Individual Care |  |  | ☒ |
|  | Staff and Resources |  |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |  |
| Outstanding audit recommendations may affect quality, safety and patient experience. It is essential that where audit recommendations are made, they are acted upon with leadership from the relevant Director. Reports addressing Q&S issues are discussed in more detail in the Q&S Committee. |  |  |  |  |
| Financial Implications |  |  |  |  |
| Whilst there are no direct financial implications that need to be highlighted in this report, such may arise from individual audit reports or recommendations made. |  |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |  |
| Failure to address audit recommendations relating to areas such as staff and/or patient safety, or legislative compliance, may lead to action being taken against the health board. |  |  |  |  |
| Staffing Implications |  |  |  |  |
| Whilst there are no direct staffing implications that need to be highlighted in this report, there may be issues arising from individual audit reports or recommendations made which have staffing implications for the Health Board. |  |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |  |
| A robust Governance Work Programme will assist the Board in assessing risk and gathering assurance across all corporate objectives, which span the five ways of working, and the wellbeing goals identified in the Act. |  |  |  |  |
| Report History |  | The Committee last received a report on this topic in July 2024 |  |  |
| Appendices |  | Appendix A | Overdue Actions – Audit Wales |  |
|  |  | Appendix B | Closed Actions – Audit Wales |  |
|  |  | Appendix C | Overdue Actions – NWSSP A&A (Summary) |  |
|  |  | Appendix D | Overdue Actions – NWSSP A&A (Detail) |  |
|  |  | Appendix E | Closed Actions – NWSSP A&A |  |
|  |  | Appendix F | Recommendations Closed with Alternate Actions |  |