Appendix 2

Board Effectiveness Action Plan

Outstanding Actions from Previous Years

| Quality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Progress Level Results |  | Criteria to Support this level The health board has a quality strategy and implementation framework, with clear quality priorities, that integrates into and drives our overall organisational strategy. A quality impact assessment process is in place and drives quality based decisions. The health board receives high quality intelligence and information through both soft and hard sources to provide assurance that services are safe, and takes account of patient experience, outcomes, and quality improvement. Information on quality is of high quality, with limited data quality issues, is well summarised to provide assurance around quality of care. |  |  |
| Lead Committee Quality & Safety Committee |  |  |  |  |
| No | Actions | Target Date | Lead Executive | Progress/Status |
| A | Development of a reward/recognition structure. | October 2022 | Director IC&E | March 2025: Aligned to the Health Board’s ten-year vision to become a high-quality organisation, the Culture, Organisational Development and Staff Experience Team have produced an Appreciation & Recognition Leadership Toolkit. As well as highlighting the importance of staff/team appreciation and recognition, the Toolkit gives direction to managers on how this can be achieved in a practical way, and includes detail on: - The One Bay Way Staff Awards - Long Service Recognition - Patient Choice Awards |
| B | A dashboard be developed which sets out the quality impacts of performance for patients. | August 2021 | Director of Finance Director of Nursing & Pat. Experience | March 2025: Phase 1 of the quality dashboard has now been launched. Development of Phase 2 of the dashboard is nearing completion. |

| Appraisal Process of Directors and Other Feedback |  |  |  |  |
| --- | --- | --- | --- | --- |
| Progress Level Maturity |  | Criteria to Support this level The board is recognised as adding value |  |  |
| Lead Committee Remuneration Committee |  |  |  |  |
| No | Actions | Target Date | Lead Executive | Progress/Status |
| C | Develop and agree a 360-appraisal process for Executive directors. | February 2023 | Director of Workforce & OD | March 2023: This action has been superseded by an action contained within the Board Effectiveness Action Plan 2024 (Action 31 refers). This action has therefore been closed. |