| Meeting Date | 16 May 2024 |  | Agenda Item |  |  | 2.3 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Audit Tracker and Status of Agreed Actions |  |  |  |  |  |
| Report Author | Len Cozens, Head of Compliance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Len Cozens, Head of Compliance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to provide the Audit Committee with an update regarding performance in the delivery of actions agreed as a result of the findings of audit reviews (NWSSP Audit & Assurance and Audit Wales), and the resulting recommendations. |  |  |  |  |  |
| Key Issues | This report includes all updates entered onto the Tracker since the last report, up to and including the 24th April 2024. Audit Wales There are currently 6 actions overdue, which represents no movement when compared to the last report. In total, 2 actions were closed during the reporting period, neither of which were overdue at the point of closure. NWSSP A&A There are currently 106 actions overdue, which represents a decrease of 4 when compared to the last report. A total of 13 new actions became overdue during the reporting period, however, this figure has been more than offset by the closure of 17 other actions which had previously been reported as overdue. In total, 31 actions were closed during the reporting period. The DECLO is reporting risk around the Teams ability to complete actions stemming from the audit of ALN, primarily as a result of the withdrawal of project support. Progress against outstanding Patient Discharge actions has been hampered by the departure of the Head of Nursing. Two of the three outstanding estates-based actions referenced in the last NWSSP Follow-Up Estates Assurance report have now been closed. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the current position of the Audit Tracker and the status of the agreed actions therein. - AGREE any specific areas where the Committee feel that further assurance is required in order that these may be addressed with the relevant Lead Executive(s). |  |  |  |  |  |

AUDIT TRACKER AND

STATUS OF AGREED ACTIONS

- INTRODUCTION

1.1	The purpose of this report is to provide the Audit Committee with an update regarding performance in the delivery of actions agreed as a result of the findings of audit reviews (NWSSP Audit & Assurance and Audit Wales), and the resulting recommendations.

- BACKGROUND AND CONTEXT

2.1	The Audit Committee receives and considers reports as part of normal business, which provide information and assurance in respect of:

- The delivery of Audit Plans;

- Receipt of draft and final reports; and

- Health Board management responses to recommendations contained therein

2.2	This report is intended to provide assurance in respect of performance in implementing agreed actions across all reports received from both NWSSP Audit & Assurance, and Audit Wales.

2.3	Action plans in respect of all final audit reports are available on the Finance Portal through SharePoint for executives and managers to access and update throughout the year. The deadlines for the reporting periods to the Audit Committee are clearly set out within the file set up, and guidance notes have been produced and distributed to assist users in the review and update of the Tracker.

2.4	It should be noted that the charts and tables within this report relate to all reports where outstanding recommendations remain, regardless of their age. When all recommendations within a given report are marked closed, the report is archived, and will no longer be included as part of this update.

2.5	Where recommendations have been superseded by the content of later reports, then the original recommendation has been closed and does not form part of the following.

3.	STATUS UPDATE – AUDIT WALES REPORTS

3.1	The following sets out the current position in respect of performance in implementing agreed actions stemming from Audit Wales recommendations, when measured against the original deadlines agreed by management at the time the reports were finalised.

Fig 1: Audit Wales Reports

3.2	No new actions became overdue during the reporting period. A total of two actions were closed, neither of which were overdue at the point of closure. Both of these actions related to the Structured Assessment 2022.

3.3	A summary of all overdue Audit Wales actions is set out in the table below, with a more detailed breakdown included at Appendix A for information.

| Report Title | Number of Overdue Actions |  |
| --- | --- | --- |
|  | High Priority | Other Priority |
| Exec Lead: Director of Corp. Gov. | 0 | 3 |
| Quality Governance Arrangements | - | 1 |
| Structured Assessment 2022 | - | 2 |
| Exec Lead: Director of ICE | 0 | 3 |
| Equality Impact Assessments | - | 3 |
| Total | 0 | 6 |

3.4	Where agreed actions have become overdue, lead executives and/or their teams are asked to provide targets/milestones for completion or further update as part of their progress reporting. These are included in the narrative update provided at Appendix A for information.

3.5	A further table detailing all actions closed since the last report, including any comments made by the lead executive or their teams in doing so, can be found at Appendix B.

4.	STATUS UPDATE – NWSSP AUDIT & ASSURANCE REPORTS

4.1	The following sets out the current position in respect of performance in implementing agreed actions stemming from NWSSP Audit & Assurance recommendations, when measured against the original deadlines agreed by management at the time the reports were finalised.

Fig 2: NWSSP Audit & Assurance Reports

4.2	A total of 13 new actions became overdue during the reporting period. However, this figure has been more than offset by the closure of 17 other previously overdue actions. The overall number of overdue actions has therefore decreased by 4.

4.3	The 13 new overdue actions are spread across a number of reports, as summarised below:

| Report Name | High Priority | Medium Priority | Low Priority |
| --- | --- | --- | --- |
| Continuing Care COO | - | 1 | - |
| Access to Cancer Services COO | - | 1 | - |
| Technical Resilience | - | 1 | - |
| Savings Programme | - | 6 | - |
| Sickness Absence Management | - | - | 2 |
| Commissioning LTA Contracts DoS | - | 1 | - |
| Health & Social Care RIF | - | 1 | - |
| Total | 0 | 11 | 2 |

4.4	As reported in the last update to the Committee in March 2024, the Head of Compliance had intended to undertake further work with the Head of Nursing (Optimising & Improving Patient Flow) with a view progressing overdue actions relating to Discharge Planning. However this did not prove possible following her subsequent departure from the Health Board. The Head of Compliance has now provided all relevant details to the Matron who has taken over this work, and will work with her to progress matters over the coming weeks.

4.5	The NWSSP Follow-Up Estates Assurance report which was presented to the last Committee meeting confirmed that nine of the 12 estates-based actions which were expected to have been addressed during the course of the 2023/24 financial year had been concluded as closed. The following three actions remained open at that time:

| Capital Systems Financial Safeguarding |  |
| --- | --- |
| 13 | No documented procedures in place for the management of Estates Stores. Formal procedures should be developed and implemented for the management of Estates stores (in accordance with SFIs). |
| 14 | Issues which reduced the effectiveness of intended controls, and SFI breaches were noted, including: - No annual stocktake at Morriston - Singleton stocktake not independently verified - ‘Not stock’ items on shelves at both stores, but not recorded on Planet FM Stores practices should be reviewed and enhanced in line with audit findings and SFI requirements. |
| Waste Management |  |
| 6 | A process of action tracking and reporting was not evidenced for Pre-Acceptance audit non-conformities. Recommendations / non-conformities arising from Pre-Acceptance audits should be monitored via the central tracker. Pre-Acceptance audit non-conformities, and progress towards actioning the same, should be reported to a relevant forum/s (e.g. Estates Board / Hospital Management Boards). |

As part of the update for this report, the Assistant Director of Estates has reported both of the above Capital Systems Financial Safeguarding actions as closed, with the revised procedure document having been approved by the Estates Board, and subsequently shared with NWSSP Audit & Assurance colleagues.

The Waste Management action currently remains open due to difficulties in appointing to a Technical Services position within the Department. This post has now be re-advertised as 12-month secondment opportunity.

4.6	As part of his update in respect of the Additional Learning Needs (ALN) audit, the Designated Education Clinical Lead Officer (DECLO) has confirmed that the temporary project support to the ALN work has now been withdrawn. Whilst funding has been identified to recruit further support, the time this will take is likely to have an adverse effect on the team’s ability to complete all of the actions relating to this audit within the originally agreed deadlines. Whist exact details were not clear at the time of reporting, the DECLO has identified the following actions as being at risk of becoming overdue:

| Ref & Priority | Agreed Action | Target Date |
| --- | --- | --- |
| 2.1 M | All draft guidance documents to be finalised or reviewed and revised as necessary to ensure documents are clear and that they align with the requirements of the ALN Act. | 31/05/24 |
| 2.2 M | On completion, all guidance documents / Standard Operating Procedures will be brought to the ALN Steering Group via the Operational Group for approval and for direction regarding any other fora at which approval is required. Approval / ratification will then be sought through the appropriate forum as needed. Review arrangements and the mechanism for review for all documents will be formally documented. | 30/09/24 |
| 4.1 b H | A contingency plan will be developed to clarify roles and responsibilities in the event of key corporate ALN staff being absent (specifically, the DECLO and the ALN Administrative Assistant) and articulating any associated risks. | 30/06/24 |
| 4.1 c H | There will be liaison between Swansea Bay, Hywel Dda and Powys Health Boards to formally document the agreement that the DECLO post for the three Health Boards, hosted by Swansea Bay University Health Board, is jointly funded by the three Health Boards with salary recharge arrangements in place. | 30/06/24 |
| 5.1 a M | An audit will be carried out to assess the knowledge and confidence of all relevant operational staff from services impacted by the ALN Act that provides assurance that they are able to effectively carry out their role. | 30/04/24 |
| 5.1 b M | Following this audit, a plan will be developed setting out the actions required to address current gaps in the knowledge and confidence of staff. A regular process to assess staff’s knowledge and confidence will be developed. | 30/06/24 |
| 5.1 c M | An ‘ALN Induction Pack’ will be developed, comprising resources to be provided to new staff that ensures they are able to effectively carry out their role. | 30/09/24 |
| 5.2 M | Mechanisms to ensure that the voices of children and young people with ALN and their parents / carers will be developed, with a clear plan in place to achieve agreed outcomes. This will be built into the ALN work plan. | 31/07/24 |
| 5.3 ai H | Subject to the outcome of the Digital Prioritisation Process, it is anticipated that the data infrastructure required to ensure reliable data regarding the Health Board’s compliance with its statutory duties will be in place to enable reporting from April 2024. | 30/04/24 |
| 5.3 aii H | Measurement of outcomes and experience will be brought to the ALN Steering Group as an agenda item for consideration and agreement of ways forward, linking to partnership and national work as appropriate. | 31/07/24 |
| 5.3 b H | As part of finalising the ALN data infrastructure, clarity will be provided regarding data retention requirements. This will be informed by engagement with Information Governance colleagues | 30/04/24 |

In addition to the foregoing, the DECLO is also reporting that action relating to reporting the Health Board’s compliance with its duties under the ALN Act will also miss its deadline of 30/06/2024. This is due to ongoing challenges securing engagement from Digital Services, as a result of competing priorities.

4.7	A summary table of all overdue actions is set out at Appendix C, with a more detailed breakdown included at Appendix D for information.

4.8	Where agreed actions have become overdue, lead executives and/or their teams are asked to provide targets/milestones for completion or further updates as part of their progress reporting. These are included in the detailed narrative update provided at Appendix D for information.

4.9	A table detailing all actions closed since the last report, including any comments made by the lead executive or their team in doing so, is included at Appendix E.

5.	FINANCIAL IMPLICATIONS

5.1	There are no direct financial implications arising from this report.

6.	RECOMMENDATIONS

6.1	Members are asked to:

- NOTE the current position of the Audit Tracker and the status of the agreed actions therein.

- AGREE any specific areas where the Committee feel that further assurance is required in order that these may be addressed with the relevant Lead Executive(s).

| Governance and Assurance |  |  |  |  |
| --- | --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |  |
|  | Partnerships for Improving Health and Wellbeing |  |  | ☐ |
|  | Co-Production and Health Literacy |  |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |  |
|  | Best Value Outcomes and High Quality Care |  |  | ☐ |
|  | Partnerships for Care |  |  | ☐ |
|  | Excellent Staff |  |  | ☐ |
|  | Digitally Enabled Care |  |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  |  | ☐ |
| Health and Care Standards |  |  |  |  |
| (please choose) | Staying Healthy |  |  | ☒ |
|  | Safe Care |  |  | ☒ |
|  | Effective Care |  |  | ☒ |
|  | Dignified Care |  |  | ☒ |
|  | Timely Care |  |  | ☒ |
|  | Individual Care |  |  | ☒ |
|  | Staff and Resources |  |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |  |
| Outstanding audit recommendations may affect quality, safety and patient experience. It is essential that where audit recommendations are made, they are acted upon with leadership from the relevant Executive Director. Reports addressing quality and safety issues are discussed in more detail in the Quality & Safety Committee. |  |  |  |  |
| Financial Implications |  |  |  |  |
| Whilst there are no direct financial implications that need to be highlighted in this report, there may be issues arising from individual audit reports or recommendations made which have financial implications for the Health Board. |  |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |  |
| Failure to address audit recommendations relating to areas such as staff and/or patient safety, or legislative compliance, may lead to action being taken against the health board. |  |  |  |  |
| Staffing Implications |  |  |  |  |
| Whilst there are no direct staffing implications that need to be highlighted in this report, there may be issues arising from individual audit reports or recommendations made which have staffing implications for the Health Board. |  |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |  |
| A robust Governance Work Programme will assist the Board in assessing risk and gathering assurance across all corporate objectives, which span the five ways of working, and the wellbeing goals identified in the Act. |  |  |  |  |
| Report History |  | N/A |  |  |
| Appendices |  | Appendix A | Overdue Actions – Audit Wales |  |
|  |  | Appendix B | Closed Actions – Audit Wales |  |
|  |  | Appendix C | Overdue Actions – NWSSP A&A (Summary) |  |
|  |  | Appendix D | Overdue Actions – NWSSP A&A (Detail) |  |
|  |  | Appendix E | Closed Actions – NWSSP A&A |  |