Counter Fraud Work Plan 2024/25

Matthew Evans

Head of Counter Fraud Services

16 May 2024

Introduction

The Health Board is assessed as now being in full compliance with Government Functional Standard 013 Counter Fraud: NHS Requirements. All 12 Components are rated Green. This work plan has been devised to embed and consolidate the achievement of Green ratings as all address local and national fraud risk.

The Work Plan is set around proactive activity covering Inform & Involve, Prevent & Deter and Strategic Governance as well as reactive activity covered by Hold to Account. The planned days are split as proactive days – 359 and reactive days - 345 days. This is in line with delivery of previous years and takes in to account the commitments made within this Work Plan.

| INFORM AND INVOLVE |  |  |  |
| --- | --- | --- | --- |
| The Organisation is required to maintain an ongoing programme of work to raise awareness of fraud, bribery and corruption and to create a counter fraud, bribery and corruption culture among all staff, across all sites, using all available media. |  |  |  |
| TASK/OBJECTIVE |  | RISK/FPN/STANDARD | PROPOSED DELIVERY |
| I&I.1 | Design and deliver a programme of counter fraud awareness presentations to staff at all levels within the Health Board, including participation in the Health Board induction programme, with the aim of ensuring that the organisation is proactive in raising fraud awareness and building an anti-fraud Review and maintain materials and media used. Evaluate presentations, collate results, and amend presentations as a result of the feedback received. Report outcomes to the Director of Finance. | GovS 013 component 11 | Throughout the Year |
| I&I.2 | Undertake awareness work to highlight the availability of counter fraud awareness training aiming to increase attendance numbers. | GovS 013 component 11 | Throughout the Year |
| I&I.3 | To develop and maintain the counter fraud information contained on the Health Board intranet site, to include details of successfully prosecuted cases – both local and national | GovS 013 component 11 | Q2 and Q4 |
| I&I.4 | Ensure that Fraud and Corruption Reporting Line advertising posters are displayed throughout the organisation, publicising the free-phone reporting line number. | GovS 013 component 11 | Throughout the Year |
| I&I.5 | Actively promote and encourage staff awareness and completion of the Counter Fraud E-learning package. | GovS 013 component 11 | Throughout the Year |
| I&I.7 | Design, produce and distribute two counter fraud newsletters annually, containing articles on proven fraud cases (both local and national) and other “beware” notices and relevant messages. | GovS 013 component 11 | Q2 and Q4 |
| I&I.8 | In conjunction with the Health Board Communications Team, review the strategy in place for raising awareness of economic crime risks and publicise the work of the LCFS, to ensure that it remains fit for purpose and that all appropriate awareness-raising mechanisms are being fully exploited. | GovS 013 component 11 | Q2 |
| I&I.9 | Undertake targeted surveys of staff to measure awareness of: Counter Fraud, Bribery and Corruption Policy and Response Plan; Fraud, Bribery and Corruption incident reporting routes; and Policy and procedures relating to Conflicts of Interests, Gifts and Hospitality and Bribery Act. | GovS 013 Components 4, 7 and 12 | Throughout the Year |
| I&I.10 | Utilise the finding and results of the fraud risk assessment programme to inform delivery of counter fraud training to business areas of higher risk of exposure to fraud. | GovS 013 Components 7 and 12 | Throughout the Year |
|  | TOTAL DAYS ALLOCATED | 120 |  |

| PREVENT AND DETER |  |  |  |
| --- | --- | --- | --- |
| The organisation must carry out comprehensive local risk assessments to identify fraud, bribery and corruption risks, and has counter fraud, bribery and corruption provision that is proportionate to the level of risk identified. The organisation identifies and reports on annual outcome-based metrics with objectives to evidence improvement in performance. The organisation undertakes proactive work to detect fraud using relevant information and intelligence to identify anomalies that may be indicative of fraud, bribery and corruption and takes the appropriate action, including local exercises and participation or response to national exercises. |  |  |  |
| TASK/OBJECTIVE |  | RISK/FPN/STANDARD | PROPOSED DELIVERY |
| P&D.1 | Review key organisational policies, procedures and documents, to ensure that they are adequately robust to counter fraud. The communication of revised policies, procedures and documents as appropriate, emphasising the organisational commitment to countering fraud. | GovS 013 component 3 GovS 013 component 10 | As Appropriate |
| P&D.2 | Carry out risk analysis in line with Government Counter Fraud Profession (GCFP) fraud risk assessment methodology. Record and manage assessed risk in line with the Health Board’s Risk Management policy and include on the risk registers where appropriate. | GovS 013 component 3 | Throughout the Year |
| P&D.3 | Utilise DATIX for recording of risk assessment work to effectively manage, evaluate, evidence and measure the effectiveness of counter fraud work in mitigating and reducing fraud risk or expenditure and influencing of policy and procedure aimed at reducing fraud. | GovS 013 component 2 GovS 013 component 3 GovS 013 component 5 | Throughout the Year |
| P&D.4 | Review existing fraud risk assessments with Risk Owners before recording on DATIX for ongoing management. | GovS 013 component 2 GovS 013 component 3 GovS 013 component 5 FR01, FR02, FR03, FR04, FR06, FR07, FR21, FR26, FR60, FR61 | Q2 |
| P&D.5 | Liaise with Corporate Governance colleagues around measuring effectiveness and staff awareness of conflicts of interest policy and registers that include gifts and hospitality with reference to fraud, bribery and corruption, and the requirements of the Bribery Act 2010. | GovS 013 component 12 | Q1 |
| P&D.6 | Utilise National Fraud Initiative data, which matches payroll records to creditors and suppliers, to undertake a proactive exercise to measure compliance with the conflicts of interest policy. | GovS 013 component 10 | Q2 |
| P&D.7 | Follow up to Proactive Exercise undertaken around Impersonating a Medical Professional and finalise a fraud risk assessment. | FPN H-003-23 | Q2 |
| P&D.8 | Finalise fraud risk assessment around identified issue of False International English Language Testing System Certificates (IELTS) | FPN H-005-23 | Q1 |
| P&D.9 | Finalise fraud risk assessment around identified issue of Salary Sacrifice | FPN – L004-23 | Q1 |
| P&D.10 | Finalise fraud risk assessment around identified issue of Working Elsewhere | FPN – L001-23 | Q2 |
| P&D.11 | Review both FR08 & FR09 around updated issue of Mandate Fraud. Seek to amalgamate both risks into one comprehensive risk assessment to streamline future review of this ever evolving fraud risk | FPN – L002-23 | Q1 |
| P&D.12 | Review FR22 in response to the identified issue of CEO/Unsolicited Payment Requests | FPN-M001-24 | Q1 |
| P&D.13 | Participate in NHS Counter Fraud Authority national proactive procurement risk exercise entered around specific risks of due diligence and contract management. | FR02 FR03 FR04 FR05 | Q2 |
| P&D.14 | Review and update information sharing protocols currently in place. Review and refresh protocols with People Services. | Service level | Q1 |
| P&D.15 | Regular meetings with the Head of Internal Audit (NWSSP Audit & Assurance) | Service level | Throughout the Year |
| P&D.16 | Record and respond to ad-hoc requests for assistance received. | Service level | Throughout the Year |
| P&D.17 | Action Fraud Prevention Notices issued by NHS Counter Fraud Authority and/or Counter Fraud Services Wales as and where appropriate. | GovS 013 component 3 | As Appropriate |
| P&D.18 | Issue of fraud alerts to all appropriate staff. | GovS 013 component 11 | As Appropriate |
| P&D.19 | Regular liaison with the Post Payment Verification Location Manager (NWSSP Primary Care) and Primary Care leads to ensure that any contractor visits which result in the identification of anomalies are reported to the LCFS. | Service level | Throughout the Year |
| P&D.20 | Participate in mandatory national proactive exercises, as instructed by NHS Counter Fraud Authority, Auditor General for Wales and/or the Cabinet Office (e.g. NFI). | GovS 013 component 10 | Throughout the Year |
| P&D.21 | Participate in thematic fraud risk evaluation exercises as instructed by the NHS Counter Fraud Authority. | GovS 013 component 10 | As Required |
| P&D.22 | Conduct proactive work to detect fraud using relevant information and intelligence to identify anomalies that may be indicative of fraud, bribery and corruption. Results of this work are evaluated and where appropriate feed into improvements to prevent and deter fraud, bribery and corruption in line. | GovS 013 component 10 | Throughout the Year |
| P&D.23 | Membership of Local Intelligence Network and attendance at meetings. | Service level | As Required |
|  | TOTAL DAYS ALLOCATED | 170 |  |

| HOLD TO ACCOUNT |  |  |  |
| --- | --- | --- | --- |
| The organisation employs or contracts in an accredited, person (or persons) nominated to the NHSCFA to undertake the full range of counter fraud, bribery and corruption work, including proactive work to prevent and deter fraud, bribery and corruption and reactive work to hold those who commit fraud, bribery or corruption to account. The organisation must have well established and documented reporting routes for staff, contractors and members of the public to report incidents of fraud, bribery and corruption. The organisation uses the approved NHS fraud case management system to record all incidents of reported suspect fraud, bribery and corruption, to inform national intelligence and NHS counter fraud functional standard return submission by the NHSCFA. |  |  |  |
| TASK/OBJECTIVE |  | RISK/FPN/STANDARD | PROPOSED DELIVERY |
| HTA.1 | Conduct investigations into all allegations of economic crime as required, in line with the requirements of the NHS Counter Fraud Authority Counter Fraud Manual, and all relevant guidance and legislation. | GovS 013 component 9 | As Required |
| HTA.2 | Appropriate use of the prescribed case management system, in line with NHS Counter Fraud Authority and NHS CFS Wales requirements. | GovS 013 component 6 GovS 013 component 8 | As Required |
| HTA.3 | Assist NHS Counter Fraud Authority and/or NHS CFS Wales as required in respect of any regional or national investigations. | GovS 013 component 9 | As Required |
| HTA.4 | Ensure the application of sanctions in line with legislation and the policy document ‘Applying Appropriate Sanctions Consistently’. | GovS 013 component 6 GovS 013 component 9 | As Required |
| HTA.5 | Identify and maintain appropriate records and, wherever possible, seek financial redress/recovery in respect of any proven loss to the Health Board, having due regard to the particular circumstances of each case. | GovS 013 component 6 GovS 013 component 8 | As Required |
| HTA.6 | Review professional competencies and capabilities of accredited staff nominated to undertake the full range of counter fraud work to assess requirements for professional development opportunities. | GovS 013 component 9 | Q1 |
| HTA.7 | Explore Memorandum of Understanding between South Wales Police and the Health Board to cover matters of joint interest when undertaking investigation. | Service level | Throughout the Year |
|  | TOTAL DAYS ALLOCATED | 364 |  |

| STRATEGIC GOVERNANCE |  |  |  |
| --- | --- | --- | --- |
| A member of the executive board or equivalent body is accountable for provision of strategic management of all counter fraud, bribery and corruption work within the organisation. The organisation’s non-executive directors, counter fraud champion or lay members and board/governing body level senior management are accountable for gaining assurance that sufficient control and management mechanisms in relation to counter fraud, bribery and corruption are present within the organisation. The organisation maintains an annual work plan that is informed by national and local fraud, bribery and corruption risk assessment identifying activities to improve capability and resilience. |  |  |  |
| TASK/OBJECTIVE |  |  | PROPOSED DELIVERY |
| SG.1 | Attendance at all Fraud Forum meetings held by CFS Wales. | Service Level | As Required |
| SG.2 | Completion and agreement of the annual work plan with Director of Finance. | GovS 013 component 2 | Q4 |
| SG.3 | Completion and agreement of the annual report with Director of Finance. | GovS 013 component 5 | Q1 |
| SG.4 | Regular meetings/liaison with Director of Finance. | GovS 013 component 1 | Throughout the Year |
| SG.5 | Preparation for and attendance at Audit Committee meetings. | GovS 013 component 1 | As Required |
| SG.6 | Full participation in the quality assurance process as directed by NHS Counter Fraud Authority | Service Level | Q4 and As Required |
| SG.7 | Undertake additional training as required by the Health Board or NHS Counter Fraud Authority. | Service Level | As Required |
| SG.8 | Continuing use of CLUE3 case management system, as mandated by the NHS Counter Fraud Authority. Utilise system to record all fraud, bribery and corruption investigative activity, including all outcomes, recoveries and system weaknesses identified during the course of investigations and/or proactive prevention and detection exercises. | GovS 013 component 8 | Throughout the Year |
| SG.9 | Provide regular reports and ad hoc information to NHS Counter Fraud Authority and Welsh Government as required | GovS 013 component 6 | Throughout the Year |
| SG.10 | Review the Health Board’s Counter Fraud Policy and Response Plan to ensure up to date and relevant contents as well as alignment to Government Functional Standards. | GovS 013 component 4 GovS 013 component 7 | Q2 |
|  | TOTAL DAYS ALLOCATED | 50 |  |

SUMMARY TOTALS

|  | STRATEGIC AREA OF ACTIVITY | RESOURCE ALLOCATED (in days) |
| --- | --- | --- |
| A | INFORM AND INVOLVE | 120 |
| B | PREVENT AND DETER | 170 |
| C | HOLD TO ACCOUNT | 364 |
| D | STRATEGIC GOVERNANCE | 50 |
|  | TOTAL | 704 |