| Meeting Date | 21 May 2026 |  | Agenda Item |  |  | 2.3 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Audit Committee |  |  |  |  |  |
| Report Title | Audit Tracker – Status of Agreed Action |  |  |  |  |  |
| Report Author | Len Cozens, Head of Compliance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Len Cozens, Head of Compliance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to provide the Committee with an update on performance in delivering actions agreed as a result of the findings of audit reviews undertaken by NWSSP Audit & Assurance and Audit Wales. |  |  |  |  |  |
| Key Issues | This report summarises updates entered onto the Tracker since the last report, up to and including the 08/05/2026. It should be noted that due to resource issues, it has not been possible to establish an updated position in respect of final audit reports considered at the March 2026 Committee meeting. This will be fully addressed as part of the July 2026 update. Audit Wales There are currently 11 actions recorded as overdue on the tracker, which represents a decrease of 2 when compared to the last report. A total of 2 actions were closed during the period. In addition, management have indicated that they would like to close a further 8 actions. Work to gather, review and verify the evidence to support these closures is currently ongoing. NWSSP A&A There are currently 119 actions recorded as overdue on the Tracker, which represents an increase of 32 when compared to the last report. A total of 24 actions were closed during the period. In addition, management have indicated that they would like to close a further 60 actions. Work to gather, review and verify the evidence to support these closures is currently ongoing. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - CONSIDER the current position of the Audit Tracker and the status of the agreed actions therein. - AGREE any specific areas where the Committee feel that further assurance is required in order that these may be addressed with the relevant Lead Director(s). |  |  |  |  |  |

AUDIT TRACKER AND

STATUS OF AGREED ACTIONS

- INTRODUCTION

1.1	The purpose of this report is to provide the Committee with an update on performance in the delivery of actions agreed as a result of the findings of audit reviews undertaken by NWSSP Audit & Assurance and Audit Wales.

- BACKGROUND AND CONTEXT

2.1	The Audit Committee receives and considers reports as part of normal business, which provide information and assurance in respect of:

- The delivery of Audit Plans;

- Receipt of draft and final reports; and

- Health Board management responses to the findings contained therein

2.2	This report is intended to provide assurance in respect of performance in implementing agreed actions across all reports received from both NWSSP Audit & Assurance, and Audit Wales.

2.3	Action plans in respect of all final audit reports are available on the Finance Portal through SharePoint for Directors and managers to access and update throughout the year, with the deadlines for the reporting periods to the Audit Committee clearly set out within the file set up. In addition, the Head of Compliance has produced and distributed guidance notes to assist users in the review and update of the Tracker.

2.4	It should be noted that the charts and tables within this report relate to all reports where outstanding actions remain, regardless of their age. When all actions within a given report are marked closed, the report is archived and will no longer be included as part of this update.

2.5	Where actions or findings have been superseded by the content of later reports, then the original has been closed and does not form part of the following.

3.	STATUS UPDATE – AUDIT WALES REPORTS

3.1	The following sets out the current position in respect of performance in implementing agreed actions stemming from Audit Wales findings, when measured against the original deadlines agreed by management at the time the reports were finalised. It should be noted that due to resource issues, any final reports considered at the March 2026 Audit Committee meeting are not included in the following. This will be fully addressed as part of the July 2026 update.

Fig 1: Audit Wales Reports

3.2	A summary of all overdue Audit Wales actions is set out in the table below.

| Report Title | Number of Overdue Actions |  |  | Closure Evidence Under Review |
| --- | --- | --- | --- | --- |
|  | High Priority | Medium Priority | Other |  |
| COO | 0 | 0 | 3 | 1 |
| Primary Care Follow-Up | - | - | 2 | - |
| Operational Gov. COO | - | - | 1 | 1 |
| Dir. Corp. Gov. | 0 | 0 | 7 | 7 |
| Quality Gov. | - | - | 1 | 1 |
| Operational Gov. DoCG | - | - | 5 | 5 |
| Structured Ass. 2024 | - | - | 1 | 1 |
| Dir. Finance | 0 | 0 | 11 | 0 |
| Structured Ass. 2022 | - | - | 1 | - |
| Total | 0 | 0 | 11 | 8 |

3.3	A total of 2 actions were closed during the period.

3.4	In addition, management have indicated that they would like to close a further 8 actions – these are summarised in the ‘Closure Evidence Under Review’ column in the preceding table. Again, due to resources issues, it has not been possible to gather, review and verify all of the evidence to support these closures. This work is currently ongoing, and an update will be brought to the next meeting of the Committee.

4.	STATUS UPDATE – NWSSP AUDIT & ASSURANCE REPORTS

4.1	The following sets out the current position in respect of performance in implementing agreed actions stemming from NWSSP Audit & Assurance findings, when measured against the original deadlines agreed by management at the time the reports were finalised. It should be noted that due to resource issues, any final reports considered at the March 2026 Audit Committee meeting are not included in the following. This will be fully addressed as part of the July 2026 update.

Fig 2: NWSSP Audit & Assurance Reports

4.2	A summary table of all overdue actions is set out at Appendix A for information.

4.3	A total of 24 actions were closed during the period.

4.4	In addition, management have indicated that they would like to close a further 60 actions – these are summarised in the ‘Closure Evidence Under Review’ column at Appendix A. Again, due to resources issues, it has not been possible to gather, review and verify all of the evidence to support these closures. This work is currently ongoing, and an update will be brought to the next meeting of the Committee. In terms of priority, these 60 actions can be split as follows.

| High | Medium | Low |
| --- | --- | --- |
| 15 | 45 | 0 |

5.	FINANCIAL IMPLICATIONS

5.1	There are no direct financial implications arising from this report.

6.	RECOMMENDATIONS

6.1	Members are asked to:

- CONSIDER the current position of the Audit Tracker and the status of the agreed actions therein.

- AGREE any specific areas where the Committee feel that further assurance is required in order that these may be addressed with the relevant Lead Director(s).

| Governance and Assurance |  |  |  |  |
| --- | --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |  |
|  | Partnerships for Improving Health and Wellbeing |  |  | ☐ |
|  | Co-Production and Health Literacy |  |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |  |
|  | Best Value Outcomes and High Quality Care |  |  | ☐ |
|  | Partnerships for Care |  |  | ☐ |
|  | Excellent Staff |  |  | ☐ |
|  | Digitally Enabled Care |  |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  |  | ☐ |
| Health and Care Standards |  |  |  |  |
| (please choose) | Staying Healthy |  |  | ☒ |
|  | Safe Care |  |  | ☒ |
|  | Effective Care |  |  | ☒ |
|  | Dignified Care |  |  | ☒ |
|  | Timely Care |  |  | ☒ |
|  | Individual Care |  |  | ☒ |
|  | Staff and Resources |  |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |  |
| Outstanding audit recommendations may affect quality, safety and patient experience. It is essential that where audit recommendations are made, they are acted upon with leadership from the relevant Director. Reports addressing Q&S issues are discussed in more detail in the Q&S Committee. |  |  |  |  |
| Financial Implications |  |  |  |  |
| Whilst there are no direct financial implications that need to be highlighted in this report, such may arise from individual audit reports or recommendations made. |  |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |  |
| Failure to address audit actions relating to areas such as staff and/or patient safety, or legislative compliance, may lead to action being taken against the health board. |  |  |  |  |
| Staffing Implications |  |  |  |  |
| Whilst there are no direct staffing implications that need to be highlighted in this report, there may be issues arising from individual audit reports or recommendations made which have staffing implications for the Health Board. |  |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |  |
| A robust Governance Work Programme will assist the Board in assessing risk and gathering assurance across all corporate objectives, which span the five ways of working, and the wellbeing goals identified in the Act. |  |  |  |  |
| Report History |  | The Committee last received an update on this topic in January 2026 |  |  |
| Appendices |  | Appendix A | Overdue Actions – NWSSP A&A (Summary) |  |