| Meeting Date | 21 November 2024 |  | Agenda Item |  |  | 3.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Audit Tracker and Status of Agreed Actions |  |  |  |  |  |
| Report Author | Len Cozens, Head of Compliance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Len Cozens, Head of Compliance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to provide the Audit Committee with an update regarding performance in the delivery of actions agreed as a result of audit reviews (NWSSP Audit & Assurance and Audit Wales), and the resulting recommendations. |  |  |  |  |  |
| Key Issues | This report includes all updates entered onto the Tracker since the last report, up to and including the 30th October 2024. Audit Wales There are currently 13 actions overdue, which represents an increase of 1 when compared to the last report. A total of 2 new actions became overdue during the reporting period, however, this figure has been partially offset by the closure of a separate action which had previously been reported as overdue. In total, 7 actions were closed during the reporting period. NWSSP A&A There are currently 113 actions overdue, which represents an increase of 13 when compared to the last report. A total of 28 new actions became overdue during the reporting period, however, this figure has been partially offset by the closure of 15 other actions which had previously been reported as overdue. In total, 50 actions were closed during the reporting period. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☐ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the current position of the Audit Tracker and the status of the agreed actions therein. - AGREE any specific areas where the Committee feel that further assurance is required in order that these may be addressed with the relevant Lead Director(s). |  |  |  |  |  |

AUDIT TRACKER AND

STATUS OF AGREED ACTIONS

- INTRODUCTION

1.1	The purpose of this report is to provide the Audit Committee with an update regarding performance in the delivery of actions agreed as a result of the findings of audit reviews (NWSSP Audit & Assurance and Audit Wales), and the resulting recommendations.

- BACKGROUND AND CONTEXT

2.1	The Audit Committee receives and considers reports as part of normal business, which provide information and assurance in respect of:

- The delivery of Audit Plans;

- Receipt of draft and final reports; and

- Health Board management responses to recommendations contained therein

2.2	This report is intended to provide assurance in respect of performance in implementing agreed actions across all reports received from both NWSSP Audit & Assurance, and Audit Wales.

2.3	Action plans in respect of all final audit reports are available on the Finance Portal through SharePoint for Directors and managers to access and update throughout the year, with the deadlines for the reporting periods to the Audit Committee clearly set out within the file set up. In addition, the Head of Compliance has produced and distributed guidance notes to assist users in the review and update of the Tracker.

2.4	It should be noted that the charts and tables within this report relate to all reports where outstanding actions remain, regardless of their age. When all actions within a given report are marked closed, the report is archived, and will no longer be included as part of this update.

2.5	Where actions or recommendations have been superseded by the content of later reports, then the original has been closed and does not form part of the following.

3.	STATUS UPDATE – AUDIT WALES REPORTS

3.1	The figure overleaf sets out the current position in respect of performance in implementing agreed actions stemming from Audit Wales recommendations, when measured against the original deadlines agreed by management at the time the reports were finalised.

Fig 1: Audit Wales Reports

3.2	Two new actions became overdue during the reporting period, both of which relate to the Primary Care Follow Up review. The total number of overdue actions currently stands at 13.

3.3	A summary of all overdue Audit Wales actions is set out in the table below, with a more detailed breakdown included at Appendix A for information.

| Report Title | Number of Overdue Actions |  |  |
| --- | --- | --- | --- |
|  | High Priority | Medium Priority | Other |
| Lead: Chief Operating Officer | 0 | 0 | 3 |
| Primary Care Follow-Up | - | - | 3 |
| Lead: Director of Corp. Gov. | 3 | 0 | 2 |
| Quality Governance Arrangements | - | - | 1 |
| Structured Assessment 2022 | - | - | 1 |
| Structured Assessment 2023 | 3 | - | - |
| Exec Lead: Director of ICE | 0 | 0 | 3 |
| Equality Impact Assessments | - | - | 3 |
| Lead: Director of Finance & Perf. | 1 | 0 | 1 |
| Structured Assessment 2022 | - | - | 1 |
| Structured Assessment 2023 | 1 | - | - |
| Total | 4 | 0 | 9 |

3.4	Where agreed actions have become overdue, lead Directors and/or their teams are asked to provide targets/milestones for completion or further update as part of their progress reporting. These are included in the narrative update provided at Appendix A for information.

3.5	A total of seven actions were closed during the reporting period, relating to the Primary Care Follow Up Review and Workforce Planning Arrangements. A table detailing these actions, including any comments made by the lead Directors or their teams in closing them, can be found at Appendix B.

4.	STATUS UPDATE – NWSSP AUDIT & ASSURANCE REPORTS

4.1	The following sets out the current position in respect of performance in implementing agreed actions stemming from NWSSP Audit & Assurance recommendations, when measured against the original deadlines agreed by management at the time the reports were finalised.

Fig 2: NWSSP Audit & Assurance Reports

4.2	The following table represents the number of complete, in progress and overdue actions as a percentage of the total number of actions arising from the reports.

| Complete | In Progress | Overdue |
| --- | --- | --- |
| 56.99% | 12.63% | 30.38% |

4.3	A total of 28 new actions became overdue during the reporting period. However, this figure has been partially offset by the closure of 15 other previously overdue actions. The total overall number of overdue actions has therefore increased by 13. The 28 new overdue actions are spread across a number of reports, but can be primarily attributed to the following:

| Report Name | High Priority | Medium Priority | Low Priority |
| --- | --- | --- | --- |
| Service Group Governance MH&LD | - | 5 | - |
| Agency Staff Management | - | 4 | - |
| Quality Management System | - | 3 | - |
| Additional Learning Needs | - | 3 | - |
| Consultant Job Planning | 2 | 1 | - |

4.4	Reporting against all 7 overdue actions relating to the audit of the Swansea Wellness Centre continues to be suspended due to the fact that this project has been paused, pending a review of its overall scope. Once this review has been completed and a way forward agreed, all actions will be revisited and addressed in the context of the revised arrangements.

4.5	Similarly, noting that Discharge Planning will be reviewed again by NWSSP Audit & Assurance during 2024/25, reporting against all 16 overdue actions relating to the February 2021 report on this area also remains suspended. All outstanding actions will be revisited in light of the findings of the new review, and a new combined/amalgamated action plan incorporating the relevant findings from both audits will be produced thereafter.

4.6	A summary table of all overdue actions is set out at Appendix C, with a more detailed breakdown included at Appendix D for information.

4.7	Where agreed actions have become overdue, lead directors and/or their teams are asked to provide targets/milestones for completion or further update as part of their progress reporting. These are included in the detailed narrative update provided at Appendix D for information.

4.8	A total of 50 actions have been closed during the reporting period. In the instance highlighted below, changes to circumstances since the audit review have meant that it is not possible to deliver the action as stated in the original recommendation. The foregoing notwithstanding, management feel it is reasonable to close this recommendation at this time given the action taken to date and all other circumstances:

| Stds. of Business Conduct – Declarations of Interest |  |
| --- | --- |
| Finding / Recommendation |  |
| There is no set process which allows the Corporate Governance Team to be certain that all required declarations have been made, in so far as that is possible, and to identify missing declarations. We note that plans remain for the declarations form to be electronic, where the data can be held centrally. Management should determine and implement a solution to ensure the completeness and accuracy of declarations of interest, including nil returns. |  |
| Response | Remark on Closure |
| Quarterly reminders are sent to the corporate and service group leads to cascade within their teams to remind staff of their responsibilities to declare interests. In addition, declarations of interest and secondary employment are to be created as competencies within the statutory and mandatory training section of ESR with all employees required to complete these once a year and confirm that they have read the standards of business conduct policy. | October 2024: Staff have a duty to declare any interests and secondary employment. Quarterly reminders are sent to the corporate and service group leads to cascade within their teams, to remind staff of their responsibilities to declare interests. This process continues. The national ESR Team have confirmed that declarations of interest and secondary employment will not be created as competencies within the statutory and mandatory training section of ESR. This matter will now be considered for inclusion in the appropriate risk register, in line with normal processes |

4.9	A table detailing all actions closed since the last report, including any comments made by the lead director(s) or their teams in doing so, is included at Appendix E.

5.	FINANCIAL IMPLICATIONS

5.1	There are no direct financial implications arising from this report.

6.	RECOMMENDATIONS

6.1	Members are asked to:

- NOTE the current position of the Audit Tracker and the status of the agreed actions therein.

- AGREE any specific areas where the Committee feel that further assurance is required in order that these may be addressed with the relevant Lead Executive(s).

| Governance and Assurance |  |  |  |  |
| --- | --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |  |
|  | Partnerships for Improving Health and Wellbeing |  |  | ☐ |
|  | Co-Production and Health Literacy |  |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |  |
|  | Best Value Outcomes and High Quality Care |  |  | ☐ |
|  | Partnerships for Care |  |  | ☐ |
|  | Excellent Staff |  |  | ☐ |
|  | Digitally Enabled Care |  |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  |  | ☐ |
| Health and Care Standards |  |  |  |  |
| (please choose) | Staying Healthy |  |  | ☒ |
|  | Safe Care |  |  | ☒ |
|  | Effective Care |  |  | ☒ |
|  | Dignified Care |  |  | ☒ |
|  | Timely Care |  |  | ☒ |
|  | Individual Care |  |  | ☒ |
|  | Staff and Resources |  |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |  |
| Outstanding audit recommendations may affect quality, safety and patient experience. It is essential that where audit recommendations are made, they are acted upon with leadership from the relevant Director. Reports addressing Q&S issues are discussed in more detail in the Q&S Committee. |  |  |  |  |
| Financial Implications |  |  |  |  |
| Whilst there are no direct financial implications that need to be highlighted in this report, such may arise from individual audit reports or recommendations made. |  |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |  |
| Failure to address audit recommendations relating to areas such as staff and/or patient safety, or legislative compliance, may lead to action being taken against the health board. |  |  |  |  |
| Staffing Implications |  |  |  |  |
| Whilst there are no direct staffing implications that need to be highlighted in this report, there may be issues arising from individual audit reports or recommendations made which have staffing implications for the Health Board. |  |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |  |
| A robust Governance Work Programme will assist the Board in assessing risk and gathering assurance across all corporate objectives, which span the five ways of working, and the wellbeing goals identified in the Act. |  |  |  |  |
| Report History |  | The Committee last received a report on this topic in July 2024 |  |  |
| Appendices |  | Appendix A | Overdue Actions – Audit Wales |  |
|  |  | Appendix B | Closed Actions – Audit Wales |  |
|  |  | Appendix C | Overdue Actions – NWSSP A&A (Summary) |  |
|  |  | Appendix D | Overdue Actions – NWSSP A&A (Detail) |  |
|  |  | Appendix E | Closed Actions – NWSSP A&A |  |