| Meeting Date | 14 September 2023 |  | Agenda Item |  |  | 2.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Quality Management Framework Stock-Take |  |  |  |  |  |
| Report Author | Liz Stauber, Head of Corporate Governance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance Richard Evans, Executive Medical Director Gareth Howells, Director of Nursing and Patient Experience Debbie Eyitayo, Director of Workforce and OD |  |  |  |  |  |
| Presented by | Hazel Lloyd, Director of Corporate Governance Richard Evans, Executive Medical Director Gareth Howells, Director of Nursing and Patient Experience Debbie Eyitayo, Director of Workforce and OD |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of the report is to set out the progress to develop a quality management framework. |  |  |  |  |  |
| Key Issues | Quality comprises patient safety, experience, clinical effectiveness, outcomes and access within health services. It is of paramount importance in the recovery process from Covid-19 and it is essential there is a quality focus at every level. In support of a reset, the health board undertook a piece of work considering the quality governance arrangements in the service groups and this coincided with Audit Wales and internal audit reviews of quality governance and the quality governance framework respectively. Part of the work to address the recommendations of the reviews was to establish a quality management system. To support the work needed, a task and finish group was set up to agree the actions to take forward and monitor progress, chaired by the Chief Executive. Key areas of focus were agreed and progressed over the last six months. A stock-take was presented to the meeting in March 2023 and the decision made that sufficient progress had been made and the work could now be part of the Management Board going forward. Further to this, work is underway to create the vision and One Bay Way for the organisation to create a clinically-led, high quality organisation which will further drive forward the work for a quality management framework. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the progress against the actions to develop a quality management system and that this work will now been overseen by the Management Board. |  |  |  |  |  |

QUALITY MANAGEMENT FRAMEWORK STOCK-TAKE

- INTRODUCTION

The purpose of the report is to set out the next steps to develop a quality management system.

- BACKGROUND

Quality comprises patient safety, experience, clinical effectiveness, outcomes and access within health services. Quality is of paramount importance in the recovery process from Covid-19 and it is essential there is a quality focus at every level. In the last 12 months, a number of reviews, both internally and externally have taken place of quality governance:

- Internal review of the quality governance arrangements in the service groups;

- Audit Wales review of quality governance;

- Internal audit of the quality governance framework.

The reviews provided a clear baseline of the current quality system within the health board. They were followed by two externally facilitated quality workshops with the Management Board and a Health Board development session to discuss the requirements for a quality management system and the wider organisational culture. The findings of which were shared with the Management Board, Audit Committee and Board.

More recently, the Institute for Health Care Improvement and Improvement Cymru undertook a quality review, the report for which has been shared with the Management Board and board members. The main areas for improvement included data, lineation of aims and trajectories and improvement methodologies, including training for staff.

Work to develop a robust quality management system has been led by the Chief Executive and supported by the Director of Nursing and Patient Experience as the executive lead for quality along with the Medical Director, Director of Therapies and Health Science, Director of Workforce and OD and Director of Corporate Governance. However, it is recognised that everyone has a role in improving quality and that the culture is an intrinsic component of helping to drive the reset for quality improvement. Further to this, work is underway to create the vision and One Bay Way for the organisation to create a clinically-led, high quality organisation which will further drive forward the work for a quality management framework.

- GOVERNANCE AND RISK ISSUES

There are a number of key areas in which work is progressing to develop a quality management system. In order to achieve what is needed, two or three key actions were identified for four domains to ensure they are delivered well and in full, rather than having a scattergun approach and not achieving anything.

To support this work, a quality task and finish group was established, chaired by the Chief Executive. A stock-take was presented to the meeting in March 2023 and the decision made that sufficient progress had been made and the work could now be part of the Management Board going forward.  Progress to date is outlined below.

| Governance |  |  |
| --- | --- | --- |
| Action | Lead | Status |
| Identify clear leads in each service group triumvirate for patient experience, clinical outcomes and effectiveness, compliance and safety; | Service Groups | While there was some consistency within approaches, no service group’s arrangements mirrored the corporate structure or each other. Work has been undertaken by the Director of Corporate Governance and the structures are now broadly in-line with those of corporate and are in the process of being implemented. Audit Wales will be reviewing these during 2023-24. Revised Quality Framework to reflect Duty of Quality being consulted upon for approval in September 2023. |
| Service groups to have a standardised lists of quality areas to discuss in their quality governance structures throughout a 12-month cycle in a clear work programme; | Service Groups |  |
| Develop proposals for a central quality hub for approval by the Patient Safety Group; | Director of Nursing and Patient Experience | Quality hub now in place supported by a dedicated intranet page: Quality, Safety & Improvement Hub - Home (sharepoint.com) |
| Clarity be set as to whom the governance function within the service groups (complaints, concerns, patient experience) reports and this be a standard approach for all service groups as line management is currently different across all. | Director of Nursing and Patient Experience/Director of Corporate Governance | Review of resources across the health board has taken place and is being benchmarked against foundation trusts in NHS England. Full report was taken to Management Board in July 2023 with timelines for a standard approach to be in place for Autumn 2023. |

| Quality |  |  |
| --- | --- | --- |
| Action | Lead | Status |
| First draft of quality strategy be shared with the Management Board for discussion | Director of Nursing and Patient Experience | Completed. Quality strategy was approved by the board in January 2023 and launched on 2nd March 2023. |
| Identify, through a multi-disciplinary approach with the service groups and based on evidence, three to five priorities to focus on improving | Director of Nursing and Patient Experience | HB-wide priorities for 2023/24 have been agreed and governance arrangements put in place. Service groups are holding summit events to look at priorities within specific areas. |
| Tools and techniques be created for staff to measure staff and patient experience understand their services to identify problem areas | Director of Insight, Communications and Engagement/Director of Workforce and OD | Task and finish group commenced in April to take this work forward over six months. |
| External facilitator be commissioned to develop the patient and stakeholder experience and engagement sub-group to expand areas of focus from ‘friends and family’ | Director of Nursing and Patient Experience/Director of Corporate Governance | Task and finish group commenced in April to take this work forward over six months. |
| Develop a new style ‘complaint’ report | Director of Nursing and Patient Experience/Director of Corporate Governance | Completed and shared with the Quality and Safety Committee in July 2022. |
| A baseline review of quality resources within the health board to determine what should be corporate and what should be devolved to the service groups | Director of Nursing and Patient Experience/Director of Corporate Governance | Full report was taken to Management Board in July 2023 with timelines for a standard approach to be in place for Autumn 2023. |
| Development of a communications plan to set out the work being undertaken, why and expectations | Director of Insight, Communications and Engagement | Communications and implementation actions developed to support the quality strategy. |

| Outcomes |  |  |
| --- | --- | --- |
| Action | Lead | Status |
| Mortality reduction plans across primary and secondary care | Executive Medical Director | The Deputy Medical Director has created a mortality dashboard for medical examiner to review, crude and condition speciality mortality ratio with a condition specific mortality dashboard. The data is reviewed monthly and triangulated to identify outliers and themes which are brought to attention of the clinical team and the Clinical Outcomes and Effectiveness and the Patient Safety groups. The clinical team undertake a thematic analysis for outliers from the medical examiner reviews to develop a quality improvement programme, the outcome of which is reported to the Clinical Outcomes and Effectiveness group and the Patient safety groups. |
| Management system to implement and monitor compliance with NICE (National Institute for Clinical Excellence) guidance | Executive Medical Director | Completed and shared with the Audit Committee in September 2022. |

| Creating a Learning Organisation |  |  |
| --- | --- | --- |
| Action | Lead | Status |
| Big Conversation process be undertaken to staff’s views on the culture of the organisation, staff experience and quality of services | Director of Workforce and OD | The programme has three phases: - Identifying the current perception of staff and stakeholders of where we are, what we want the future to look like, how we want to work and what we stand for; - Engagement on the potential and broad vision for a quality driven organisation and to get there; - Setting a compelling vision for our organisation. Phase one, two and three are now complete and the engagement now underway on the vision document. |
| Creation of a quality improvement academy | Director of Nursing and Patient Experience | Database of staff to support quality improvement programmes in place. Internal training scoping review has been completed and discussed with Improvement Cymru. Revised training offer being implemented from October 2023. QI Community of Practice established. |
| Development of a reward/recognition structure | Director of Workforce and OD | #Livingourvalues have been extended to include additional categories. |
| Establishment of quarterly conferences and monthly ‘scale and spread’ events | Director of Nursing and Patient Experience | Quarterly congress events in the diary. |
| Create a list of those with IQT silver training | Director of Nursing and Patient Experience | Completed in September 2022 and database of staff to support quality improvement programmes in place. |

Good progress has been made in the majority of areas, with regular updates provided to the task and finish group as well as through the health board’s formal governance structure. There are a couple of priorities yet to be completed but plans are in place for these.

- FINANCIAL IMPLICATIONS

Business case for infrastructure support for the Quality Hub submitted to the Business Case Approval Group. This includes training, measurement and project management support to ensure delivery, accountability and consistency.

- RECOMMENDATION

Members are asked to:

- NOTE the progress against the actions to develop a quality management system and that this work will now been overseen by the Management Board.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☐ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☐ |
|  | Effective Care |  | ☐ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Quality, safety and experience should be the core components of all that the health board does as it is here first and foremost for patients. Having a robust quality management system will ensure that a high-level of care is being provided times when people need it most. |  |  |  |
| Financial Implications |  |  |  |
| Business case for infrastructure support for the Quality Hub submitted to the Business Case Approval Group. This includes training, measurement and project management support to ensure delivery, accountability and consistency. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| There are no legal implications. |  |  |  |
| Staffing Implications |  |  |  |
| Additional staffing requirement to support deliver of a Quality Improvement Academy and to support quality improvement and assurance. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| In order to develop the organisation to be a sustainable one for the longer-term, a quality management system is critical in creating an expectation of the public that they deserve, and should receive, care that is of the highest quality. |  |  |  |
| Report History |  | Regular update to the Management Board, Quality and Safety Committee and Board. |  |
| Appendices |  | No appendices |  |