| Meeting Date | 16 September 2025 |  | Agenda Item |  |  | 2.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Audit Committee |  |  |  |  |  |
| Report Title | Risk Report |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Presented by | Hazel Lloyd, Director of Corporate Governance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to present the Health Board Risk Register (HBRR) to the Audit Committee for review and assurance, and to provide the Audit Committee with an update on progress on the reset of the Board assurance and risk management arrangements. |  |  |  |  |  |
| Key Issues | - Content received to date from risk owners has been included in the Strategic Risk Register and presented here. - This report presents a summary of key entries within the August 2025 Health Board Risk Register (HBRR) and changes since it was last received by the Committee. - The HBRR contains 31 risks, of which 18 have risk scores at, or above, the Health Board’s risk appetite threshold. One has a risk score of 25. - The report presents a summary of high-scoring risks recorded and managed by individual services/specialties within Service Group operational risk registers. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - RECEIVE an update on progress with the development of the strategic risk register. - RECEIVE for assurance purposes the Health Board Risk Register (HBRR) and summary of movements. - RECEIVE a summary of the risks recorded and managed by services/specialties within Service Group operational risk registers. - CONSIDER whether further assurance is required on risks and their management. |  |  |  |  |  |

RISK REPORT

1	INTRODUCTION

1.1	The purpose of this report is to present the Health Board Risk Register (HBRR) to the Audit Committee for review and assurance, and to provide the Audit Committee with an update on progress on the reset of the Board assurance and risk management arrangements.

2	BACKGROUND

2.1	Update on Strategic Risk Register

2.1.1	As part of the review and reset of the Health Board’s risk management arrangements, the Risk & Assurance Team are currently supporting the production of a Strategic Risk Register (SRR).

2.1.2	To assist Directors’ considerations, the Team have:

- Reviewed arrangements in place at other health bodies and identified examples of strategic risk entries made by organisations with similar objectives to our own

- Provided relevant risks already captured within our own current Health Board Risk Register (HBRR) for comparison, together with thematic risk information on operational risks recorded within services.

- Identified common strategic risk themes and categories

- Met with Directors (or their deputies/leads) individually to discuss and help to articulate strategic risks within their portfolios, and more widely across the organisation.

- Based on the foregoing, produced draft descriptions of the strategic risks facing our Health Board for Directors’ consideration.

2.1.3	These draft risk descriptions have been shared with Directors and their teams, who have been asked complete the remainder of the entries on the SRR for each risk, prioritising the following:

- Key controls in place to manage the risk

- The sources of any assurance they have in respect of the adequacy, effectiveness and application of each control, what that source is telling us in terms of control strength, and the overall level of assurance in respect of the effective management of each risk.

- Any identified gaps in control or assurance, or any further work required, and the actions in place to address them.

2.1.4	All responses received to date have been included in the SRR document which can be found at Appendix 1. It is intended that this SRR be submitted to the September 2025 meeting of the Board. Further work is required to complete entries for the following areas of risk:

- Urgent & Emergency Care

- Planned Care

- Cancer Care

- Maintaining Our Estate

- Achieving Financial Sustainability

These risks will be added to the SRR as they are completed and agreed.

2.2	Health Board Risk Register (HBRR) Summary Position

2.2.1	The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them. The HBRR is continuing to be updated while work is ongoing to set up the new Strategic Risk Register and Corporate Risk Register.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

The Health Board approved a risk appetite statement in November 2022, setting out the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high-quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, indicating lower threshold and requiring risks scoring 16 or above to be overseen at committee level.

2.2.2	The Audit Committee last received the March HBRR at its July 2025 meeting. Since then, entries have been refreshed by Board Directors as part of the monthly review cycle. This report presents the August 2025 HBRR. The HBRR contains 31 risks, of which 18 have risk scores at, or above, the Health Board’s risk appetite threshold. One of these has risk a score of 25 (this is reduced from four risks scoring 25 at the last report to Audit Committee).

The HBRR is as attached at Appendix 2, and the most recent updates highlighted in red font. In addition to risks presented there, the following risks are deemed sensitive and are overseen in private session of Board and/or Committees:

- HBR 60	Cyber Security

- HBR 101	Industrial Action

The profile of risk scores within the HBRR is as follows:

| Risk Analysis | Number of Risks |  |
| --- | --- | --- |
|  | May 2025 HBRR | Aug 2025 HBRR |
| Risk Score of 25 | 4 | 1 |
| Risk Score of 20 | 14 | 15 |
| Risk Score of 16 | 6 | 7 |
| Risk Score 9-15 | 8 | 8 |
| Risk Score of 5-8 | 0 | 0 |
| Risk Score of 1-4 | 0 | 0 |
| Total | 32 | 31 |

2.3	Risk Changes

2.3.1	Key changes in risks scores since the last meeting are:

| CHANGES | NUMBER |
| --- | --- |
| New risks | Nil |
| Risks with increased scores | Nil |
| Risks with reduced scores | 6 |
| Risks de-escalated / closed | 1 |

Details are set out in the following sections.

2.3.2 The risk(s) with reduced scores is/are:

| Risk Ref | Reduced Risks | Lead Exec Director | Previous Risk Score | Current Risk Score |
| --- | --- | --- | --- | --- |
| 1 | Access to Unscheduled Care Service If we fail to provide timely access to Unscheduled Care, then this will have an impact on quality & safety of patient care as well as patient and family experience and achievement of targets. There are challenges with capacity/staffing across the Health and Social care sectors. Note: The Urgent & Emergency Care system continues to see high demand, with ambulance attendances higher than seen previously. However, this demand has been mitigated (beginning June 25) by improvement activity across the hospital resulting in improved flow away from the Emergency Department (ED). This improvement activity has been married with additional capacity at the front door (Ward) to decongest ED and resulted in the resultant reduced risk score. | Chief Operating Officer | 25 | 16 |
| 16 | Access and Planned Care There is a risk of harm to patients if we fail to diagnose and treat them in a timely way. Note: The Health Board delivered the 104 week and 52 week waiting time targets at the end of March 2025. This has been sustained during Quarter 1 of 2025/26. Risk score reduction reflects continued delivery of Referral to Treatment targets. | Chief Operating Officer | 16 | 12 |
| 50 | Access to Cancer Services There is a risk of delay in diagnosing patients with cancer, and consequent delay in commencement of treatment, which could lead to poor patient outcomes and failure to achieve targets. Note: Risk score is based on being off trajectory for Suspected Cancer Pathway, but the reduction (in July 25) reflects improvements in delivery. | Chief Operating Officer | 25 | 20 |
| 51 | Nurse Staffing (Wales) Act (Section 25B wards) – Risk of Non-Compliance with the Nurse Staffing (Wales) Act There is a risk we may not meet these requirements fully due to increased acuity, unplanned staff absence and vacancies. The potential impact of this maybe non-compliance with the ‘Act’, poor patient outcomes and experience, and suspension of services. Note: Following June 2025 Nursing and Midwifery Safe Staffing Assurance Group meeting the score was reduced following reduction in the operational risk score in Paediatrics. | Executive Director of Nursing & Patient Experience | 12 | 9 |
| 66 | Access to Cancer Services (SACT) The demand & complexity of planned treatment regime for cancer patients requiring chemotherapy currently exceed the available chair capacity, risking unacceptable delays in access to SACT treatment in Chemotherapy Day Unit with impact on targets and patient outcomes. Note: The reduction in score reflects improved performance from Q4 24/25 to Q1 25/26 in respect of tre4atment start timeliness. The score remains high reflects: Demand for SACT continues to exceed current service capacity. Ongoing workforce challenges persist within the Chemotherapy Day Unit (CDU) and Pharmacy Technical Services (PTS), impacting service delivery. Patient waiting times remain elevated, with a continued number of breaches against SACT Key Performance Indicators (KPIs). The introduction of new cancer diagnoses and NICE-approved treatments necessitates the implementation of additional SACT regimens, further straining resources. The risk score will be reviewed further when the next Quarter’s performance becomes available. In the meantime, most posts are now recruited to and training initiated. Once all staff are recruited and fully trained it is anticipated that the score will reduce further. | Executive Medical Director | 25 | 20 |
| 105 | Significant increased cost for the replacement Pathology System LIMS If the new Laboratory Information Management (LIMS) system is not live before 15th December 2025 then there will be significant more cost across NHS Wales which could impact the Health Board’s financial plans in 2025/26 and 2026/27. Costs would have to be covered to avoid pathology losing access to the current LIMS system resulting in the inability of pathology to deliver diagnostic results and blood transfusion services across all Health Board services including emergency, acute, primary and community services. Note: The change in risk assessment score for this risk follows a review and re-articulation of the risk as a financial risk. | Executive Director of Allied Health Professional & Health Sciences | 20 | 16 |

2.3.3 The risk that has been de-escalated is noted below:

| Risk Ref | De-escalated/Closed Risks | Lead Exec Director | Notes |
| --- | --- | --- | --- |
| 37 | Operational and strategic decisions are not data informed Significant gaps in information collection due to lack of digital clinical systems especially within Primary, Community and Mental Health services (Connecting Care System) resulting in inability to deliver statutory reporting requirements. Users are unable to access the information they require to make decisions at the right time Business intelligence and information already available is not always utilised effectively | Director of Digital | This had a score of 12 and so fell beneath the Board risk appetite threshold and was reported at the last Board meeting as de-escalated, for continued management within the Digital Services directorate operational risk register. |

2.4	Risks Above the Board Risk Appetite

There are 18 risks that are assessed as reaching the Board’s risk appetite threshold:

| Risk Ref | Risk Title & Description | Current Score | Executive Lead & Nominated Board Committee |
| --- | --- | --- | --- |
| 4 | Infection Prevention & Control | 20 | - Executive Director of Nursing & Patient Experience - Quality & Safety Committee |
| 43 | Deprivation of Liberty Safeguards | 16 | - Executive Director of Nursing & Patient Experience - Quality & Safety Committee |
| 50 | Access to Cancer Services | 20 (was 25) | - Chief Operating Officer - Performance & Finance Committee |
| 60 | Cyber Security | 20 | - Director of Digital - Digital, Data, Research and Innovation Committee |
| 61 | Paediatric Dental GA Service (Parkway) | 16 | - Chief Operating Officer - Quality & Safety Committee |
| 64 | Health & Safety Infrastructure | 20 | - Director of Finance & Performance - Quality & Safety Committee |
| 66 | Access to SACT (Cancer Services) | 20 (was 25) | - Executive Medical Director - Quality & Safety Committee |
| 69 | Safeguarding: Adolescents on Adult Mental Health Wards | 20 | - Chief Operating Officer - Quality & Safety Committee |
| 80 | Inability to Transfer Patients | 20 | - Chief Operating Officer - Quality & Safety Committee |
| 85 | Non-Compliance with ALN Act | 20 | - Director of Allied Health Professionals & Health Science - Quality & Safety Committee |
| 89 | Healthcare Nursing Staff Level (HMPS) | 20 | - Executive Director of Nursing & Patient Experience - Quality & Safety Committee |
| 90 | Non-compliance with UK-GDPR Article 15 regarding Subject Access Requests | 20 | - Director of Digital - Digital, Data, Research and Innovation Committee |
| 92 | Finance Forecast Deficit | 25 | - Director of Finance & Performance - Performance & Finance Committee |
| 93 | Reduced Capital Funds | 20 | - Director of Finance & Performance - Performance & Finance Committee |
| 96 | Develop an Approvable IMTP (statutory compliance) | 20 | - Director of Strategy - Performance & Finance Committee |
| 98 | Overall condition/compliance and suitability of Health Board Estate | 20 | - Director of Finance & Performance - Performance & Finance Committee |
| 99 | Failure to implement the population health strategy approaches at the required scale | 20 | - Director of Public Health - Population Health & Partnerships Committee |
| 104 | Failure to meet Tier 1 targets in Clinical Coding Completeness | 20 | - Director of Digital - Digital Data Research & Innovation Committee |

Following reductions in risk scores noted above, the below risks have fallen beneath the Health Board’s current risk appetite thresholds:

| Risk Ref | Risk Title & Description | Current Score | Executive Lead & Nominated Board Committee |
| --- | --- | --- | --- |
| 1 | Access to Unscheduled Care | 16 (was 25) | - Chief Operating Officer - Performance & Finance Committee |
| 105 | Loss of Pathology Services | 16 (from 20) | - Executive Director of Allied Health Professionals and Health Scientists - Quality & Safety Committee |

The full HBRR at Appendix 1 includes all risks above and below the appetite threshold, together with details of key controls in place to manage risk and actions being taken to address them further. The Board’s Committees receive regular reports on their allocated risks highlighting key steps taken to manage risk to an acceptable level. Reports also include updates on those risks below appetite, in recognition of the Board’s aspiration to reduce risks further.

2.5	Operational Service Risks

In addition to the risks escalated and accepted onto the Board-level Risk Register (HBRR), individual services within Service Groups record and manage operational risks to their service provision within local risk registers, captured within the Datix system. At the beginning of September 2025, there were 625 recorded at service level as having a current risk score of 9 or above by individual risk owners within the context of the services they provide. These can be summarised by Type as below (further detail by Sub-Type is presented at Appendix 3).

| NUMBERS OF RISKS SCORED 9+ BY RISK TYPE | MHLD | Morriston | NPTS | PCT | Total |
| --- | --- | --- | --- | --- | --- |
| Risk Type |  |  |  |  |  |
| Compliance with legislation and Statutory/regulatory inspections | 4 | 11 | 10 | 7 | 32 |
| Environment, Estates and Infrastructure | 19 | 22 | 15 | 3 | 59 |
| Financial Management | 4 | 6 | 3 | 7 | 20 |
| Governance and Assurance | 8 | 4 | 5 | 14 | 31 |
| Health and Safety | 6 | 9 | 7 | 2 | 24 |
| Health Promotion & Protection | 2 | 1 | 2 |  | 5 |
| Information Governance and Communication | 3 | 5 | 3 | 4 | 15 |
| Medical Devices, Equipment &Supplies |  | 45 | 35 | 7 | 87 |
| Patient Safety | 11 | 15 | 10 | 9 | 45 |
| Sustainable Services | 11 | 78 | 52 | 19 | 160 |
| Workforce & OD | 20 | 47 | 36 | 44 | 147 |
| Grand Total | 88 | 243 | 178 | 116 | 625 |

Risks are reviewed at Service Group level via local governance mechanisms and considered in the context of services provided. Policy requires that where a Service Group considers that risks cannot be managed within the Service Group alone or are assessed as exceeding the Health Board’s risk appetite, they are escalated corporately for review.

Corporate review is undertaken via the monthly Risk Management Group. The Group is chaired by the Executive Medical Director (vice-chair is the Executive Director of Nursing & Patient Experience) with representation from each service group and corporate directorate. Risks escalated are considered for addition to the Board-level Risk Register in the context of health board wider objectives and with consideration to the Board’s appetite.

In addition to the escalation process, the Risk Management Group has received presentations from Service Groups on their processes and the risks being managed. The Group has received an analysis and details of the operational risk register entries being managed within services and is reviewing its approach to ongoing oversight of service level risk management currently.

3	GOVERNANCE AND RISK ISSUES

The purpose of this report is to highlight significant risks associated with Health Board business. It highlights those currently assessed at levels that reach the appetite level of the Board and presents an overview of movements in risks. Supported by the Health Board Risk Register which accompanies this report, it presents key controls in place and further actions being taken to manage risks, the lead Directors accountable for their management and the Committees overseeing the same.

4	FINANCIAL IMPLICATIONS

This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case, they are highlighted within individual risk register entries or dedicated board/committee papers for information.

5.	RECOMMENDATIONS

Members are asked to:

- RECEIVE an update on progress with the development of the strategic risk register.

- RECEIVE for assurance purposes the Health Board Risk Register (HBRR) and summary of movements.

- RECEIVE a summary of the risks recorded and managed by services/specialties within Service Group operational risk registers.

- CONSIDER whether further assurance is required on risks and their management.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | This report updates on risk matters received in May 2025. |  |
| Appendices |  | Appendix 1 – Strategic Risk Register Appendix 2A – Health Board Risk Register (HBRR) Risks Appendix 3 – Summary of Risk Types & Sub-Types |  |