| Meeting Date | 16 September 2025 |  | Agenda Item |  |  | 2.6 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Audit Committee |  |  |  |  |  |
| Report Title | Speaking up Safely and Guardian Service End of Year Report 2024-5 |  |  |  |  |  |
| Report Author | Julie Lloyd, Head of Culture, OD & Staff Experience |  |  |  |  |  |
| Report Sponsor | Tina Ricketts, Director of Workforce & OD |  |  |  |  |  |
| Presented by | Julie Lloyd, Head of Culture, OD & Staff Experience |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to provide assurance through evidencing delivery of actions set out in the Internal Audit report on Speaking Up Safely as per the agreed timeframes. The report includes the Guardian Service End of Year Report for 2024-5. |  |  |  |  |  |
| Key Issues | The January 2025 internal audit report was issued with a ‘limited assurance’ rating. This recognised the need for organisation-wide ownership of the speaking up safely agenda. This report provides assurance by detailing the continued progress made against the Internal Audit Report recommendations and specific Workforce & OD actions within the agreed timeframes. In addition to those actions requiring delivery by the end of March and June 2025, particular focus is given to recommendation 3.2 requiring Service Groups to “amalgamate the detail of concerns raised (themes, trends, actions taken, lessons learned) and report to a Board subcommittee to have an organisation-wide understanding of incidents arising. The reporting should also provide assurance that policy requirements, including timescales etc, are being adhered to”. The Guardian Service End of Year Report, 2024-5 is detailed in appendix 2 and includes activity over the previous financial year, recommendations and actions to be taken to mitigate or address these. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | The Audit Committee is asked to: - RECEIVE the Guardian Service End of Year Report for 2024-5. - BE ASSURED by the continued progress against the Internal Audit Report recommendations and actions committed to are completed and by the given timeframes. - BE ASSURED by the central capture and reporting of concerns raised (themes, trends, actions taken, lessons learned) by Service Groups through agreed monitoring governance mechanisms. |  |  |  |  |  |

SPEAKING UP SAFELY AND GUARDIAN SERVICE END OF YEAR REPORT 2024-5

- INTRODUCTION

The purpose of this report is to provide assurance by evidencing continued delivery of actions set out in the Internal Audit report on Speaking Up Safely as per the agreed timeframes.  It also includes the Guardian Service End of Year Report for 2024-5.

- BACKGROUND

Swansea Bay University Health Board is committed to enabling our people to feel safe and confident to speak up and ensuring that when they do, we listen and act. It is the cornerstone of our People Strategy; People Aim 1 – Engaged motivated and Healthy. It also supports us deliver our Strategic Objective, which commits to the Health Board being a great place to work, where staff feel valued and work together towards a common goal.

An Internal Audit Report was issued in January 2025. The purpose of the audit was to ‘review the implementation of the National Speaking Up Safely Framework and assess its impact in promoting a culture that enables staff to raise concerns’.  The report was issued with a ‘limited assurance’ rating, recognising the need for organisation-wide ownership of this agenda.

It was noted that whilst Speaking Up Safely sits under the Director of Workforce & OD as the accountable Executive Officer with the Chair as the Non-Executive Sponsor, that it is everyone’s responsibility and stakeholder engagement across the Health Board is essential for successful delivery of the National Framework and its requirements.

2.1 Continued Delivery of IA Recommendations

To implement the National Speaking Up Safely Framework and as part of promoting a culture that enables staff to raise concerns, Table 1 below outlines actions completed and provides an up-dated position on those on-track actions (due between August 2025 and March 2026).  It is important to note that the progress outlined has been completed in collaboration with stakeholders, particularly those part of the Speaking Up Safely Working Group and Service Groups.  Links have also been made with Deputy Director of Therapies and Health Sciences to join the dots with their Professional and Governance Group. The revised Speaking Up Safely Action Plan 2025-6 has also been updated to highlight those actions completed and is attached in appendix 1.

Table 1.

| Action | Status / Progress | Responsible Lead | Timeframe |
| --- | --- | --- | --- |
| IA Action 1.1 Revisit and refresh the action plan to ensure the actions remain appropriate, including consideration to incorporate the recommendations raised by the Guardian Service End of Year Report. The revised action plan will be approved by the Speaking Up Safely Working Group. | COMPLETED See appendix 1 and appendix 2. | Director of WOD | 31st March 2025 |
| IA Action 1.2 Outputs of the Speaking Up Safely Working / Stakeholder Group are to be monitored and reported quarterly via the Workforce & OD Delivery Group and 6-monthly via the Health Board Workforce & OD Committee. | ON-TRACK Speaking Up Safely Working Group established in November 2024, meeting bi-monthly since. Reporting to commence with a minimum of twice yearly in line with the agreed reporting structure. | Director of Workforce & OD | July / August 2025 and Feb/March 2026 |
| IA Action 1.3 Work with Corporate Governance to develop a risk for the risk register to be monitored by Workforce & OD Committee. | COMPLETED Included as part of WOD Committee Report on 10th April 2025. | Interim Director of WOD | 31st March 2025 |
| IA Action 2.1 Finalise the review and launch of training modules and information on Speaking Up Safely, including the development of the ‘Brilliant Basics’ bitesize learning opportunities. | COMPLETED Work finalised in partnership with stakeholders and as part of the Speaking Up Safely Working Group to enhance our Raising Concerns hub and develop resources as part of the ‘Brilliant Basics’ Management Development platform. In addition to the hub itself, resources include a Speaking Up Safely Webinar accessible for all staff and teams, a printable toolkit and poster with QR code for display across areas. This was launched during Team Brief in June and cascaded through Service Groups. See links: Raising Concerns Hub Hanfodion Hwylus / Brilliant Basics - Home | Director of Workforce & OD | 30th June 2025 |
| IA Action 3.1 Development of an integrated report including data from all sources that receive concerns should be finalised to empower the health board to have complete oversight of all concerns, themes and trends. | ON-TRACK Investigations commenced, connecting with other NHS Wales organisations to understand their provision and how they gather concerns raised. See section 2.2 of this report. A national Speaking Up Safely Learning Exchange has also been set up with Health Board Speak Up Leads to exchange learning and best practice. A demonstration held with provider of the digital platform, Work in Confidence (which a majority of NHS Wales use), on 14th March 2025. | Director of Workforce & OD | 31st March 2026 |
| IA Action 3.2 Service Groups should amalgamate the detail of concerns raised (themes, trends, actions taken, lessons learned) and report to an appropriate Board-level committee to have an organisation-wide understanding of incidents arising. The reporting should also provide assurance that policy requirements, including timescales etc, are being adhered to. | ON-TRACK The first round of rotational reporting will embed local reporting from Service Groups into the overarching Speaking Up Safely Report and take place a minimum of twice yearly. Morriston & PCTS are to report in August with MHLD and NPTS Service groups to report in February/March 2026 WOD Committee alongside the overarching Speaking Up Report. Figures 1a and 1b below, provide a visual extract from the central live template used by Service Groups to both locally self-assess against section 6 of the national framework and capture key concerns, themes, actions taken and lessons learned. Access to the template has been issued to audit. | Interim Director of Workforce & OD and Service Groups | 14th August 2025 and Feb/March 2026 WOD Committee |

Figure 1a.

Figure 1b.

  - Guardian Service End of Year Report 2024-5

The Guardian Service End of Year Report, 2024-5 is detailed in appendix 2 and includes activity over the last financial year, recommendations and actions to be taken to mitigate or address these.  It should be acknowledged that since the report was drafted in April, progress has already been made against a number of actions/recommendations.

A summary of the main concern themes reported for 2024-5 and action being taken is summarised in table 2 below.  Full details are also provided in the action plan of appendix 2.

Table 2.

| Main Concern Themes | Action Taken |
| --- | --- |
| Management Concerns and System/Process | ER cases reviewed monthly by the HR BPs with the Operational HR teams. HR BPs working with services / managers to provide support/guidance to employees where cases are prolonged/not in line with process. Best Practice Review working group introduced. ER Case dashboard is to be developed Training, resources and guidance for Managers is being built into the Brilliant Basics Platform in addition to stand alone training sessions offered. Progress up-date on the Best Practice Review to be presented to WOD Committee in October 2025. |
| Behaviour/Relationship | Health Board pledged commitment to modelling compassionate leadership from Ward to Board and in all interactions; promoting a culture that supports honest conversations, mutual respect, great team working and continuous development as part of the ‘One Bay Way’ ethos. A review of our behaviour-based leadership development programmes for alignment to our values and compassionate leadership principles – new offer due for launch September 2025. Re-launch of Healthy Working Relationships and Civility Webinars in June 2025. Compassionate Leadership Toolkit built into ‘Brilliant Basics’ Management Platform. |
| Patient Safety/Quality | Individual cases/issues addressed directly by Service Groups i.e. Test of Change in Morriston’s Emergency Department, independent reviews in Gorseinon Hospital, Mental Health and Learning Disabilities, Maternity and Neonatal services and subsequent reports, recommendations and actions to be addressed. Planned Care Training Academy launched Quality Improvement Coaching Unannounced Quality Assurance Audits across areas Quality & Safety improvement hub and dashboard developed and launched. |

Further to the Internal Audit Report’s limited assurance rating issued earlier in the year, work has been undertaken to compare Speaking Up provision with other organisations across NHS Wales and share best practice through an All Wales Speaking Up Safely Learning Exchange.  A high-level summary of provision across Wales is outlined in appendix 3.

Links are also being made with Speak Up Leads in NHS England where there is further experience and evidence of outcomes. Connection has also been made with Independent Reviewer, Melanie Walker, to learn from her experience in the space of Speaking Up Safely and share learning and best practice once the review within Mental Health and Learning Disabilities is finalised.

It is essential to ensure a provision and infrastructure for staff to speak up that also provides value for money in the current financial climate.  Further work will therefore be undertaken to maximise the remaining term of the Guardian Service Contract and review the alternative options and associated costs available.

- GOVERNANCE AND RISK ISSUES

Delivery of Section 6 of the national Speaking Up Safely Framework is reliant on Service Delivery Groups taking action to respond.  Capacity and operational pressures continue to present a risk in Service Delivery Groups being able to respond and deliver in the agreed timeframes.

- FINANCIAL IMPLICATIONS

The sustained cost and value for money from the Guardian Service are risks in the current financial climate of the Health Board.  Work will be undertaken to review alternative options to mitigate against these risks and ensure staff remain safe and able to raise concerns anonymously, in addition to the other internal options available to them.

- RECOMMENDATION

The Audit Committee is asked to:

- RECIEVE the Guardian Service End of Year Report for 2024-5.

- BE ASSURED by the continued progress against the Internal Audit Report recommendations and actions committed to are completed and by the given timeframes.

- BE ASSURED by the central capture and reporting of concerns raised (themes, trends, actions taken, lessons learned) by Service Groups through agreed monitoring governance mechanisms.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☐ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☐ |
|  | Effective Care |  | ☐ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Our Speaking Up Safely offerings, including the Guardian Service aims to improve staff experience through helping to create a culture of openness and honesty. The direct correlation between patient experience and staff experience is well documented. The previous Raising Concerns process with no dedicated pathway or infrastructure to support staff created risk to staff, patients and the wider organisation. |  |  |  |
| Financial Implications |  |  |  |
| The sustained cost and value for money from the Guardian Service are risks in the current financial climate of the Health Board. Work will be undertaken to review alternative options to mitigate against these risks and ensure staff remain safe and able to raise concerns anonymously in addition to the other internal options available to them. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is important to consider the internal policies and the legislation which are linked to the provision of a confidential, safe and effective pathway and process for staff to raise concerns. Internal policies include but are not limited to – -Respect & Resolution -Disciplinary Policy -Procedure for NHS Staff Raising concerns -NHS Wales Speaking Up Safely Framework Public Interest Disclosure Act 1998 If workers bring information about a wrongdoing to the attention of their employers or a relevant organisation, they are protected in certain circumstances under the Public Interest Disclosure Act 1998. This is commonly referred to as 'blowing the whistle'. The law that protects whistle-blowers is for the public interest - so people can speak out if they find malpractice in an organisation. Blowing the whistle is more formally known as 'making a disclosure in the public interest'. Duty of Candour, 2023 The duty of candour is a legal requirement for all NHS organisations in Wales. It requires them to be open and transparent with service users when they experience harm whilst receiving health care. They will be required to: - talk to service users about incidents that have caused harm - apologise and support them through the process of investigating the incident - learn and improve from these incidents - find ways to stop similar incidents from happening again |  |  |  |
| Staffing Implications |  |  |  |
| Delivery of Section 6 requirements of the national speaking up safely requirement is reliant on Service Delivery Groups taking action to respond. Capacity and operational pressures may therefore present a risk in Service Delivery Groups being able to respond and deliver in the agreed timeframes. In turn, this may result in delayed improvements towards a culture that enables staff to raise concerns and a continued limited assurance assessment. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The paper impacts on the Well-being of Future Generations (Wales) Act 2015 as it will impact on the long-term culture and behaviours of the organisation and its staff now and in the future. It aims to support staff, through working together to improve staff wellbeing and improve the quality of patient care and outcomes through early raising of concerns, intervention and nipping concerns in the bud before they escalate. |  |  |  |
| Report History |  | - Presented to WOD Committee, 10th April 2025 - Presented to WOD Delivery Group, 29th July 2025 - Presented to WOD Committee on 14th Aug 2025 - Presented to Management Board on 20th Aug 2025 |  |
| Appendices |  | Appendix 1 – Updated Speaking Up Safely Action Plan 2025-6 Appendix 2 - The Guardian Service End of Year Report, 2024-5 Appendix 3 - Summary of Speaking Up provision across NHS Wales |  |