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	For Discussion
	Report Summary; detailing any action required

	This paper provides an update to the Audit Committee on the current status of the recommendations arising from the NHS Wales Shared Services Partnership Audit and Assurance Report on Discharge Planning, undertaken in January 2025.
The paper identifies areas where progress has been made, areas where actions have been implemented but not yet embedded or sustained, and areas where delivery remains dependent on clearer operational accountability, resourcing, digital infrastructure and implementation of revised patient flow arrangements.
While there has been progress in relation to Discharge to Recover and Assess, pathway redesign, discharge policy development and elements of optimal hospital flow, the overall position is that a number of recommendations cannot yet be considered fully closed. A more robust delivery plan is required, with named ownership, milestones, evidence of implementation and a clear route for assurance through Urgent and Emergency Care governance.

	Key Issues

	· The key issues for the Committee are:
· A number of audit recommendations have been progressed, but not all are fully implemented, embedded or sustained across the Health Board.
· There is currently no single operational lead with clear Health Board-wide accountability for discharge planning, patient flow and the coordinated delivery of the outstanding audit actions.
· Delivery has been impacted by variable access to improvement and clinical leadership resource, particularly in relation to the Optimal Hospital Flow Framework and the Integrated Discharge Hub model.
· The Integrated Discharge Hub remains a central enabler for D2RA, trusted assessor arrangements and standardised access to Pathway 2 and Pathway 3 provision, but the required leadership and workforce model has not yet been fully confirmed.
· Some areas of implementation are dependent on digital capability that is not yet available. In the interim, manual measurement and escalation arrangements need to be strengthened.
· The current position presents an operational, quality and patient safety risk because delays in discharge and transfer can increase length of stay, deconditioning, avoidable harm and pressure on acute bed capacity.
· Organised for Success may provide a future structural solution, but the Committee will require assurance on the interim controls in place before that structure is implemented.

	Decision / Action required
	Choose requirement

	Recommendations

	The Audit Committee is asked to:

· CONSIDER the progress made against the NWSSP Audit and Assurance recommendations on discharge planning.
· BE AWARE that a number of recommendations remain only partially implemented, not yet embedded, or not yet sustained across the Health Board.
· BE AWARE of the interim governance arrangements, named ownership and delivery milestones for the outstanding actions.
· BE AWARE of the plan to establish a single discharge and patient flow action tracker, reporting through Urgent and Emergency Care governance.
· AGREE to a receive a report in the January Committee to update on the progress; setting out evidence of implementation; residual risks and recommendations proposed for closure of actions.




NWSSP Audit and Assurance Report: Discharge Planning – a review of the actions.

1. INTRODUCTION

This report has been prepared at the request of the Audit Committee and provides an update on the current status of the recommendations arising from the NWSSP Audit and Assurance Report on Discharge Planning, undertaken in January 2025.

The purpose of this update is to provide assurance on progress made, identify recommendations that remain open or only partially implemented, and set out the further action required to ensure that improvements in discharge planning and patient flow are embedded and sustained across the Health Board.

2. BACKGROUND

The Health Board has undertaken a range of improvement programmes linked to discharge planning, the Discharge to Recover and Assess model, the Optimal Hospital Flow Framework and the introduction of internal professional standards. These areas are all referenced in the NWSSP audit report and remain central to improving patient flow, reducing delays in discharge and supporting safe, timely care.

Initially, this work was overseen through the Urgent and Emergency Care Board. In February 2025, a Memorandum of Understanding was agreed between Neath Port Talbot Council, Swansea Council and the Health Board, confirming a shared commitment to the delivery of Discharge to Recover and Assess as a key priority. The aim was to reduce the number of clinically optimised patients remaining in hospital and the associated bed days used by this patient group.

Progress has been made in a number of areas. However, implementation has not been consistent across the Health Board and some areas of work have not yet been embedded or sustained. Until recently Delivery was affected by the availability of improvement resource.  The continued absence of a single operational lead for discharge and flow, and limitations in digital infrastructure remain current issues which are being progressed.



Key achievements:
· Redesign of Pathway 1, including greater standardisation of processes across the region.
· Development of a Health Board discharge policy covering optimal hospital flow, patient choice and reluctant discharge.
· Agreement of a trusted assessor model, although this remains only partially implemented and is dependent on a resourced Integrated Discharge Hub.
· Process mapping of discharge pathways, with revised processes intended to reduce pathway delays.
· Revised clinically led pathway management arrangements for stroke rehabilitation.
· Reduction in delays for reablement in the community.
· Development of an optimal hospital flow dashboard with key performance indicators accessible to ward teams.

These achievements demonstrate that improvement work has taken place. However, several of these areas require further evidence of consistent implementation, embedding and sustainability before the associated audit recommendations can be considered fully closed.

Work in progress:
The following areas remain work in progress:

· Development of pathway event timescales and an escalation framework for managing pathway delays.
· Development of Pathway 3 ward arrangements for patients requiring new residential or nursing care placements.
· Further development of the Integrated Discharge Hub model, including confirmation of leadership, workforce, scope and prioritisation arrangements.
· Agreement of a consistent Health Board-wide approach to monitoring compliance with internal professional standards and escalation of non-compliance.

Work implemented – not sustained.
Some improvement actions have been implemented but cannot yet be described as embedded or sustained:

· Internal professional standards were implemented in Morriston and relaunched during the Urgent and Emergency Care test of change in June 2025. However, recent review indicates that the standards are not consistently embedded. There is currently no reliable digital mechanism to monitor compliance and escalate delays, meaning that measurement is dependent on manual reporting.
· Criteria-led discharge pilots have taken place in Morriston. A policy and competency framework are in place. However, uptake remains variable because criteria-led discharge is dependent on medical teams documenting discharge criteria in a consistent and timely way to enable nursing colleagues to act.

Robust monitoring, clinical engagement and escalation arrangements are being developed but until they are in place the work cannot be considered sustained.

Operational Accountability and Patient Flow Infrastructure
The current management of discharge and patient flow across the Health Board is fragmented. Previously, there was a senior post holder funded jointly by Health and Social Care who led integrated discharge pathways and processes. This role no longer exists.

There is currently no single operational lead with Health Board-wide accountability for discharge and patient flow. Responsibility sits within individual Service Groups, which has contributed to variable implementation of the audit recommendations and inconsistent practice across sites.

Until the Organising for Success structure is implemented, interim accountability should be clarified. Executive accountability sits with the Chief Operating Officer, with operational delivery led through Urgent and Emergency Care governance and Service Group triumvirates. The Assistant Director of Operations UEC (interim) will coordinate the outstanding audit actions and report progress through a single discharge and patient flow action tracker.

Discharge to Recover and Assess / Integrated Discharge Hub
In January 2025, external consultants were commissioned to support implementation of the Discharge to Recover and Assess model in partnership with Local Authority partners. A multi-agency discharge event was held in April 2025 and actions were agreed. Some actions have since progressed through tests of change; others have not been implemented, in part due to cost and resource constraints.

The Health Board has not yet delivered all key recommendations linked to D2RA. The most significant outstanding issues are:

· Resourcing of the Integrated Discharge Hub as the multidisciplinary function central to delivery of D2RA pathways and trusted assessor arrangements.
· Appointment of a senior integrated leader, employed in partnership with Local Authorities, to lead the Integrated Discharge Hub, coordinate policy and training, develop pathways of care and reduce reliance on long-term care.

The Integrated Discharge Hub remains a key enabler for standardising discharge processes, coordinating Pathway 2 and Pathway 3 access, and strengthening escalation across Health and Social Care. Without a clearly resourced hub and named leadership, the Health Board is unlikely to fully embed the D2RA model or close all related audit recommendations.

Regional Partnership and Policy Development
Work to improve discharge and transfer arrangements has continued through the Community and Older Persons Regional Partnership Board. However, this has been a prolonged programme of work and some key operational enablers remain outstanding, particularly the leadership role and the central Integrated Discharge Hub.

Policy development has been aligned to this wider discharge pathway programme. However, until pathway design and implementation arrangements are finalised, the supporting policies will remain limited in their impact.

First drafts of the following policies are due to be presented to the UEC Board in September for approval:

· SAFER flow policy.
· Discharge policy, including reluctant discharge and patient choice.

The approval of these policies should be accompanied by an implementation plan setting out training requirements, compliance monitoring, escalation arrangements and evidence required to support audit closure.

Internal Professional Standards
Internal professional standards were introduced as part of the Urgent and Emergency Care test of change in Morriston in June 2025. They have not yet been launched on a Health Board-wide basis.

Recent changes have been made to the standards, but the key challenge remains the ability to measure compliance and escalate non-compliance. In the absence of a reliable digital solution, the Health Board should agree an interim manual reporting process covering a small number of core measures. These should be reported through UEC governance until digital functionality is available.

Suggested core measures include:

· Number of clinically optimised patients.
· Delay by pathway.
· Pathway 1, Pathway 2 and Pathway 3 volumes and waits.
· Number of patients exceeding agreed pathway time standards.
· Compliance with ward-level internal professional standards reporting.

Criteria-Led Discharge
Implementation of criteria-led discharge remains variable. Pilots have taken place in Morriston Hospital and a policy and competency framework are in place. However, consistent delivery is dependent on clinical engagement and on medical teams documenting clear discharge criteria in the designated format.

Further action is required to secure consultant and multidisciplinary team engagement, agree priority specialties or wards for implementation, monitor utilisation, and escalate areas where criteria-led discharge is not being used appropriately.

Digital Infrastructure
The absence of an integrated electronic patient record remains a limitation. Patient information is held across multiple systems, which restricts the ability to monitor discharge pathway milestones, internal professional standards and reasons for delay in real time.

The audit report refers to reconciling SIGNAL entries with the Welsh Nursing Care Record. However, these systems are designed to deliver different outputs, and capturing reasons for changes in SIGNAL within WNCR may not provide meaningful operational benefit to ward multidisciplinary teams.

The key requirement is a pragmatic interim reporting approach while longer-term digital solutions are developed. The Health Board should agree the minimum dataset required for discharge and flow oversight and ensure this is reported consistently through UEC governance.

National Programme Context
The Six Goals Programme for Urgent and Emergency Care formally closed in March 2026. The work programme has been replaced by the National Strategic Programme for Urgent and Emergency Care, which spans the whole urgent care pathway.
The outstanding discharge planning recommendations should be mapped to the new national programme to ensure that local delivery remains aligned to national expectations, available funding streams and performance requirements.

3. GOVERNANCE AND RISK ISSUES

The report identifies clear gaps in the operational delivery and oversight of patient flow and discharge planning. The principal governance issue is the absence of a single operational lead with Health Board-wide accountability for coordinating delivery of the outstanding audit recommendations.

This risk may be mitigated in the longer term through Organised for Success and the development of Clinical Care Boards with central supporting structures, including patient flow. However, this does not fully address the immediate risk.

Interim governance arrangements will therefore be strengthened as follows:

· Confirm executive accountability through the Chief Operating Officer.
· Identify a named interim operational lead for discharge and patient flow.
· Establish a single discharge planning audit action tracker.
· Report progress monthly through the Urgent and Emergency Care Board.
· Define evidence requirements for each recommendation before closure is proposed.
· Escalate risks relating to resource, digital capability or partner dependency through existing executive governance routes.

Consideration is also being given to appointing an integrated manager, jointly funded by Health and Local Authority partners, to lead the discharge agenda, coordinate the Integrated Discharge Hub, support policy and procedure development, and act as a senior point of escalation across Health and Social Care.

4.  OPEN AUDIT RECOMMENDATIONS: 

The detailed status of the recommendations is included at Appendix 2. However, for assurance purposes, the Committee should receive a concise summary of the open recommendations within the body of the report.
It is recommended that each recommendation is categorised as:

· Implemented and evidenced.
· Implemented but not yet embedded.
· Partially implemented.
· Not yet implemented.
· Dependent on further resource, digital development or organisational change.

Each open recommendation should include a named owner, target completion date, evidence required for closure and current RAG status. This will allow the Committee to track whether the Health Board is moving towards closure and whether residual risks are being managed.

	Theme
	Current status
	Evidence
	Gap to close
	Owner
	Target date

	D2RA pathway implementation
	
	Pathway 1 redesign and process mapping
	Standardisation of Pathway 2 and 3 arrangements
	Assistant Director Ops: UEC
	End October 26

	Integrated Discharge Hub
	
	Model described
	Hub resourcing and leadership not confirmed
	Associate Director PCCT pending Executive decisions regarding resource
	End Nov 26

	Internal professional standards
	
	Morriston test of change
	Not Health Board-wide; limited measurement
	Executive Medical Director
	End Nov 26

	Criteria-led discharge
	
	Policy, competency framework and pilots
	Variable clinical uptake

	Service Group Medical Directors
	End Nov 26

	Digital flow measurement
	
	Dashboard partly available
	No reliable automated compliance measurement
	Director of Digital Services
	Unknown – dependant on new digital infrastructure



5. FINANCIAL IMPLICATIONS

The resourcing of critical roles in discharge and patient flow may be partly addressed through reorganisation of existing resources to develop a central patient flow team and Integrated Discharge Hub. However, even if existing discharge and transfer teams are mobilised into a central model, the hub is likely to remain relatively small and will need to prioritise its activity clinically.

The previous jointly funded integrated leadership post is no longer in place. It is unclear where the funding for this post has been redirected. This role remains important to the development of the Integrated Discharge Hub and the management of discharge and transfer across the Health Board.

Welsh Government has ringfenced approximately £250k to support implementation of the Optimal Hospital Flow Framework, subject to a successful bid and achievement of agreed flow key performance indicators. Failure to meet the funding conditions would reduce available improvement capacity and create a risk to delivery of the outstanding audit recommendations.

Mitigating actions should include confirmation of KPI ownership, monthly monitoring of funding conditions, and an agreed fallback plan if funding is not released or cannot be sustained beyond March 2027.

6. RECOMMENDATIONS

The Audit Committee is asked to:
· CONSIDER the progress made against the NWSSP Audit and Assurance recommendations on discharge planning.
· BE AWARE that a number of recommendations remain only partially implemented, not yet embedded, or not yet sustained across the Health Board.
· BE AWARE of the interim governance arrangements, named ownership and delivery milestones for the outstanding actions.
· BE AWARE of the plan to establish a single discharge and patient flow action tracker, reporting through Urgent and Emergency Care governance.
· AGREE to a receive a report in the January 2027 Committee to update on the progress; setting out evidence of implementation; residual risks and recommendations proposed for closure of actions.

	Governance and Assurance

	Strategic Objectives

	Strategic Objectives
(please choose which is impacted)
	People of Swansea Bay live healthier, fairer and more prosperous lives
	☐
	
	Care is high quality, safe, efficient and delivers the best possible outcomes for people in partnerships  
	☒
	
	Care is delivered in partnership with our communities in safe and appropriate setting, supported by innovation
	☐
	
	The health board is a great place to work where staff feel valued and work together towards a common goal
	☐
	
	The health board is a resilient, sustainable and responsible organisation
	☐
	Health and Care Standards

	Standards (please choose which applies)
	Safe Care
	☐
	
	Timely Care
	☐
	
	Effective Care
	☒
	
	Efficient Care
	☐
	
	Equitable care
	☐
	
	Person-centred Care
	☐
	
	Staff and Resources
	☐
	Enablers (please choose which applies)
	Whole Systems Approach
	☒
	
	Leadership
	☐
	
	Workforce
	☐
	
	Culture
	☐
	
	Information 
	☐
	
	Learning, Improvement and Research
	☐
	Quality, Safety and Patient Experience

	Discharge planning and patient flow have a direct impact on patient safety, quality of care and patient experience. Delays in discharge and transfer can increase the risk of deconditioning, hospital-acquired harm, reduced independence, poorer patient experience and avoidable length of stay. Delayed flow also reduces acute bed availability and affects the Health Board’s ability to manage urgent and emergency care demand.
The outstanding audit recommendations should therefore be considered both an operational delivery issue and a patient safety issue. Strengthening discharge pathways, internal professional standards, criteria-led discharge and Integrated Discharge Hub arrangements will support safer, more timely care and reduce exposure to delay-related harm.

	Financial Implications

	Resource constraints have affected the pace and consistency of delivery against the audit recommendations. There is potential to address some of these constraints through Organising for Success and the realignment of existing resources into a central patient flow and Integrated Discharge Hub model.
Funding is available through Welsh Government to support Optimal Hospital Flow Framework implementation, but this is conditional on agreed performance requirements being met. The Health Board should therefore identify the value at risk, confirm ownership of the relevant KPIs, and monitor the impact of any failure to secure or sustain this funding.
There is no confirmed recurrent solution for ongoing training and support in relation to discharge and flow. This presents a sustainability risk if implementation is dependent on short-term programme funding.

	Legal Implications (including equality and diversity assessment)

	There are no specific legal implications identified in this report. However, discharge arrangements must continue to comply with statutory duties relating to safe care, mental capacity, safeguarding, equality and partnership working with Local Authority partners.
Any revised discharge policy and pathway arrangements should be subject to appropriate equality and impact assessment before full implementation.

	Staffing Implications

	The report identifies a number of staffing implications linked to discharge planning, patient flow and the Integrated Discharge Hub. These include the need for clear operational leadership, sufficient improvement and training capacity, and appropriate multidisciplinary input across Health and Social Care.
The proposed approach does not currently assume additional expenditure, but delivery may require realignment of existing resources through Organising for Success and confirmation of partner contributions where integrated posts are required.

	Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015)

	Sustained improvement in discharge planning and patient flow will support the Health Board’s long-term objectives by reducing avoidable length of stay, improving patient outcomes, supporting independence and making more effective use of hospital capacity.
The work aligns with the Well-being of Future Generations (Wales) Act 2015 through its focus on prevention, integration, collaboration and long-term sustainability. However, these benefits will only be realised if the improvement work is embedded through clear governance, consistent operational delivery and reliable performance measurement.

	Report History

	Previous updates provided-no formal report history.

	Appendices

	Appendix 1:



Appendix 2:
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Executive Summary

Purpose

To review the arrangements in place within the health board for the timely and safe discharge of patients and whether established processes are being adhered
to, including progress in implementing the actions agreed with management to address the issues identified in the previous internal audit report (SBU-1920-
025). This review has been limited to the arrangements and mechanisms within the health board to facilitate the discharge of patients.

Overview

Since our previous review, the health board has embedded the use of SIGNAL, its in-house patient flow system, and incorporated SAFER (Seen, Aim, Flow,
Early Discharge, Recovery) principles within ward rounds, to support the discharge planning process. Through recent externally facilitated discharge planning
and patient flow reviews, the health board has identified a number of process and system issues, including external constraints within social care, which are
preventing the operation of Discharge to Recover and Assess (D2RA) model in its intended form, with extended length of stay providing further challenges in
identifying and agreeing the level of support patients require. Our review of patient records and SIGNAL noted similar issues impacting the timely discharge of
patients, alongside areas for improvement for the health board to comply with national discharge/patient flow guidance, and where detail and documentation
could be improved.

The Urgent and Emergency Care Summit, held by Management Board in October 2024, set out the actions, and preliminary timescales, required to address
the gaps identified from the above referenced external reviews. The operational management and delivery of actions by partners or third parties was excluded
from the scope of this audit, however we noted the health board’s recent development of an Integrated Discharge Strategy and the phased roll out of the
Integrated Discharge Hub (IDH) demonstrates alignment with partners within this area. Whilst IDH operation is yet to be embedded at all acute sites,
performance data shared at the UEC Programme Board in November 2024 indicated the initial impact has been positive.

We have concluded reasonable assurance on this area reflecting the arrangements for planning, monitoring and reporting of patient discharges. It will take
time for recently agreed actions to be embedded and improvements to be realised; and at time of audit fieldwork concluding, performance and outcomes
remain a significant challenge as is the case for all NHS organisations in Wales.

The matters requiring management attention include:

e Welsh Government hospital discharge guidance has been adopted by the health board, but this does not offer standards for completion, quality or
ongoing audit requirements. The development of a discharge toolkit or policy could strengthen this area.

e Criteria Led Discharge protocol has been adopted by Morriston; however, it has not been formally approved, and would benefit from greater engagement
and promotion.

e The health board does not undertake formal discharge planning training or quality improvement programmes to support all sites.

e Review of records identified occasions where expected discharge dates had not been assigned in line with guidance, and the need to improve
documentation.

e Action plans from recent discharge planning/patient flow reviews have been developed, however some initial timescales have not been met and, noting
the cross over between these, there is opportunity to combine within one improvement plan to assist in monitoring and oversight.

e Reporting against UEC Programme 3 (‘Acute Hospital Flow and Discharge’) is limited to updates for the Morriston site only, and the narrative does not
reflect current action status.

Full details of matters arising are detailed within the Findings & Agreed Action Plan. Review of progress in implementing the recommendations raised (see
Appendix A) within the previous internal audit report has identified five actions which can be closed within the audit tracker; and for those which remain
outstanding we have indicated where these are superseded by recommendations raised within this review.





Scope & Assurance Summary

Objectives Related Findings Assurance

Guidance is available for staff on discharge processes and responsibilities are
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Findings & Agreed Action Plan

Objective 1: Guidance is available for staff on discharge processes and responsibilities are clearly outlined. Reasonable

The health board applies the Welsh Government’s Hospital Discharge Guidance (issued December 2023). Noting its coverage, including standards, tasks and
responsibilities, the health board decided not to review its SAFER Flow Policy which was previously used. The National Six Goals Programme has also provided
operational guidance through the Optimal Hospital Patient Flow Framework (‘the Framework”) which refines and collates the ward-based principles to support
effective discharge planning. A recent externally facilitated review of all patients with a length of stay in excess of 21 days (see audit objective two),
identified instances where roles and responsibilities between health board teams, staffing groups, and partner organisations could be further clarified (see Key
Finding 1). Noting also the recent implementation of the Integrated Discharge Hub (IDH), there could be consideration of including key documents, in support
of regional working, within the centralisation of discharge planning resources. (see Key Finding 1).

A local protocol is in use within both Morriston and Singleton Hospitals to support the adoption of Criteria Led Discharge (CLD), however we note that the
protocol has not been formally approved and take-up could be improved through greater engagement. (see Key Finding 2).

A structured roll out of SAFER principles at the Morriston site in 2023 was accompanied by a programme of ward training and follow up/quarterly reviews. Due
to the reduction in the team’s capacity this has since been discontinued (Q2/2023), and there is now focus on supporting Medicine wards with clinically
optimised patients (COPs) through daily deep dives. Whilst wards on other sites have received support in adopting SAFER principles, we could not identify
similar programmes, or a health board wide quality improvement approach to discharge planning. (See Key Finding 3)

Resources and services to support discharge planning have been collated to inform staff planning, and within Morriston the SAFER champion role is to be
introduced; but currently, there is not a standard approach to discharge planning training to promote SAFER and other productive ward initiatives. We also
identified limited uptake of the national Discharge to Recover and Assess (D2RA) training. (See Key Finding 3).

Key Findings Risk & Impact Agreed Management Action
1 Discharge Planning Toolkit Lack of clarity, | Agreed Action: The health board recognises there is a need to
consistency, and develop a local policy to ensure consistency across acute sites

National discharge guidance is available to support health board
staff, which establishes responsibilities across ward,
management and integrated care teams, but does not include
reference to documentary, quality or audit requirements to
ensure consistency of application.

staff awareness. whilst retaining alignment with national guidance. The revised
policy will include supporting documents outlined, and these will
be available through the health board SharePoint for staff
awareness and use.

As part of the UEC programme of work the Health Board is
commissioning a piece of work to develop its D2RA pathways
against the national standard commencing in January 2025. The
health board will be holding its 3rd UEC summit in March 2025
which will be completely focussed on discharge processes and
e health board wide internal professional standards, policy.

e clinical criteria to reside,

e escalation frameworks (both internal and those agreed

Additionally, external reviews have highlighted where further
health board guidance or protocols are required which could be
incorporated into the health boards resources once developed
and approved:

with partners)
e Trusted Assessor standards/responsibilities, and
e revised Patient Choice policy. Development of a health board discharge policy, and approval
at an appropriate forum.

Expected Evidence of Implementation:






Key Findings

Risk & Impact

Agreed Management Action

' Policy and supporting guidance/documents communicated to

staff and uploaded to the health board SharePoint.

Theme: Policies & Procedures

Medium Priority

Control Design

Officer: Emily Warren (Associate Service Group Director of
Primary, Community and Therapies) in conjunction with Alison
Gallagher (Associate Director, Urgent and Emergency Care)

Date: 30t June 2025

Criteria Led Discharge Protocol

A Criteria Led Discharge (CLD) Protocol has been introduced
within both Morriston and Singleton Hospitals. This allows a
designated member of a multidisciplinary team to accept
discharge responsibility for a patient, based upon a criteria
agreed by the consultant responsible for the patients care. The
protocol does not have an approver/authoriser indicated and is
not available within the health board’s clinical library.

Whilst a positive tool, we note that there are a limited number
of patients in receipt of a CLD and wider MDT engagement could
support its wider use.

Opportunities to
expedite discharge
may be lost,
resulting in
increased length of
stay.

Agreed Action: Approval of Criteria Led Discharge protocol at
an appropriate forum, inclusion within the health board discharge
policy, and identification of leads to promote its use across sites.

Expected Evidence of Implementation:
Approval of the Criteria Led Discharge protocol.
Inclusion within the health board policy

Confirmation of CLD leads for each site.

Theme: Policies & Procedures

Medium Priority

Control Operation

Officer: Alison Gallagher (Associate Director, Urgent and
Emergency Care) in conjunction with Sharon Price (Group Nurse
Director, Neath Port Talbot and Singleton Service Group)

Date: 315t March 2025

Discharge Planning Training & Quality Improvement

Resources are available to assist in the planning of discharges,
however since the conclusion of the SAFER roll out in Morriston
Hospital, there has been no formal health board training
available to support the embedding of discharge planning
principles and procedures. We are informed that the NHS
Executive is developing resources aligned to the Optimal Patient
Flow Framework which may assist in this area, although the

Lack of staff
training may result
in inconsistent or
ineffective planning
processes.

Agreed Action: Following receipt of national training resources,
there should be circulation to wards and uptake of training
monitored.

The principles established within the SAFER roll out programme
will be adopted across other sites. SAFER principles and Criteria
to Reside will form a major part of the D2RA implementation
referenced within Key Finding 1.






Key Findings

timescale for release had not been confirmed at time of fieldwork
closing.

Similarly, we identified that ad-hoc support was available to
support wards to refresh awareness of SAFER principles,
however this was not consistent across the health board.

Risk & Impact

Agreed Management Action

Expected Evidence of Implementation:
Evidence to confirm uptake of training.

Evidence of SAFER audits undertaken across all sites.

Medium Priority

Theme: Training & Development

Control Operation

Officer: Alison Gallagher (Associate Director, Urgent and
Emergency Care) in conjunction with Emily Warren (Associate
Service Group Director of Primary, Community and Therapies)

Date: 31t July 2025






Objective 2: Discharge processes are complied with to support the timely and safe discharge of patients. Reasonable

The Optimal Hospital Patient Flow Framework (‘the Framework’), and its key principles, have been embedded into the patient discharge process across all
health board sites through regular ward rounds. Attendance by a Multi-Disciplinary Team was noted, although capacity constraints for some staff groups
(district liaison nurses, pharmacists) and social workers limit this being fully adopted. A recent externally facilitated discharge event at Morriston Hospital
provided positive feedback relating to Board rounds, however we noted the use of Red2Green! varied across sites. Discussion with management confirmed
that there is intention to focus instead on the Clinical Criteria to Reside to identify the reason why a patient requires acute treatment, and its use to identify
systemic issues impacting the discharging of patients. Noting this differs from the adopted national guidance there is an opportunity to develop further guidance
to clarify the requirements on a health board wide basis. (see Key Finding 1)

We reviewed and compared information within SIGNAL (the health board’s patient flow system) and the Welsh Nursing Care Record (WNCR) to evidence
compliance with discharge planning principles. This demonstrated there has been significant progress in embedding the use of SIGNAL since our previous
internal audit. Our testing confirmed the majority of patients had been assigned to a D2RA pathway. The setting of expected discharge dates (EDD) varied
against the Framework target of 24 hours (see Key Finding 4), however, we did note frequent revision of EDD indicating pro-active review. We also noted
that some WNCR entries held limited detail of patient and carer communication relating to discharge planning. (See Key Finding 4) Similar Audit and Assurance
reviews elsewhere across Wales have highlighted similar challenges, including the need to ensure a consistent approach to discharge planning, and to improve
the completeness of patient records.

Each health board site has established arrangements for regular review of COP patients, including daily deep dives for Medicine wards at Morriston Hospital.
Observation of the COP meetings noted a check and challenge approach which scrutinised the accuracy of the information captured within SIGNAL, and
considered a range of actions to support patient discharge. Constraints to discharge processes were noted through the lack of social worker availability and
assessment capacity, the complexity and frailty of patients (where further risk of deconditioning can result in increased care requirements); and patient/family
reluctance to agree discharge.

In October 2024, an externally facilitated review of all patients with a length of stay in excess of 21 days was undertaken across the health board. This identified
that 220 (69.6%) of the 316 patients reviewed were deemed ‘not to require a hospital bed’. The length of stay audit followed three prior discharge/patient flow
reviews, where similar themes regarding internal professional standards, the need for agreement for criteria to reside (to ensure treatment plans reflect care
that can be provided in an acute setting only); and agreement of rehabilitation pathway standards (to assist in setting definitive treatment periods) were
identified. An Urgent and Emergency Care (UEC) Summit held by the Management Board in October 2024 included additional actions to centralise discharge
resources in support of expansion of the Integrated Discharge Hub. We noted that the timescales included for some of the actions were not defined; with others
unlikely to be achieved (as per the discussions held at the second UEC summit in December 2024) (see Key Finding 5).

Key Findings Risk & Impact Agreed Management Action
4  Compliance with discharge planning guidance Inaccurate or Agreed Action: The development of a health board policy will
Of the 30 patients sampled: incomplete include direction on the completeness of records, including in
P pled: information retain relation to setting of expected discharge dates, and
e 17 had not had an initial EDD set within 24 hours in line | impacting on the communication with patients and carers.
with Welsh Government guidance. safe and timely S . - .
. . This will also include arrangements for periodic review of records
e 3 had no D2RA pathway assigned. discharge of o . P ; .
; ; . . . - to support quality improvement, and identification of outliers in
e 2 held no evidence of discharge planning discussions patients.
within WNCR. respect of records completeness.

1 Red2Green is a system to capture nonvalue adding day (such as a planned intervention not taking place, or where the care provided could be provided in a non-acute setting) as a red day,
whereas, a green day signifies progress is being made towards the patient’s discharge. Through inclusion within daily review, it can identify internal or external delays.






Key Findings

e 9 held Ilimited reference planning
discussions.

e 13 had no detail within the patient recorded under ‘What
Matters to Me’ which should inform the development of

discharge plans.

Changes to EDD are recorded within SIGNAL but this does not
capture reasons for change, although it can be cross referenced
with WNCR by date, we did not see changes to EDD referenced
directly.

to discharge

These points highlight that there are opportunities to address
non-compliance and improve the detail recorded within clinical
records.

Risk & Impact

Agreed Management Action

Expected Evidence of Implementation:
Approved policy with associated guidance.

Evidence to support regular review of the accuracy and
completeness of patient records.

Medium Priority

Theme: Information, Data Quality & Data Accuracy

Control Operation

Officer: Callum Allen Ridge (Head of Patient Flow and Site
Services, Morriston Service Group) in conjunction with Emma
Mitchell (Head of Nursing, Medicine Division, Morriston Service
Group).

Date: 31st March 2025

Actions to strengthen discharge processes

Several externally facilitated diagnostic reviews have examined
the health boards discharge planning and patient flow pathways.
These have highlighted where further health board guidance or
protocols are required, including:

e health board wide Internal Professional Standards;
e Clinical criteria to reside; and
e A revised Patient Choice policy.

Action plans to address the above diagnostic reviews have been
received at the UEC Programme Board. There have also been

Failure to address
identified
weaknesses could
extend the cycle

Agreed Action: The health board will incorporate outstanding
actions from recent diagnostic reviews and those identified as
relating to discharge planning from within the UEC Summit, and
collate these into one discharge/patient flow improvement plan
with agreed timescales and action leads. Progress against the
plan will be shared with the UEC Programme Board and Quality
and Safety Committee.

Expected Evidence of Implementation:

Development and approval of the improvement plan, evidence of
progress being reported within appropriate forums.






Key Findings

Summit held in October 2024.

While there is good crossover between both of the above, we
noted the action plan from the Multi Agency Discharge event
(MADE) lacked specific timescales. We were also informed that
whilst progress has been made against the UEC Summit actions,
some timescales in relation to the areas above would not be
achieved.

The above action plans have yet to be shared with the Quality
and Safety Committee.

Theme: Planning, Delivery & Deadline Management

Risk & Impact

actions developed based upon the Management Board UEC

Medium Priority

Control Design

Agreed Management Action

Officer: Emily Warren (Associate Service Group Director of
Primary, Community and Therapies) in conjunction with Alison
Gallagher (Associate Director, Urgent and Emergency Care)

Date: 30t June 2025






Objective 3: There are robust governance and reporting arrangements established in relation to the discharge of patients Reasonable

We reviewed the arrangements in place for oversight of patient discharge performance at a health board level and did not include review of reporting
arrangements within individual Service Groups.

The health board has an established Urgent and Emergency Care Programme Board (UECPB), which meets monthly and is chaired by the Chief Operating
Officer. Review of minutes (August 2023 - July 2024) noted regular attendance from Service Group senior management and assigned UEC programme leads.

UEC Programme 3 ‘Acute Hospital Flow and Discharge’ submit monthly highlight reports to the UECPB, providing a RAG rating (amber as at the date of audit
fieldwork) and narrative updates on the status of discharge initiatives such as SAFER, Red2Green, and D2RA. Review of the content identified opportunities to
enhance completeness (see Key Finding 6), and include more detail related to ward-based metrics (see Key Finding 7) to align with national patient flow
guidance. UEC Programme 3 remains within the health board’s draft Annual Plan priorities for 2025/26, with revised monitoring arrangements recently discussed
to take place within the wider UEC Redesign structure - although we note that this had yet to be implemented at date of fieldwork conclusion.

The high number of COP admitted to health board sites has been regularly reported to the Quality and Safety Committee (QSC), alongside detail of internal
and external actions and initiatives underway to try and address the number of delayed discharges. Reports have been consistent in highlighting that despite
the range of work undertaken (through a focus on admissions avoidance, expansion of same day emergency care services, and expansion of virtual wards) the
impact on overall number of COP has been minimal. This was shared, by QSC, with the Board in May 2024.

In July 2024, the QSC received the newly developed Integrated Discharge Strategy, setting out the health board’s alignment with partners including the
establishment of the Integrated Discharge Hub (IDH) at Morriston Hospital. In October 2024, initial IDH performance measures were shared indicating
improvements in the allocation to discharge pathways (both in accuracy of pathway allocated and receipt by community services) and timescales (including
referral times from IDH to community service; and between referral and discharge). The expanded roll out of the IDH to other acute sites was taking place in
December 2024, as audit fieldwork concluded.

The health board routinely submits monthly pathway of care delays figures to Welsh Government.

Key Findings Risk & Impact Agreed Management Action
6 UEC Programme 3 Reporting coverage Lack of oversight Agreed Action: Future reporting to the UEC Programme Board
relating to on UEC Programme 3 will include updates for all sites.

UEC Programme 3 highlight reports have provided regular
updates against the roll out of productive ward initiatives within
Morriston Service Group. However, there has not been similar
detail related to other health board sites.

discharge processes
across the wider
health board.

Expected Evidence of Implementation:

Amended UEC Programme highlight reports.

Officer: Neil Cooper (Assistant Director of Operations, Urgent
and Emergency Care) in conjunction with Lee Elwell (UEC
Programme Manager)

Date: 29t February 2025

Medium Priority

Theme: Reporting Control Design






Key Findings

UEC Programme 3 Performance metrics

UEC Programme 3 highlight reports contain UEC programme
metrics, but there are no measures or indicators reported
through Programme 3 itself.

The National Six Goals Programme Optimising Patient Flow
guidance includes 12 suggested measures to assess pathways
of care and patient flow, six of these feature within current
health board dashboards. There could also be benefit in
development of reporting indicators linked to the use of SIGNAL
which could identify any variation in use at ward level.

Following the agreement of Internal Professional Standards,
there is a need to establish monitoring arrangements to ensure
they are embedded - this could also support the measurement
of productive wards

Risk & Impact

Lack of ward
focussed metrics
could prevent
identification of
areas of poor
performance.

Agreed Management Action

Agreed Action: Metrics to support monitoring of discharge
planning performance will be developed for inclusion in UEC
Programme 3 reporting.

Expected Evidence of Implementation:

Amended UEC Programme highlight reports.

Theme: Performance Monitoring

Medium Priority

Control Design

Officer: Neil Cooper (Assistant Director of Operations, Urgent
and Emergency Care) in conjunction with Lee Elwell (UEC
Programme Manager)

Date: 29t February 2025
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Key Findings

All patients we reviewed had some form of
clinical plan in place promptly following
admission, but the detail of plans varied
from ward to ward, and the clear
documentation of clinical management
plans with content as expected by section
7.9 of the SAFER Policy was not common.

Agreed Management Response

The policy is being reviewed and
revised to provide greater clarity on

expectations regarding the
documentation of clinical
management plans and include
actions to provide assurance

regarding implementation.

Anticipated first draft for consultation
end of February 2021.

Appendix A: Status of Prior Year Recommendations

2024/25 Status

Welsh Government Hospital
Discharge Guidance is being
followed, although this includes
roles and responsibilities across
services it does not set out the
documentary requirements for
discharge planning.

Our sample testing identified

variation in the level of detail held
within records.

2024 /25 outcome

Recommendation superseded
See Key Findings 1 & 4

The methods used across wards for setting
EDDs was inconsistent - on some wards,
EDDs were set by Ward Managers, and
some by Ward clerks, but there was little
evidence within patient notes of medical
input in determining the EDD.

The policy is being reviewed and
revised to provide greater clarity on
expectations regarding the
documentation of expected date of
discharge within clinical management
plans, and on signal.

Requirement to audit and improve

recording of EDD will be included
within the corporate audit tool.

EDD is set through MDT review
during board rounds. We note
variation in achieving the target set
within Welsh Government guidance
(24 hours), however we found that
detail of EDD amendments were
often not directly referenced within
patient notes.

We could not identify a health board
wide audit or quality improvement
approach to discharge planning.

Recommendation superseded
See Key Finding 1 & Key
Finding 3

Testing at Ward E, Neath Port Talbot
Hospital, showed that EDDs are not always
set within 24 hours having identified 9
patients that did not have an EDD after
being admitted between 2 to 14 days

The policy is being reviewed and
revised to provide greater clarity on
expectations regarding the
documentation of expected date of
discharge within clinical management
plans, and on signal.

A sample of patients reviewed for
Ward E, NPT confirmed EDD had
been set appropriately. Whilst this
is the case on a wider basis we
found the setting of EDD varied

Recommendation superseded
See Key Finding 4

carlier Requirement to audit and improve | @against both national and local
' recording of EDD will be included | targets.
within the corporate audit tool.
Ward rounds within NPTH and

Several observations identified divergence
from policy requirements across wards:

e Records did not demonstrate senior
medical review occurring on a daily
basis. Discussion with the Senior
Corporate Matron has identified that a
senior review might not always be

The policy is being reviewed and
revised to provide greater clarity on
expectations regarding the
frequency, timing and recording of
senior medical review, and include
actions to provide assurance
regarding implementation.

Gorseinon include daily medical
review, but not all included daily
consultant review. No update to
policy has been made, we were
informed there would be differences
between acute vs non acute wards.
At present the differences in

Recommendation superseded
See Key Finding 1
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Key Findings

required for some patients on some
wards.

e Patients at Gorseinon and Neath Port
Talbot Hospitals did not receive a daily
consultant review and there were also
gaps between reviews by junior doctors
too, but it was considered that patients
on the wards visited here did not require
daily medical input. The Policy does not
indicate where variation from the daily
requirement would be acceptable.

e Often, the times of patient reviews
recorded in notes fell after midday.

e Reviews undertaken at weekends were
very inconsistent across all wards with
the majority of patients not receiving a
senior or junior review.

Agreed Management Response

2024/ 25 Status

arrangements are not formally set
out.

2024 /25 outcome

Ward 8 at Singleton used a Weekend
Handover Sheet which outlined the criteria
for patient discharge over the weekend to
enable nurse-led discharge.

The standard for handover will be
reflected within the revised policy
version.

The development of Criteria Led
Discharge provides the scope to
increase nurse and wider MDT led
discharge, however we found
outside of Morriston use was
limited.

Recommendation superseded
See Key Finding 2

There was non-compliance with policy in
that the reason for changing the EDD was
not always recorded within the Clinical
Portal (or SIGNAL) which meant that it was
not always possible to establish if all of the
changes to the EDD were appropriate.
Additionally, we noted differences between
EDD dates recorded in the portal and those
within SIGNAL (with one ward inputting
only to SIGNAL). SIGNAL being a relatively
new development is not currently covered
by policy.

The policy is being reviewed and
revised to provide greater clarity on
expectations regarding adjustments
to EDDs, appropriate reasons for
them and how these will be
documented. The policy will include
actions to provide assurance
regarding implementation

SIGNAL functionality captures the
revision of EDD dates, including the
date/time of revisions for each
patient but not the reason.
Information within WNCR contained
changes in patient status, but did
not directly reference EDD in doing
so.

Recommendation superseded
See Key Finding 4
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Key Findings

Of the 55 patients tested there were ten
patients where the EDD was updated
beyond a patient being medically fit for
discharge with the reason being related to
Social Worker, Continuing
Healthcare/Funded Nursing Care
applications or repatriation. These do not
fall under clinical reasons for change of
EDD and therefore the EDD should not
have been changed.

Five patients at Singleton Hospital were
identified as being medically fit for
discharge within patient notes but this was
not recorded as such within the Clinical
Portal or Signal and so the EDD continued
to be updated.

Agreed Management Response

The policy is being reviewed and
revised to provide greater clarity on
expectations regarding adjustments
to EDDs, appropriate reasons for
them and how these will be
documented. The policy will include
actions to provide assurance
regarding implementation.

2024/ 25 Status

The setting of EDD has been
standardised, guidance from NHS
Delivery Unit was provided to

support this. SIGNAL provides
detail of EDD, COP, and recently
introduced, clinically safe for
transfer. Our review of patient
records did not identify EDD
amendment for non-medical
reasons.

2024 /25 outcome

We recommend closing of this
recommendation within the
audit tracker.

Whilst the ABMU Clinical Portal prompts for
reasons, the field is not mandatory.
Neither SIGNAL nor the Welsh Clinical
Portal provide fields seeking reasons for
EDD changes, so wards using them may
not capture the same level of information.

Furthermore, limitations within Signal and
the Clinical Portals do not provide the
functionality to support the display of
'+days' when a patient is medically fit for
discharge but remains in hospital beyond
their EDD.

Steps should be taken to ensure the
systems chosen to facilitate the
management of EDD promote the
completeness of information required
by policy. This may require working
with NHS Wales partners to develop
national products.

Action closed by health board in
August 2022 noting the improved
functionality of Signal version 3.

N/A

The review of 69 patients found that only
one patient had an EDD recorded within
patient notes and this did not provide any
evidence of discussion with patient, family
or carers. Through discussion at the MDT
Board Round we attended at Gorseinon,
there was evidence that EDDs were being
discussed with patients but that this was
not sufficiently recorded within patient’s
notes.

Further engagement with Carers via
Stakeholder reference group will be
undertaken and a leaflet produced
that outlines what communications
and involvement patients and their
families can expect to receive
regarding the plans for their expected
date of discharge.

A comprehensive training and
communication programme will be
developed that includes

communication with families and

We did not identify revised leaflet/
communication to patients and
families regarding the planning of
expected date of discharge.

Discussions held within fieldwork
highlighted the need to refresh the
Patient Choice policy to assist in the
managing of expectations of
families and patients.

EDD are captured within SIGNAL,
and we found that communication
with patients, families and carers is

Recommendation superseded
See Key Findings 1, 4 & 5.
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Key Findings

Agreed Management Response

patients as part of the launch of the
revised SAFER policy.

The All Wales newly developed and
piloted digital clinical risk
assessments includes Expected date
of discharge and will be rolled out
across the health Board - this will
improve recording of EDD and
engagement with families and carers.

2024/ 25 Status

referenced within WNCR, however
this at times was limited in detail
recorded.

2024 /25 outcome

Within Signal, the 'MDT d/c planning'
column is utilised to record details and
actions in relation to a patients discharge.

To be captured as a requirement
within the new Audit Tools. Which will
be included within the appendices to
the revised policy.

Our sample testing for Morriston
confirmed use of the MDT d/c

planning column as a tool for
planning discharge, only one
example identified where the
column held no information.

Review of the detail within the MDT

We recommend closing of this

remaining three did not use them as
intended, instead using them to show that
a patient was Medically Fit and waiting for
a process (e.g. Social Worker, CHC
assessment). There was no evidence of

be included within the appendices to
the revised policy.

10 There were wards at Morriston that had no | A case will be presented to signal user d/c planning column was the main ;i%ﬁ?ﬂt?;ecrlli?tlon within  the
comments this column in and very little | group to consider if a standardised | feature of the COP deep dive '
detail recorded within patient’s notes. approach to board rounds could be | reviews taking place within the
designed within Phase 3 of signal. Medicine Division.
SIGNAL functionality now includes a
board round view to aid in the
consistency of use.
On ward 6 at Singleton there was evidence Ward 6 Singleton is no longer in
to suggest that arrangements for patients use. Within the sample of patients We recommend closing of this
1 discharge would wait until after the patient | The standards will be reflected in the | reviewed we identified only one . s
) ; ) . . ) - . . recommendation within the
is medically fit for discharge rather than | rewording of the revised policy example of setting of EDD taking audit tracker
this process being ongoing from place post patient becoming )
admission. clinically optimised.
There was a low level of compliance with Review of the documentation
the Red / Green Day aspect of Policy. Two supporting the Morriston roll out of
of the five wards tested at Morriston SAFER confirmed the inclusion of
Hospital did not utilise the Red to Green | To be captured as a requirement | R2G, and the Signal functionality is
12 columns on their PSAG Boards and the | within the new Audit Tools. Which will | in place to reset patient status each | Recommendation superseded

day to prompt discussion within
board rounds.

Discussion with site leads
highlighted that the wuse and
embedding of R2G remained

See Key Finding 1
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Key Findings

use of Red to Green days at Singleton
Hospital or NPTH.

Agreed Management Response

2024/ 25 Status

variable at NPT, Singleton and
Gorseinon sites.

We were informed that the health
board will instead be emphasising
the use of criteria to reside as a tool
for the identification of patient need
for treatment within an acute
setting and this will assist in
identification of delays to patient
discharges.

2024 /25 outcome

13

Staff at Singleton ward 8 highlighted that
patient notes available at ward level were
not comprehensive - interventions
provided by staff from Therapies were held
separately.

Revised policy will clarify how
discharge planning will be recorded
following the introduction of new
systems.

Review of records and discussion
with leads confirmed that there
remains variation in where
therapies staff record information.

Recommendation superseded
See Key Finding 1

14

There were mixed findings in relation to
Information Governance with different
wards having different concepts relating to
the amount of patient data permitted to be
displayed within patient and visitors view.

However, in general, full patient names
were visible on most Signal PSAG Boards
with some Wards displaying dates of birth,
area of residence and detailed health
information. These screens should be
switched off when not in use for Board
Rounds to limit the visibility to patients
and visitors, however there were several
instances when a Board was left
unattended by staff and visible to passers-

by.

The Quality & Safety Governance
Group will develop a standard for
inclusion of key requirements and
management of PSAG “know how you
are doing” boards.

Action closed by the health board in
June 2023 noting that guidance in
relation to PSAG Boards had been
shared with Service Groups.

N/A

15

A review of Signal at Singleton in
particular, has shown that staff are
populating the system with detailed
patient information which is not duplicated
within patient notes. Staff report the
system has had a positive impact at ward
levels, reducing workloads and making
patient information more accessible -
However, once Signal is optimised across

This identified risk will be escalated to
the Signal User Group and any
unresolved risk assessed and added
to the corporate risk register for
monitoring until action is identified to
resolve it.

There has been substantial change
to the infrastructure/platform that
supports SIGNAL, and patient data
is transferred to a data warehouse
for secure long term storage.

Our sample testing noted that
SIGNAL contained clearer outline of
discharge planning progression,
with WNCR retaining clinical detail.

We recommend closing of this
recommendation within the
audit tracker.
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Key Findings

the Health Board, it will only have capacity
to store information for a maximum of
30,000 patients which translates to storing
information for approximately 6 months
post patient discharge. After which, all of
the detailed entries within Signal will be
deleted.

It is noted that the introduction of
electronic nursing notes will overcome
some of the above, however this system
only includes entries from Nurses and
assessments undertaken.

Agreed Management Response

2024/ 25 Status

2024 /25 outcome

16

(Summary issue added following
discussion of draft report)

The audit has highlighted a number of
areas of non-compliance with policy

Development of a new Corporate
Audit Management Tool, and
standard operating procedure
outlining the roles, responsibilities
and expectations (including
frequency) for service group audit of
compliance, and to identify
improvements and actions relating to
the discharge policy.

This has not been progressed, and
whilst the roll out of SAFER on the
Morriston site included quality
improvement support and follow
up reviews, this was not replicated
across other sites, and has not

continued in the structured format.

Recommendation superseded
See Key Finding 3
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Appendix B

Assurance Opinion

Few matters require attention and are
Substantial compliance or advisory in nature.

Low impact on residual risk exposure.

Some  matters require management

attention in control design or compliance.
Reasonable . . .

Low to moderate impact on residual risk

exposure until resolved.

More significant matters require

.. management attention.
Limited . . .
Moderate impact on residual risk exposure
until resolved.

Action is required to address the whole

Unsatisfactor control framework in this area.
§ ‘ y High impact on residual risk exposure until
resolved.

Given to reviews and support provided to
management which form part of the internal
audit plan, to which the assurance
" Advisory definitions are not appropriate.
C’_:;:"_Fr These reviews are still relevant to the
evidence base upon which the overall
opinion is formed.

Prioritisation of Findings

Priority Explanation

Significant risk to achievement of a system objective OR
evidence present of material loss, error, or misstatement.
Poor system design OR widespread non-compliance.

Some risk to achievement of a system objective. Minor

Medium weakness in system design OR limited non-compliance.

Website: Audit & Assurance Services - NHS Wales Shared Services Partnership

Disclaimer

This audit report has been prepared for internal use only. Audit and Assurance
Services reports are prepared, in accordance with the agreed audit brief, and the
Audit Charter as approved by the Audit Committee.

Audit reports are prepared by the staff of the NHS Wales Audit and Assurance
Services and addressed to Independent Members or officers including those
designated as Accountable Officer. They are prepared for the sole use of the
Swansea Bay University Health Board and no responsibility is taken by the Audit
and Assurance Services Internal Auditors to any director or officer in their individual
capacity, or to any third party.

The report is based on the review work undertaken and is not necessarily a
complete statement of all weaknesses that exist or potential improvements. Whilst
every care has been taken to ensure that the information provided in this report is
as accurate as possible, no complete guarantee or warranty can be given with
regard to the advice and information contained.

Our work does not provide absolute assurance that material errors, loss or fraud
do not exist. Responsibility for a sound system of internal controls and the
prevention and detection of fraud and other irregularities rests with management
of the Swansea Bay University Health Board. Work performed by internal audit
should not be relied upon to identify all strengths and weaknesses in internal
controls, or all circumstances of fraud or irregularity. Effective and timely
implementation of recommendations is important for the development and
maintenance of a reliable internal control system.

Public Sector Internal Audit Standards

Audit work undertaken by NHS Wales Audit and Assurance
Services conforms with the International Standards for the
Professional Practice of Internal Auditing and associated Public
Sector Internal Audit Standards as validated through the
external quality assessment undertaken by the Chartered
Institute of Public Finance & Accountancy in April 2023.

QN GIG | Partneriaeth
0S5 Cydwasanaethau
§7 NHS
Shared Services
Partnership
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Discharge Planning

		Key Finding Ref		Key Findings		Impact		Agreed Management Action		Priority		Expected Evidence of Implementation		Responsible Officer		Deadline		Completed Date		Status at Report Date		Status as at 03/09/26		Comments

		1		National discharge guidance is available to support health board staff, which establishes responsibilities across ward, management and integrated care teams, but does not include reference to documentary, quality or audit requirements to ensure consistency of application.

Additionally, external reviews have highlighted where further health board guidance or protocols are required which could be incorporated into the health boards resources once developed and approved: 
•	Health board wide internal professional standards,
•	Clinical criteria to reside,
•	Escalation frameworks (both internal and those agreed with partners)
•	Trusted Assessor standards/responsibilities, and
•	Revised Patient Choice policy. 		Lack of clarity, consistency, and staff awareness.		The health board recognises there is a need to develop a local policy to ensure consistency across acute sites whilst retaining alignment with national guidance. The revised policy will include supporting documents outlined, and these will be available through the health board SharePoint for staff awareness and use.
 
As part of the UEC programme of work the Health Board is commissioning a piece of work to develop its D2RA pathways against the national standard commencing in January 2025. The health board will be holding its 3rd UEC summit in March 2025 which will be completely focussed on discharge processes and policy. 		M		Development of a health board discharge policy, and approval at an appropriate forum. 

Policy and supporting guidance/documents communicated to staff and uploaded to the health board SharePoint. 		Associate Service Group Director
PCTSG

Associate Director
UEC 		6/30/25				Overdue		In progress		June 2025 (AG): In April 2025, a test of change was implemented to develop an Integrated Discharge Hub focussed at the 'front doors' of Morriston to promote admission avoidance and early supported discharge in line with the D2RA principles. Due to the overwhelming success if this test of change, the hub has continued in its temporary arrangement. However, plans are in place to designate a Strategic and Operational Lead for the D2RA Hub this will allow for a formal organisational change process to be applied to the affected staff from across the Health Board. In addition, a work programme has been developed with a number of workstreams to address the following:
-  Trusted assessment model and training needs
-  Revised discharge policy with supporting policies and procedures to include: patient choice and reluctant discharge (based on the WG 2025 guidance)
-  D2RA demand profile for the pathways
-  Review of the Pathway 2 bed pool and pathways
In parallel to this work, there is community and integrated teams review to explore the resources available in the community, their activity, cost and opportunities to reduce duplication, increase productivity and remodel available resources to provide a consistent Pathway 1 offer

Dec 2025 (LE): A Health Board wide discharge policy is currently in development (aligned with national policy). At present this has been revised/ updated but requires final completion and sign-off. This sign-off will be via the West Glamorgan RPB's 'Communities & Older Persons Board' and shared for information at the SBUHB UEC Board. After said sign-off this will be made available to all Health Board staff via COIN (SBUHB Directory for Clinical Guidelines and Documents) and to Local Authority colleagues via appropriate West Glamorgan Regional Partnership Board channels. Once this process has been completed a 'link' to the location of said discharge policy will be shared with relevant colleagues across SBUHB region (irrespective of site, location worked etc). It is anticipated that said discharge policy will shared at the next available Communities and Older Persons Board date for sign-off/ratification.

Feb 2026 (LE): Overarching discharge policy still in development - system pressures limited ability to complete in a timely manner. Anticipated this will be completed shortly and taken through governance previously highlighted for sign-off

June 2026: Draft discharge policy needs sign off via the Older Persons RPB. This will be uploaded to COIN at point of sign off. Criteria to admit audit undertaken by Dr Henson, findings to be presented to UEC Board. Criteria to reside and implementing the guidance is heavily dependent on the availability of timely access to community services. Essentially, all Pathway 1 and 3 patients do not meet CTR however there is a gap in the provision and an absence of D2RA pathways. Trusted assessment is partially in place for some of the Pathway 2 bed pools via the IDH however there is a requirement to resource the IDH to enable wider trusted assessment - this may be achieved through the IDH engagement aimed at pooling discharge and transfer resources from across the Health Board under the IDH to provide clinically prioritised discharge/transfer services and management of the clinically optimised patient cohort.

Aug 26:
- December 2024-Integrated Discharge Standards developed and agreed by ROAG. Unable to fully implement due to lack of resource in IDH. Refresh June-August 2026 as part of updated POCD BI Dashboard.
- 2026- Internal Professional Standards agreed and signed off. Inability to measure timescales set out in the standards, limited value as no reliable data source and no real time escalation mechanism.

		2		A Criteria Led Discharge (CLD) Protocol has been introduced within both Morriston and Singleton Hospitals. This allows a designated member of a multidisciplinary team to accept discharge responsibility for a patient, based upon a criteria agreed by the consultant responsible for the patients care. The protocol does not have an approver/authoriser indicated and is not available within the health board’s clinical library. 

Whilst a positive tool, we note that there are a limited number of patients in receipt of a CLD and wider MDT engagement could support its wider use. 		Opportunities to expedite discharge may be lost, resulting in increased length of stay.		Approval of Criteria Led Discharge protocol at an appropriate forum, inclusion within the health board discharge policy, and identification of leads to promote its use across sites.		M		Approval of the Criteria Led Discharge protocol.
 
Inclusion within the health board policy 

Confirmation of CLD leads for each site. 		Associate Director
Urgent and Emergency Care

Group Nurse Director
NPTSSG		3/31/25				Overdue		In progress		June 2025 (SP): The wards at Singleton undertaking CLD have all now transferred to Morriston under the AMSR work.  Action therefore closed for NPTSSG.   

June 2025 (AG): Criteria Led Discharge protocol in place. Test of change in progress focussing on medical wards, Morriston with oversight from a Matron who is working weekends to promote weekend discharge using the CLD protocol

Dec 2025 (LE): CLD protocol has been approved by Consultant Lead and utilised for 'tests of change' at Morriston Hospital site during 2025. CLD protocol to form part of the overarching SBUHB discharge policy. This overarching policy requiring final completion (as work in progress) and subsequent sign-off at RPB Communities & Older Persons Board and shared for information with SBUHB UEC Board. Next steps re; the roll-out of CLD include forming a T&F group to roll-out CLD across all sites and to assign site specific leads.

Feb 2026 (LE): CLD protocol to form part of overarching discharge policy referred to previously - this discharge policy requires completion and sign-off. Full roll-out of CLD across all sites/ approporiate wards to be completed. System pressures limited ability to roll-out

June 2026: There is limited application of Criteria Led discharge across all sites. Pilots previous implemented in Morriston with nominated support to wards. No identified leads for CLD, this would need to be led and driven by the nursing leadership teams as opposed to a designated lead per site.

Aug 26:
- Criteria Led Discharge developed with supporting documentation and competency framework.
- CLD assessment and competency framework reliant on ward based nursing teams - no designated training resource available.
- CLD Leads identified in Morriston - nursing and medical.
- SOP & Local Policies refreshed and updated to match new Welsh Govt Guidance-National Launch due for September 26. 

		3		Resources are available to assist in the planning of discharges, however since the conclusion of the SAFER roll out in Morriston Hospital, there has been no formal health board training available to support the embedding of discharge planning principles and procedures. We are informed that the NHS Executive is developing resources aligned to the Optimal Patient Flow Framework which may assist in this area, although the timescale for release had not been confirmed at time of fieldwork closing. 

Similarly, we identified that ad-hoc support was available to support wards to refresh awareness of SAFER principles, however this was not consistent across the health board. 		Lack of staff training may result in inconsistent or ineffective planning processes.		Following receipt of national training resources, there should be circulation to wards and uptake of training monitored. The principles established within the SAFER roll out programme will be adopted across other sites. SAFER principles and Criteria to Reside will form a major part of the D2RA implementation referenced within Key Finding 1.		M		Evidence to confirm uptake of training. 

Evidence of SAFER audits undertaken across all sites. 		Associate Director
Urgent and Emergency Care

Associate Service Group Director
PCTSG 		7/31/25				Overdue		In progress		June 2025 (AG): Band 6 x 2wte and Band 8a x 1wte funding confirmed June 2025 to support roll out of the optimal hospital flow framework as part of the Six Goals national programme. Recruitment process in place

Dec 2025 (LE): Board Round reviews/ audits recently (Nov. 25) undertaken by national NHS Wales colleagues. This feedback alongside internal reviews of Board Rounds have resulted in the development of a scheme of work to improve Board Rounds in line with Optimal Hospital Flow/ SAFER principles. This work programme currently underway. To support said developments a SAFER dashboard monitors key metrics such as percentage of discharges before midday, % of patients with an EDD set, number of 'red or 'green' days, average LOS, COP status, use of discharge lounge etc. The aim of this scheme of work to improve overall Board Round productivity and improve flow out of the hospital aligning with a Discharge to Recover then Assess model (D2RA). Activity currently underway at Morriston Hospital site with the aim to roll-out across all sites in due course.

Feb 2026 (LE): Roll out of all activity still planned and will continue moving into 26/ 27 F/Y. System pressures limited ability to roll-out more recently. Feedback from national reviews being fed into planned activity (Optimal Hospital Flow/ SAFER principles). Roll-out across all sites to be completed

June 2026: Optimal hospital flow roll out in progress however national funding has ceased and all staff on fixed term contracts, the leads post end July 26 - to cover whole Health Board team will need to be increased and existing posts extended. Paper going to Executive Board to extend existing roles and to explore opportunities for mobilising existing resource to accelerate roll out.

Aug 26:
- Optimal Hospital Flow programme roll out in progress with tests of change in respect of Red to Green and pathway delays in progress NPTH.
-EDD in use with variable compliance across the Health Board, good compliance on the Optimal Hospital Flow programme wards.
-SAFER flow audits undertaken on all Morriston wards as baseline pre OHFF roll out.
-Current bid in progress for submission to NHS P & I - funding available to support OHFF roll out until end Mar 27. Scheduled roll out plan to be developed HB wide.

		4		Of the 30 patients sampled: 
•	17 had not had an initial EDD set within 24 hours in line with WG guidance.
•	had no D2RA pathway assigned.
•	2 held no evidence of discharge planning discussions within WNCR.
•	9 held limited reference to discharge planning discussions.
•	13 had no detail within the patient recorded under ‘What Matters to Me’ which should inform the development of discharge plans. 

Changes to EDD are recorded within SIGNAL but this does not capture reasons for change, although it can be cross referenced with WNCR by date, we did not see changes to EDD referenced directly. 

These points highlight that there are opportunities to address non-compliance and improve the detail recorded within clinical records. 		Inaccurate or incomplete information retain impacting on the safe and timely discharge of patients.		The development of a health board policy will include direction on the completeness of records, including in relation to setting of expected discharge dates, and communication with patients and carers. 

This will also include arrangements for periodic review of records to support quality improvement, and identification of outliers in respect of records completeness. 		M		Approved policy with associated guidance.

Evidence to support regular review of the accuracy and completeness of patient records. 		Head of Patient Flow & Site Services
MSG

Head of Nursing
Medicine Division
MSG		3/31/25				Overdue		In progress		June 2025 (AG): Rolls will focus on HB wide roll out of the optimal hospital flow framework, underpinned by the SAFER flow principles and development of robust Board Round processes with clear task allocation, follow-up and escalation

Dec 2025 (LE): Overarching discharge policy currently nearing completion and will include guidance on the completing/ appropriately updating of patient records in a timely manner as part of Board Rounds. This in line with Optimal Hospital Flow principles and to include setting and monitoring of EDDs. This policy also to set out best practice guidance on the frequency of data review to ensure that decision making regarding patients next steps is made on the best possible information. The overarching discharge policy nearing completion and to be signed off by the RPB Communities & Older Persons Board and shared the SBUHB UEC Board for information as soon as possible.

Feb 2026 (LE): Overarching discharge policy still in development - system pressures limited ability to complete in a timely manner. Anticipated this will be completed shortly and taken through governance previously highlighted for sign-off

June 2026: This is linked to the roll out of OHFF noted above. There are areas with good compliance and evidence of application of the OHFF including EDD, pathway designation. Ward flow dashboard in place. Red to Green day reporting formally commences August 26.

Aug 26:
- Updates provided on all programmes to UEC Programme Board monthly.
- Older Persons Board agreed 4 refreshed strategic priorities in January 2026.
- Delivery programme reconfigured to meet these priorities.
-Optimal Hospital flow focus oon updating SIGNAL to accurately reflect patient status - all Morriston wards have had a baseline audit taken against the optimal flow measures - completion 21st August 26.

		5		Several externally facilitated diagnostic reviews have examined the health boards discharge planning and patient flow pathways. These have highlighted where further health board guidance or protocols are required, including: 
•	Health board wide Internal Professional Standards;
•	Clinical Criteria to Reside; and
•	A revised Patient Choice policy. 

Action plans to address the above diagnostic reviews have been received at the UEC Programme Board. There have also been actions developed based upon the Management Board UEC Summit held in October 2024.

While there is good crossover between both of the above, we noted the action plan from the Multi-Agency Discharge Event (MADE) lacked specific timescales. We were also informed that whilst progress has been made against the UEC Summit actions, some timescales in relation to the areas above would not be achieved.

The above action plans have yet to be shared with the Quality and Safety Committee. 		Failure to address identified weaknesses could extend the cycle		The health board will incorporate outstanding actions from recent diagnostic reviews and those identified as relating to discharge planning from within the UEC Summit, and collate these into one discharge/patient flow improvement plan with agreed timescales and action leads. Progress against the plan will be shared with the UEC Programme Board and Quality and Safety Committee.		M		Development and approval of the improvement plan.

Evidence of progress being reported within appropriate forums. 		Associate Service Group Director
PCTSG

Associate Director
Urgent and Emergency Care		6/30/25				Overdue		Overdue		June 2025 (AG): There is an organisational change document in development to support the centralisation of patient flow. This will focus the resource in Morriston and will provide HB wide bronze cover. Singleton and Neath Port Talbot sites will have a proportionate flow resource on site who will report into the bronze Clinical Site Matron Morriston. 
'Your Next Patient' has been launched Health Board wide which identifies areas within wards where patients can be safely nursed whilst awaiting a bed. This allows patients to gain earlier access to the specialist care they need as opposed to waiting for a bed in the Emergency Department or within Admission Units.
Significant progress has been made in relation to tactical patient flow management, data collection and reporting.
In relation to the three specific points raised in the summit, updates are as follows:
-  Health board wide Internal Professional Standards: relaunched as part of the Anglesey Ward test of change supported by Associate Medical Directors - no formal measurement or escalation reporting available.
-  Clinical Criteria to Reside: test of change in progress as from 16th June 25 in Morriston - no reportable findings available.
-  A revised Patient Choice policy: drafted as part of the revised HB Discharge Policy

Dec 2025 (LE): Activity underway across the region in relation to discharge planning aligning with a broader improvement plan agreed at both Health Board and regional Partnership Board levels. This to include a shift to a true D2RA model (aligning with Optimal Hospital Flow principles). Specific actions include:
•	   Development of an overarching Discharge Policy to include reference to key aspects such as: SAFER/ productive Board Rounds, Reluctant Discharge, appropriate data recording in real time
•	   Review of demand and capacity across the region pertaining to P1, P2, P3 (D2RA pathways) - this so as understand true demand
•	   Linked Community Services Review so as to gauge whether there is sufficient community resource that may be able to be reallocated so as to support timely discharge (and admission avoidance)
•	   Process mapping the discharge process to highlight any operational blockages - this across both health and social care boundaries
•	   Undertaking Board Round improvement activity linked to SAFER principles so as to improve flow in the acute system
•	   Review Pathway of Care Delay (POCD) data so as to understand where system delays occur and whether these can be mitigated
Updates on progress against actions shared regularly and RPB Communities & Older Persons Board and at SBUHB UEC Board

Feb 2026 (LE): There continues to work to improve flow throughout the system. System pressures, namely increased demand at front door, increased acuity coupled with a poor discharge profile has limited improvement activity more recently. However work (noted in previous update) continues to be carried out and reported at both RPB Communities & Older Persons Board and at SBUHB UEC Board

June 2026: 
-Discharge and in particular the D2RA pathway work programme is governed via the RPB and the work programme is set and agreed by both HB and LA Directors. The work programme remains in progress as follows:
-Development of an overarching Discharge Policy to include reference to key aspects such as: SAFER/ productive Board Rounds, Reluctant Discharge, appropriate data recording in real time
-Review of demand and capacity across the region pertaining to P1, P2, P3 (D2RA pathways) - this so as understand true demand
-Linked Community Services Review so as to gauge whether there is sufficient community resource that may be able to be reallocated so as to support timely discharge (and admission avoidance)
-Process mapping of the discharge process to highlight any operational blockages - this across both health and social care boundaries
-Undertaking Board Round improvement activity linked to SAFER principles so as to improve flow in the acute system
-Review Pathway of Care Delay (POCD) data so as to understand where system delays occur and whether these can be mitigated

August 26:
-Discharge and flow improvement represented in Pillar 3 of the national UEC programme.
-Recommendations from external reviews largely relate to the development of underpinning policies for discharge and the optimal hospital flow toolkit application - with roll out in progress.
-Discharge including patient choice policy forsign off at UEC Board Sept 26.

		6		UEC Programme 3 highlight reports have provided regular updates against the roll out of productive ward initiatives within Morriston Service Group. However, there has not been similar detail related to other health board sites.		Lack of oversight relating to discharge processes across the wider health board.		Future reporting to the UEC Programme Board on UEC Programme 3 will include updates for all sites.		M		Amended UEC Programme highlight reports.		Assistant Director of Operations
Urgent & Emergency Care

UEC Programme Manager		3/31/25				Overdue		In progress		April 2025 (LE): Full oversight of all sites will be possible once work is completed to ensure that there is a centralised discharge team/resource in place across all sites

June 2025 (AG): As noted above there is an organisational change document in development to support the centralisation of patient flow (which will work across all acute hospital sites). Furthermore 'Your Next Patient' has been launched Health Board wide which identifies areas within wards where patients can be safely nursed whilst awaiting a bed. This allows patients to gain earlier access to the specialist care they need as opposed to waiting for a bed in the Emergency Department or within Admission Units. These changes will allow for linked up reporting across sites (and in turn be able to reported up at UEC Programme Board) and provide Health Board wide assurance re; discharge processes.
To support said changes 2x B6 'Improvement facilitators - Optimal hospital flow & D2RA' are being recruited on a pilot basis funded by NHS Executive until end of financial year 25/ 26. This to trial an enhanced level of resource focussing solely on flow and discharge across the Health Board. These roles working with ward staff to support optimal hospital flow/ D2RA principles and encourage timely recording of information which in turn can be reported upon

Dec 2025 (LE): Programme structure amended with D2RA activity reported through the RPB Communities and Older Person Board as relating to joint activity across health & social care boundaries. Information also shared with UEC Board for information.  SAFER dashboard already developed to monitor key flow metrics, whilst Board Round improvement activity underway in relation to improving productivity at Board Rounds. Board Round improvement activity currently being rolled out at Morriston Hospital site with plans to roll-out across all sites in due course.

Feb 26 (LE): POCD measures used as a proxy for monitoring flow - this across all sites and reported at SBUHB UEC Board & RPB Communities & Older Persons Board. Board Round improvement activity planned across all sites - roll-out in a timely manner subject to sufficient resource to implement 

June 2026: Optimal Hospital Flow (productive wards) not rolled out Health Board wide therefore no highlight reporting in place. Morriston roll out of Optimal Hospital Flow reports to the UEC Operational Delivery Group and the UEC Board.

Aug 26:
- Highlight reporting provided on all programmes to UEC Programme Board monthly
- Welsh Govt stood down Six Goals and refreshed as 3 Pillars with highlight reporting centrally.
- New programme of work developED to support UEC 3 pillars.
- Governance review Older Persons/ UEC Board undertaken by Internal Audit-management response submitted.
-The gap in wider health board reporting regarding optimal hospital flow relates to the smalll resource available to suport roll out and therefore NPT and Singleton Hospitals have not received any training.


		7		UEC Programme 3 highlight reports contain UEC programme metrics, but there are no measures or indicators reported through Programme 3 itself. 

The National Six Goals Programme Optimising Patient Flow guidance includes 12 suggested measures to assess pathways of care and patient flow, six of these feature within current health board dashboards. There could also be benefit in development of reporting indicators linked to the use of SIGNAL which could identify any variation in use at ward level. 

Following the agreement of Internal Professional Standards, there is a need to establish monitoring arrangements to ensure they are embedded - this could also support the measurement of productive wards 		Lack of ward focussed metrics could prevent identification of areas of poor performance.		Metrics to support monitoring of discharge planning performance will be developed for inclusion in UEC Programme 3 reporting.		M		Amended UEC Programme highlight reports.		Assistant Director of Operations
Urgent & Emergency Care

UEC Programme Manager		3/31/25				Overdue		In progress		April 2025 (LE): Work on the implementation of Internal Professional Standards is currently ongoing

June 2025 (AG): Regarding the use of SAFER, D2RA and Pathways of Care Delays (POCD), appropriate dashboards have already been developed. These being relevant to the roll-out of 'productive wards' initiatives and align with national optimal hospital flow and D2RA principles/ frameworks.    
As noted, 2x B6 'Improvement facilitators - Optimal hospital flow & D2RA' are being recruited on a pilot basis funded by NHS Executive until end of financial year 25/ 26. This to trial an enhanced level of resource focussing solely on flow and discharge across the Health Board. These roles working with ward staff to support optimal hospital flow/ D2RA principles and encourage timely recording of information which in turn can be reported upon. It is anticipated that any improvement of data recording will have a significant improvement on the data quality currently available via SAFER, D2RA and POCD dashboards - and in turn can be used more effectively to drive improvements/ change

Dec 2025 (LE): Programme structure amended with D2RA activity reported through the RPB Communities and Older Person Board as relating to joint activity across health & social care boundaries. Information also shared with UEC Board for information.  SAFER dashboard already developed to monitor key flow metrics, whilst Board Round improvement activity underway in relation to improving productivity at Board Rounds.

Feb 26 (LE): Ward focussed metrics already monitored via SAFER dashboard and accessible by all

June 2026: Internal professional standards implemented in Morriston as part of June 25 test of change. Revised IPS in progress with internal measurement being explored as currently not measurable. IPS not in place NPT/Singleton - plan to roll out revised standards when approved by EMD.

Aug. 26:
 - POCD = SBUHB to work with partners to continue to achieve a reduction in Pathway of Care Delays (including a reduction in total delays, days delayed and assessment delays)’ – SBUHB’s target is to reduce the number of Pathway of Care Delays to <100 at any one time by 31 March 2027 
- Weekly POCD review and validation
- Performance slide deck issued weekly to Exec Directors in Health and Social Care
- Weekly operational monitoring of POCD via ROAG
- POCD BI Dashboard developed to enhance grip on performance 
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