| Meeting Date | 14 May 2026 |  | Agenda Item |  |  | 2.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Charitable Funds Committee |  |  |  |  |  |
| Report Title | Defence Medical Welfare Service (DMWS) matching funding grant. |  |  |  |  |  |
| Report Author | Lewis Bradley, Fundraising Support Manager |  |  |  |  |  |
| Report Sponsor | Deb Lewis, Chief Operating Officer. |  |  |  |  |  |
| Presented by | Lewis Bradley, Fundraising Support Manager. |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | To secure approval for a jointly funded post for no more than two years in support of our Health Board’s work with members of the Armed Forces Community. |  |  |  |  |  |
| Key Issues | This paper seeks approval from the Charitable Funds Committee to contribute £26,062 toward the establishment of a pilot Welfare Service delivered by the Defence Medical Welfare Service (DMWS) within Swansea Bay University Health Board. This approach enables immediate implementation while creating a sustainable pathway for long-term provision. This funding will enable the introduction of a specialist, non-clinical support service for members of the Armed Forces Community (AFC), addressing a recognised gap in provision and improving patient outcomes, experience, and recovery. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☐ | ☒ |  |
| Recommendations | Members are asked to: - APPROVE the following: - £26,062 of charitable funding per year (for no more than two years) to support a jointly funded pilot Welfare Service - The development of a clear exit strategy by the Welfare Service which would either see it being funded via other means or securing its orderly closure by the end of year two. - The fact that charitable funds will not be used beyond the second year in any circumstances. |  |  |  |  |  |

Defence Medical Welfare Service (DMWS) matching funding grant

- INTRODUCTION

Swansea Bay University Health Board serves a significant Armed Forces Community population. According to the 2021 Census, approximately 8,074 veterans live within Swansea, representing 4.1% of the adult population (around 1 in 22 people).

Despite this, there is currently no dedicated, embedded welfare provision tailored to veterans and their families within the Health Board despite what are often, additional needs.

This gap results in:

- Veterans struggling to navigate civilian healthcare systems

- Unmet non-clinical needs (housing, finances, social isolation, mental health)

- Increased risk of delayed discharge and avoidable readmission

- Additional pressure on clinical teams

This proposal directly addresses this inequity in service provision and mirrors that already in place in other HBs across Wales.

- BACKGROUND & Opportunity

The Defence Medical Welfare Service (DMWS) is a UK-wide charity with over 80 years’ experience supporting the Armed Forces Community.

DMWS:

- Operates in 46+ NHS Trusts and Health Boards

- Is the MOD Hospital Welfare Service provider

- Works alongside NHS veteran services including Op RESTORE and Op COURAGE

- Provides bedside, community, and remote support

Their delivery model is well-established, evidence-based, and successfully integrated within NHS systems.

Benefits:

A 4-day per week Welfare Officer-led service, embedded within Swansea Bay hospital and community pathways.

The service will deliver:

- Holistic emotional and practical support

- Care navigation and social prescribing

- Discharge planning support

- Advocacy and multi-agency coordination

- Ongoing community-based follow-up

- Support extends to patients, families, and carers, maximising impact.

Expected Outcomes:

For Patients and Families

- Reduced stress, anxiety, and isolation

- Improved recovery and overall wellbeing

- Better engagement with healthcare services

- Increased access to financial, housing, and community support

For the Health Board

- Reduced delayed discharges

- Fewer avoidable readmissions

- Improved patient flow

- Reduced pressure on clinical staff

For the Armed Forces Community

- Access to military-informed, culturally competent support

- Improved trust and engagement

- Delivery against the Armed Forces Covenant Duty

Estimate of Research benefits:

- 65 direct beneficiaries (patients)

- 180 indirect beneficiaries (families/carers)

Value for Money

This proposal represents a high-impact, preventative investment.

Evidence from DMWS services shows:

- Significant reductions in readmissions (up to 87% in complex cases)

- Reduced escalation to crisis services

- Improved long-term independence

Cost comparison:

- Average readmission cost: ~£4,400

- Preventing 6–10 readmissions annually would offset the charitable investment

This excludes wider system and societal benefits.

- FINANCIAL IMPLICATIONS

Charitable funds usage:

The use of Morriston General Fund is being explored, but conformation has not yet been secured. An alternative is to secure contribution from a number of different funds that would benefit from the support given.

The health board over-arching general fund has insufficient funds to support the opportunity.

### Year 1: Pilot (Joint Funding Model)

| Contribution | Amount |
| --- | --- |
| DMWS (secured external funding) | £20,000 |
| Charitable Funds Request | £26,062 |
| Total Cost | £46,062 |

Charitable funding enables immediate service delivery by leveraging secured external funding.

- DMWS will provide structured reporting including:

- Activity and demographic data

- Outcome measures (ONS4, wellbeing complexity)

- Case studies and qualitative impact

- Evidence of system benefits (e.g. discharge facilitation)

In advancement of year two, we would look for additional support from the same funding sources (internally & externally). Therefore, year 2 support from charitable funds is conditional on the same level of external support as year 1.

### After year 2

The options after year 2 include:

- Closure of the service

- Securing of other forms of charitable funding to continue the service

- Cost benefit analysis demonstrating cash savings generated as a result of the service, leading to its mainstreaming within the Health Board.  The analysis would include:

  - Robust data around improvements in terms of admissions, lengths of stay, ED attendances etc for the cohort

  - Evidence of tangible cost avoidance and / or cash savings

For absolute clarity, extending the funding of the post from charitable funds is not an option.

- Risks & Exit Strategy

Failure to approve this proposal would result in:

- Continued lack of dedicated support for veterans and their families within Swansea Bay University Health Board

- Ongoing unmet non-clinical needs impacting recovery (e.g. housing, financial hardship, social isolation)

- Increased likelihood of delayed discharges and avoidable readmissions

- Sustained pressure on clinical staff to manage complex social issues outside their core role

- Reduced ability to meet commitments under the Armed Forces Covenant

- Missed opportunity to develop an evidence-based, sustainable model of care for this population, supported by external funding

This would perpetuate existing inequalities in access to appropriate support for the Armed Forces Community.

Exit Strategy – End of Year 2

If the service is not continued after the second year, a phased exit strategy in the lead up to that period will ensure sustainability of impact and minimal disruption:

Extended Wind-Down Period

- A transition phase (typically 2–4 months) will reflect an established caseload and system integration.

- Graduated Caseload Reduction

- No new referrals accepted in the final 2–3 months

- Planned reduction of caseload through staged discharges and transitions

- Prioritisation of high-risk and complex cases for intensive support before closure

- Embedding Within Existing Systems

Where effective:

- Key elements of the DMWS model (e.g. referral pathways, identification processes, care navigation approaches) will be embedded into existing Health Board pathways

- Tools, guidance, and protocols will be shared with clinical teams and partners

- Opportunities for partial continuation via statutory or third-sector provision will be explored

- Workforce Knowledge Transfer

- Training and handover sessions delivered to NHS staff and partner organisations

- Documentation of best practice, referral triggers, and engagement strategies

- Support for sustained system benefit beyond the life of the service

- Managed Beneficiary Transitions

All active beneficiaries will:

- Receive personalised exit plans

- Be connected to appropriate long-term support

- Experience no abrupt withdrawal of service

- Final Evaluation and Strategic Recommendations

A comprehensive end-of-programme report will include:

- Comparative Year 1 and Year 2 outcomes

- Cost-benefit and return on investment analysis

- Strategic recommendations for commissioning, scaling, or alternative delivery models

Stakeholder Engagement and Communication

- Early notification of closure timelines

- Ongoing engagement with Health Board leadership and partners

- Clear communication to maintain continuity of care and system confidence

This approach ensures that the exit is managed safely, learning is retained, and system value is maximised.

- ‘Why’ the use of Charitable Funding

This request aligns strongly with charitable funding principles:

- Enhances patient wellbeing beyond statutory provision

- Targets a clearly underserved group

- Enables pilot innovation and service development

- Leverages external partnership funding

Without charitable support, this service will not be established, and the current gap will remain.

- RECOMMENDATION

This proposal provides a practical, evidence-based solution to a clearly identified gap within Swansea Bay.

It offers:

- Immediate benefit to veterans and their families

- Measurable improvements in patient outcomes and system efficiency

- A clear pathway to sustainable, long-term provision

Charitable investment at this stage is pivotal in enabling both delivery and future transformation of support for the Armed Forces Community.

The Charitable Funds Committee is asked to APPROVE:

- £26,062 of charitable funding per year (for no more than two years) to support a jointly funded pilot Welfare Service

- Agree the development of a clear exit strategy by the Welfare Service which would either see it being funded via other means or securing its orderly closure by the end of year two.

- Agree the fact that charitable funds will not be used beyond the second year in any circumstances.

Appendix 1,

Business Case: Welfare Service provision for Armed Forces Community patients at Swansea Bay University Health Board

Presented by Defence Medical Welfare Service

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| This project will drive up the quality and responsiveness of our services on behalf of this cohort of the population. |  |  |  |
| Financial Implications |  |  |  |
| The financial implications are clearly laid out in the paper with the backstop of no further charitable funding beyond the end of year two. Any financial implications for the Health Board after year two would need to be considered at that time with the default position being that the project would either have proved its value in terms of efficiencies and savings or would be brought to an orderly end. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| There are no legal implications. |  |  |  |
| Staffing Implications |  |  |  |
| A member of staff would be employed in order to deliver this project. An internal appointment would be preferrable and any appointment would need to go through the Health Board’s vacancy control process. In any case, the post would need to be filled in a way that does not expose the Health Board to continuing employment obligations beyond the end of year two. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| In delivering against its public purposes the Charity undertakes its activities in a way that supports the Future Generations Act. |  |  |  |
| Report History |  | N/A |  |
| Appendices |  | Appendix One – Business Case |  |