| Meeting Date | 16 January 2025 |  | Agenda Item |  |  | 3.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Digital Transformation Progress Report FY24/25 |  |  |  |  |  |
| Report Author | Deirdre Roberts, Assistant Director of Digital Transformation |  |  |  |  |  |
| Report Sponsor | Matthew John, Director of Digital |  |  |  |  |  |
| Presented by | Deirdre Roberts, Assistant Director of Digital Transformation |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The paper provides an overview of the digital progress made across the Health Board during Q3 FY24/25. |  |  |  |  |  |
| Key Issues | - The long-term sustainability of health and social care is dependent on having the right digital foundations in place. - The Health Board’s digital plan is aligned to the key goals, measures and outcomes of the organisations FY 24/25 annual plan. - Most digital projects included in the Digital Plan for FY24/25 are progressing to schedule or are within their programme tolerance. - Delays pertaining to the delivery of key projects have been escalated locally and / or nationally; Swansea Bay Patient Portal, Radiology Information Management System and the Laboratory Information Management System. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - Receive the progress being made across the digital portfolio of projects year to date. - Receive the process in place to manage risks related to the delivery of the digital plan. |  |  |  |  |  |

DIGITAL TRANSFORMATION PROGRESS REPORT FY24/25

- INTRODUCTION

The paper provides a summary on the digital transformation progress across the six key digital programmes of work during Q3 FY24/25.

# DIGITAL ANNUAL PLAN PROGRESS Q3

The RAG status used within this report is aligned to the Integrated Medium Term Plan (IMTP) quarterly reporting mechanisms.  Table 1 provides a key of the statuses that are used to reflect delivery against the milestones outlined in the plan.

Table 1

| Green | ON TRACK - Action progressing as planned and to agreed timelines |
| --- | --- |
| Amber | OFF TRACK - action not progressing as planned/ to original timelines, however this is manageable and mitigating actions are in place |
| Red | OFF TRACK - action not progressing as planned/ to original timelines, there are significant issues which require escalating |

## 2.1 Patient Empowerment & Outpatient Modernisation

Paperless Outpatients <Green>: 17 services across multiple specialities are currently running paperless outpatient clinics. This means that clinicians in these services are undertaking consultations using the electronic information available and not the paper record. An estimated 22,906 (15%) face to face appointments have been undertaken without the paper record during Q3. The focus for Q4 is a go live across the Breast service and The Early Pregnancy Clinic Singleton Hospital.

Video Consultations<Amber>: In August 2024 Health boards were informed that the TEC Cymru Virtual Consultations programme would be closing, and that the national contract with Attend Anywhere would cease at the end of March 2025. The digital team are assessing the appropriateness of Teams as an alternative solution for the current user base; potentially negating the need to extend the current contract (cost of extension is £30k inclusive of VAT).

In parallel, the Health Board has agreed a mechanism to extend the current contract with the supplier; should a contract extension be required i.e. Teams is deemed unsuitable for virtual consultations.

Swansea Bay Patient Portal <Amber>: A public communication campaign to promote the availability and benefits of the Swansea Bay Patient Portal (SBPP) has been developed in readiness for the relaunch of the SBPP in February ’25. Over 200,000 patients and citizens are registered with portal accounts but only 8,986 patients and citizens have “claimed” their record. Adoption of the SBPP has been inhibited by delayed approvals for use of the NHS log- in function. The NHS log-in function is used to authenticate patients and citizens, after which point, they can subsequently “claim” their record. Agreement from Digital Health Care Wales (DHCW) and NHS England is required before the NHS log in function can be used with the SBPP. The approval process has taken over 12 months to date, considerably delaying the implementation of the portal. Final stages of approval are underway with submissions to national change advisory boards scheduled for early and mid – Jan in readiness for a February ’25 go live.

Hybrid Mail <Amber>: Hybrid mail can be described as posted mail (letters, leaflets, brochures etc) delivered using a combination of electronic and physical delivery; by outsourcing to a 3rd party company (Synertec). It is being used by Rheumatology and Dermatology to upload outpatient letters/inserts to the Swansea Bay Patient Portal (SBPP) or print and post with a hybrid mail solution. Functionality is being rolled out incrementally across all services from February ’25 on the assumption that the NHS log in issue referenced above is resolved. Efficiency savings derived from the project are proportionate to the adoption of the SBPP. A task and finish group has been established between digital, service groups, communications and the booking office to ensure adoption is promoted and encouraged at all touch points with patients and citizens. Services have been advised to confirm adoption targets and report progress against targets to the recovery and sustainability board.

## 2.2 Unscheduled Care, Emergency Care and Hospital Patient Flow

Signal <Green>: Version 3.4 of Signal was released on the 19th of November. The release includes functionality to embed new guidance from Welsh Government to support monthly reporting of clinical optimised patients; ensuring updated definitions and correct packages of care delay codes are recorded. Version 3.5 is on schedule for deployment at the end of January; the release is focused on mental health functionality in response to a recent Regulation 28 report from Welsh Government.

Hospital Electronic Prescribing and Medicines Administration (HEPMA) <Green>:

HEPMA is now live across all sites; the Surgical, Mental Health and Learning Disabilities evaluation is underway. Refinements to the out of hours support model were implemented on the 9th December; support hours are now 7am – 11pm weekdays and 9am – 1pm on Saturdays, Sundays and bank holidays, removing the requirement for a 24 x 7 on call rota. Urgent and emergency support i.e. system unavailable to all users will continue to be supported out of hours. A new release (v8.2) is on schedule for release at the end of January which includes key clinical functionality e.g. dose range prescribing.

Welsh Clinical Portal (WCP) <Amber>: Hospital Initiated Referral functionality has been developed in WCP to enable an electronic process for internal hospital referrals. This will transform the way  referrals are made, monitored and actioned between clinicians in SBUHB. An initial pilot in the Neurology service has identified the need for further development which is being undertaken by DHCW in readiness for health board wide adoption from Q4. A go live of the palliative care elements of the cancer module has been deferred from Q3 to Q4 (mid – January) due to a shortage of clinical leads to undertake testing. Go live of the remaining elements of the cancer module are on schedule to go live during Q4 allowing for the decommissioning of the existing legacy system (CANISC) across Wales.

Laboratory Information Management System 2 <Amber>: The Health Board continues to work in collaboration with organisations across Wales on this programme. A change control notice has been agreed to delay the SBUHB go live from Feb to May ’24 to accommodate additional time for Health Board testing and resolution to defects. SBUHB and HDUHB will be the first Health Boards in Wales to adopt the new solution which will help facilitate regional pathology across both organisations.

Radiology Information System Procurement <Amber>: This ambitious national programme will replace the current Radiology Information System (RIS) and Picture Archive Communication System (PACS). The Health Board is scheduled to go live in October 2025. Concerns relating to the challenging timescales have been discussed locally and nationally. To mitigate against the risk of being without a PACS system, the Health Board is extending its contract for the existing PACS service to ensure services are unaffected by any potential delays in the national programme. The contract extension received Health Board approval in December 2024.

2.3 Integrated Health and Care

Connected Care:  Management Board approved the initiation of a new project during Q4, which will oversee the procurement of a new solution to support the integrated teams (approx. 750 users) who currently use the Swansea Council instance of the Welsh Community Care Information System (WCCIS), which will be out of support in January 2026. The Health Board will be working closely with Swansea Council to ensure alignment of approaches and plans, such that integrated teams can continue to work efficiently, and there is no detrimental impact to service provision.

## 2.4 Digital Infrastructure

Imprivata (solution to facilitate fast log in to computer systems) <Green>:  Imprivata provides a solution to facilitate fast access to computer systems. The login to the computer is made quicker and easier by simply tapping an Identity (ID) card on a card reader instead of entering a login and password using a computer keyboard, similar to chip and PIN when paying for goods. This solution is very efficient when used on shared devices, for example the Hospital e-prescribing and Medication Administration (HEPMA) carts and significantly reduces login times. 3.2

Rollout across most in-patient wards has completed. Implementation across maternity and Ophthalmology outpatients completed in December 2024; the implementation in theatres and outpatients is scheduled to conclude by the end of Q4.

Cloud Business Case <Amber>: Digital Services continue to develop the SBU Cloud Business Case. As systems are upgraded/ renewed, Software as a Service solutions are becoming more prevalent and therefore the health board is adopting these solutions such as Patients Know Best, NHS Wales app, Microsoft 365, Oracle Financials, Allocate HR system and future services such as RISP and WLIMS2. In addition, initial exploratory work has begun utilising Microsoft Azure and the National Data Repository investment in Google Cloud. A cloud approach will be developed in the context of the digital .

Tech Refresh <Green>: In December the Health Board received an additional £1.91m Welsh Government funding for Tech Refresh.

£1.81m has been allocated to upgrade the core networks at Morriston and Singleton (Phase 1) which are running on legacy technology, it is essential that these are upgraded to modern networks which have better security to protect against cyber security threats. Phase 2 requires further investment (approximately £1.8m) to replace the hospitals network switches which provide access to computers, video surveillance systems, medical equipment (such as CT scanners, MRI scanners) to ensure highly available and resilient access.

The additional £100K has been allocated to upgrade devices i.e. desktop and laptop devices which are too old to run Windows 11. As of October 2025, Windows 10 will no longer receive critical updates to protect against known vulnerabilities. Further funding in the region of £1.45m will be required to address the remaining devices.

## 2.5 Business Intelligence (BI) <Green>: Key achievements during Q3 include the development of the bed modelling tool (phase 1) which will act as an enabler to establish the impact of schemes and external pressures on the number of hospital beds required. Other achievements include the launch of the quality and safety dashboard and development of a machine learning auto coding model which will be integrated into the clinical coding application for testing in Q4. Once successfully tested and deployed this application will automate diagnosis and procedure codes for specific episodes of care, expediting the time taken to code.

2.6 Centralisation of Medical Records <Green>: Ty Samlet has now been handed over to the Health Board (November 2024) and is currently having racking fitted to facilitate the move of active records from the Health Boards three main hospital sites and unit 32. The ambition to also house records currently in storage in offsite facilities. The records should start to flow into the Ty Samlet from late January 2025. The Organisational Change Process (OCP) has completed, and all staff are aware of their outcomes. The project is on schedule to have the unit operational from April 2025.

- GOVERNANCE AND RISK ISSUES

Governance

The digital plan is overseen by the Digital Leadership Group (DLG), which has representation from each corporate directorate and service delivery group and meets quarterly. The DLG reports to Management Board. The delivery of the digital plan continues to be managed by digital programme boards, providing updates and / or escalations (where appropriate) to DLG.

Risk

Risks pertaining to the delivery of digital programmes are managed via the relevant programme board and escalated to DLG when necessary. Risks that impact a live operational service will be recorded via the digital service management group (DSMG). Where a digital risk impacts a service or a service delivery group (SDG), digital will work with the relevant SDG to ensure the risk and associated impact is reflected on the SDG risk register and where relevant, escalated to the Health Board risk register. For example, the lack of a digital solution in Mental Health, Learning Disabilities (MHLD) and Community has been recorded by the digital Integrated Health and Care Programme Board as a digital risk, a separate but related risk has been recorded by the SDGs. Given the impact associated with the risk it has been jointly escalated by the SDGs to the Health Board risk register.

- RECOMMENDATION

Members are asked to:

- Receive the progress being made across the digital portfolio of projects year to date.

- Receive the process in place to manage risks related to the delivery of the digital plan.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Implementation of digital systems in healthcare can have a significant positive impact on quality, safety and patient experience. Critical to success is the wide scale adoption of an effective business change model, digital service team capacity and capability, workforce digital skills and clinical leadership. |  |  |  |
| Financial Implications |  |  |  |
| Please reference agenda item 2.4 – Digital Financial Management |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| None. |  |  |  |
| Staffing Implications |  |  |  |
| Increasing numbers of staff will be required to deliver the digital change programme in SBUHB. This will be detailed in future workforce plans, individual business cases and digital priorities and plans. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| - Long Term – Health and Social Care “A Healthier Wales” (2018) sets out a long term future vision of a ‘whole system approach to health and social care’, which is focussed on health and wellbeing, and on preventing illness - Wellbeing of Future Generations Act (2015) - Focus on prevention, not service provision. - Prevent ill health, reduce impact of illness or injury and delay onset of frailty. - Provide services to carers that prevent, reduce, or delay them developing a need for support. - SBU HB’s Clinical Services Plan (2019-2024) - Adoption of digital solutions and technology. - Create a mobile workforce that is digitally connected to ensure staff work seamlessly to ‘Make Every Contact Count’. - Technology to support care closer to the patient’s home or in the community. |  |  |  |
| Report History |  | November 2024 |  |
| Appendices |  | Nil |  |