| Meeting Date | 22 January 2026 |  | Agenda Item |  |  | 5.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Digital, Data, Research and Innovation Committee |  |  |  |  |  |
| Report Title | Digital Strategy and Plan Update Focus on Quarter 4 challenge; risk; mitigation |  |  |  |  |  |
| Report Author | Tracey Bell, Head of Digital Planning, Unscheduled and Community Care Gareth O’ Gorman, Head of Digital Planning, Diagnostics and Patient Flow |  |  |  |  |  |
| Report Sponsor | Matthew John, Director of Digital |  |  |  |  |  |
| Presented by | Deirdre Roberts, Assistant Director of Digital Transformation |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The paper provides a summary of digital transformation progress for delivery of milestones in Q4 of Financial Year (FY) 2025/2026, with a focus on key risks and mitigations. Delivery milestones are spread across eight programmes of work, aligned to the digital strategic plan, the Integrated Medium-Term Plan (IMTP) and the organisational strategy. |  |  |  |  |  |
| Key Issues | - The long-term sustainability of health and social care is dependent on having the right digital foundations in place. - The Health Board’s digital plan is aligned to the recently approved Digital Strategy, and the three priority components that contribute to the delivery of a health and social care record. - Delays pertaining to the delivery of projects have been escalated locally and/or nationally: Radiology Information Management System, Laboratory Information Management System and Digital Maternity. - A significant number of projects are scheduled to go live in Quarter 4 of 2025/26, with many deadlines mandated by Welsh Government. This concentration of national requirements, combined with local priorities, results is an ambitious delivery period for Q4. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| thematic | Members are asked to: RECEIVE: the update on the FY2025/2026 Q4 scheduled digital delivery noting the number of parallel implementations. CONSIDER: the delivery risks for Q4, taking into account the established risk management framework and the proposed mitigation strategies. |  |  |  |  |  |

Quarter 4 Delivery Plan and associated risks

- INTRODUCTION

The Swansea Bay University Health Board’s Digital strategic plan is aligned with the organisation’s Integrated Medium-Term Plan (IMTP) including the 2025/2026 digital work programme.

A significant number of projects are scheduled to go live in Quarter 4 of 25/26. Delivery in Quarter 4 has been imposed for several reasons, including funding availability for Financial Year 25/26 and delivery deadlines mandated by Welsh Government. This concentration of national requirements, combined with local priorities, results is an ambitious delivery period. The need to balance national directives with operational realities will challenge the Health Board’s ability to deliver against these deadlines, requiring agile resource allocation, robust risk management, and clear communication to ensure successful delivery and sustainable transformation.

This paper sets out the key milestones scheduled for delivery in Quarter 4 of 2025/2026, highlighting key risks and mitigations to deliver against the ambitious timescales.

# BACKGROUND

The Digital 3-year plan was developed and assured by DDRI in July 2025 which demonstrated alignment between the digital strategic plan, the IMTP and the organisational strategy.

A three-year “Plan on a Page” provides a high-level view of the digital transformation journey for 2025 – 2028 (refer to Appendix 1). It demonstrates how key programmes and enabling capabilities such as infrastructure upgrades, digital front door initiatives, data platform enhancements, and workforce development are sequenced. It serves as a reference point for external and internal stakeholders, including the DDRI Committee.

The 2025/2026 timeline (Appendix 1, Figure 2) provides a high-level overview of digital transformation schemes for delivery in Financial Year 2025/2026. A detailed Project Delivery Dashboard for active Digital projects in FY 2025/2026 has been developed to support the high-level overview and is provided in Appendix 2.

- Quarter 4 Delivery Schedule

The delivery of multiple programmes of work scheduled for delivery during Quarter 4 has been recognised by DDRI as a pressure for digital and operational services, which may impact the pace and effectiveness of organisational change.

Figure 1 outlines the Quarter 4 Digital Transformation Programme plan, detailing key delivery milestones. It reflects the high volume of concurrent system go-lives scheduled within a compressed timeframe and underscores the extensive readiness and stakeholder engagement activities currently underway to ensure successful deployment.

Figure 1

- GOVERNANCE AND RISK ISSUES

Governance

Digital delivery for Quarter 4 continues to be governed by dedicated digital programme boards, which include representation from clinical and operational teams. These boards provide regular progress updates and escalate risks, where necessary, to the Digital Leadership Group and the relevant Health Board Care Boards (e.g., Unscheduled Care, Mental Health, and Planned Care). Reporting to the appropriate Care Board is critical to ensure delivery timelines are understood, resources are aligned to support implementation and service transformation, and that risks, coupled with mitigation strategies are actively monitored and addressed.

Risks pertaining to live operational services continue to be managed via the digital service management group (DSMG).

Throughout the year, the digital team have worked closely with service leads to identify emerging risks early, assessing potential impact, and agreeing mitigation strategies to safeguard delivery and maintain patient safety. In addition to the governance framework in place key risks have been described in project specific updates for management board and where necessary individual risks have been added to the relevant service delivery group register and / or escalated to the Health Board risk register.

Risk

Key risks specific to Quarter 4 delivery are set out below:

Laboratory Information Management System 2 (LIMS):

- SBUHB Cellular Pathology was scheduled to go live during November, bringing the first users in Wales onto the system. Delays in defect resolution and testing the bulk data upload has delayed go live. A revised go live date of the 12th January 2026 has been agreed and the Health Board is confident in meeting that date.

- Blood sciences the national team is working up a plan with the aim to go live across Wales by end of Quarter 1. Go live in Quarter 1 is extremely ambitious and continues to be a risk given the number outstanding defects for resolution i.e. 217 severity 1 and 2 defects that need to be resolved prior to go live.

- Microbiology will go live by the end of April 2026. This will be a “big – bang” implementation approach across Wales. The Health Board is confident in meeting this deadline.

- Blood bank

  - The blood bank module of the current Laboratory Information Management System (LIMS) starts to be unsupported from August 2026 with different components becoming end of life over the subsequent months thereafter.

  - SBUHB are one of four Health Boards migrating to the blood bank module of the new LIMS (CAVUHB and ABUHB are procuring alternative solutions). At present, there is no national published plan to inform Health Board go live dates.

  - There is a risk to the Health Board that the blood bank module of LIMS 2 will not be available to the Health Board in readiness for the decommissioning of the current platform.

  - There is an associated risk that the current blood bank platform requires continued investment and support to maintain service provision whilst the migration to the new solution is underway.

To mitigate against the risks associated with the delayed delivery to the blood sciences and blood bank modules of LIMS 2 the national programme board has requested a “back up” plan from DHCW, including additional costs to maintain the existing solutions for these services whilst readiness for the new solution runs in parallel. An initial figure of £0.4m per quarter for SBUHB was provided. These figures are being revised by the national programme and an update is expected in January. The project continues to submit monthly updates to management board with progress updates and risks highlighted. Delays to the LIMS programme is included in the Health Board risk register (Datix ID 3114 – score 16).

Radiology Information System Programme

- The Health Board is scheduled to go live on the 23rd February 2026. SBUHB have committed the necessary resource and effort available across digital and operational teams to maintain the date.

- Good progress has been made in Quarter 3 in the configuration of the Radiology system and the PACS data migration activity.

- There is a risk that testing of the Radiology system (RAD+) which commences 5th January will surface severity 1 defects which could delay go live.

- In addition, there is a risk that activity to connect radiology scanners and check sending live images to the new PACS alongside the existing PACS (known as ‘wet runs’) scheduled for 21st January to 11th February will impact go live.

- To mitigate against this, the project team is maintaining rigorous oversight of the project plan, with particular attention to the critical path and interdependencies between key stakeholders DHCW, Swansea Bay, Soliton (Radiology system provider), and Philips (PACS provider). This ensures all leads have full visibility of delivery dates, dependency linkages, and the limited timeframes available to meet their respective deliverables, especially where one party’s output is a prerequisite for another.

- The Health Board remains concerned about Philips’ capacity to successfully manage their deliverables to meet a 23rd February 2026 go-live and continue to escalate the importance of meeting agreed milestones during Quarter 4 to the Phillips Managing Director. A follow up meeting with the Phillips Managing Director has been requested for early January.

- These escalations are in addition to the existing reporting and escalation mechanism via the local project board and national programme board.

- The Health Board has a commitment of £1.4m for the initial go live payment to Philips. If Philips are unable to deliver within this financial year the Health Board will be unable to utilise the full funding allocation. SBUHB finance colleagues are continuing to work with DHCW finance on mitigation, with any potential impact this financial year likely to be significantly lower; in the region of £150k.

- The SBU current Picture Archiving and Communications System (PACS) contract (Fuji) has been extended to March 2027 by way of mitigation should delivery timescales slip beyond March 2026. A delayed go live has an associated benefit of reduced dual running costs alongside the Fuji contract.

- The SBUHB RISP Project Board continues to oversee delivery against the plan and mitigations for utilising the full funding allocation should Philips be unable to deliver within this financial year. The project will continue to submit monthly updates to management board on progress and risks.

Unscheduled & Emergency Care:

Minor Injuries Unit (MIU) – Contract Expiry

- The Minor Injury Unit currently use the Welsh Emergency Department System (WEDS) provided by Optum which expires 31st August 2026. A replacement solution is required.

- At the request of the national 6 goals programme for unscheduled care, DHCW have developed the UEC app (including the Welsh Emergency Care Data Set (WECDS) dataset) as a Minimal Viable Product (MVP) to replace the functionality in WPAS ED.

- SBUHB have also had agreement that it can be implemented in the MIU as a short-term tactical solution followed by a potential implementation in the Emergency Department.

- Testing of the solution by Health Boards was due to commence in Q3 but delays to development means testing will not commence until February 2026. The risk pertaining to the continued delay of the app, associated integrations and the lack of data migration could result in the UEC App not being delivered in time to replace WEDS in the MIU, in line with the contractual end date.

Suitability of the UEC App to support the UEC footprint

- There is continued concern that the solution will not provide the functionality to support the UEC footprint in Swansea Bay, including rationalising the number of systems in use.

- Recent usability testing with clinicians has raised concerns on the suitability of the app with the clinical leads suggesting it is a backwards step for the ED department in particular.

- To mitigate this risk the health board are engaging with third party suppliers to establish how alternative solutions could support flow and safety across the UEC footprint, including the timescales for delivery.

- Funding for a third party UEC solution is being factored into the UEC re-design discussions between the Health Board and Welsh Government.

- These risks continue to be discussed at the UEC Care Board and a paper setting out proposed options is being developed for consideration by Executives.

Digital Maternity:

- Three out of the four key integrations with the national technical architecture included within all Health Board’s contracts will not be delivered for Phase 1 (31st March), given delivery of the integration components was not included in the DHCW IMTP plan for 2025/2026.

- This presents several clinical risks (e.g. dual data entry, administrative burdens, delays in care delivery, transcription error, incorrect patient selection) and a potential impact to clinical engagement across maternity services and overall patient care.

- A clinical risk assessment has been undertaken by lead Digital Midwives across Wales; a summarised view of these assessments is being prepared by the Director of Digital in Aneurin Bevan Health Board, for consideration by the Digital Maternity Technical Advisory Group; to establish if integrations can be delivered and/or agree workarounds to mitigate the risks highlighted. In parallel discussions are ongoing with DHCW to ensure integration requirements are included in the 2026/2027 IMTP plan.

- Although SBUHB are continuing to work towards a March go live, the Health Board is constrained by other Health Board implementations that are closely scheduled ahead of the SBUHB go live, therefore there is a risk that the Health Board may not meet the aggressive timescale of March 31st, 2026. To mitigate this risk SBUHB are working closely with the supplier, DHCW and regionally with Hywel Dda to share lessons learned with a focus on system configuration.

Open Eyes Electronic Referral System (ERS):

- The Open Eyes Electronic Patient Record (EPR) has been successfully implemented across all speciality pathways and configuration continues to support clinical workflows.

- However, in addition to the implementation of Open Eyes, health boards are also required to implement an Electronic Referral System (ERS) in Quarter 4.

- DHCW have procured Opera from a third-party supplier (RMSL), however this is yet to be configured to support the Wales General Ophthalmic Services (WGOS) pathways, and the order of implementation nationally has not yet been agreed making a March 2026 go live extremely challenging.

- To mitigate this risk, SBUHB are continuing to engage with DHCW and the supplier to understand the level of national and local configuration needed, as well as the resources required to support an implementation by March 2026.

Signal Admission Discharge and Transfer (ADT) development

- Given the contractual commitments to deliver other projects in Quarter 4, resources to deliver Admission, Discharge and Transfer developments in Signal are constrained.

- The development plan is being revisited, which may lead to a delay beyond Quarter 4.

Morriston Data Network Replacement: Work is underway to procure network equipment in readiness to replace the data network at Morriston. Funding has recently been secured from Welsh Government to enable this to happen. The procurement process has commenced, and the risk is any delay in the approval process could mean that equipment is delivered after the end of 2025/26 and that funding could not be fully utilised, creating a pressure in next financial year.

- FINANCIAL IMPLICATIONS

All digital projects scheduled for delivery in Quarter 4 of 2025/26 have secured funding either through direct allocations from Welsh Government, utilisation of existing resources within Digital Services, or a combination of both. This ensures that each project is financially underpinned, supporting the Health Board’s commitment to delivering its digital transformation objectives within the agreed timeframe.

Project budgets are subject to robust monitoring and are reported on in accordance with the arrangements set out in the separate finance paper to the DDRI Committee. This ensures transparency and accountability, with regular updates provided to both the Committee and the Health Board’s management structures.

It is important to note that any slippage in the delivery of key projects beyond Quarter 4 of 2025/26 will have financial implications that the Health Board will need to manage. As outlined above there are two projects that have specific external financial implications from slippage:

Radiology Information System Programme (RISP): The Health Board has committed £1.4 million for the initial go-live payment to Philips. Should delivery slip beyond the current financial year, the impact is likely to be significantly lower, in the region of £150,000. The contract for the current Picture Archiving and Communications System (PACS) has been extended to March 2027 as a mitigation, which may reduce dual running costs if go-live is delayed.

Laboratory Information Management System (LIMS): To mitigate risks associated with delayed delivery of the blood sciences and blood bank modules, the national programme board has requested a “back up” plan from DHCW, including additional costs to maintain existing solutions while readiness for the new solution runs in parallel. An initial figure of £0.4 million per quarter for Swansea Bay University Health Board was provided, with revised figures expected in January.

Delays in other projects after 2025/26 will require the reallocation of resources from 2026/27 IMTP objectives to finish implementation.

These financial implications are being actively managed through close collaboration between Digital Services, Capital Finance, and are escalated to the Executive Team as appropriate. This ensures that risks are identified early, mitigation strategies are developed, and any required decisions are taken at the appropriate level to safeguard both service delivery and financial sustainability.

The introduction of new Health Board financial controls may also impact the ability to deliver digital projects, particularly where restrictions on variable spend and procurement are in place. These controls, while necessary for overall financial governance, have the potential to introduce delays if not managed proactively. It is therefore essential that Digital Services work closely with the Executive Team, Finance and Procurement colleagues to ensure that any constraints are identified and addressed early, minimising the risk of unnecessary delays to project delivery and ensuring that the Health Board continues to meet its strategic objectives.

- RECOMMENDATION

Members are asked to:

RECEIVE: the update on the FY2025/2026 Q4 scheduled digital delivery noting the number of parallel implementations.

CONSIDER: the delivery risks for Q4, taking into account the established risk management framework and the proposed mitigation strategies.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |  |
|  | Co-Production and Health Literacy |  | ☒ |  |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |  |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High-Quality Care |  | ☒ |  |
|  | Partnerships for Care |  | ☒ |  |
|  | Excellent Staff |  | ☒ |  |
|  | Digitally Enabled Care |  | ☒ |  |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |  |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |  |
|  | Safe Care |  | ☒ |  |
|  | Effective Care |  | ☒ |  |
|  | Dignified Care |  | ☒ |  |
|  | Timely Care |  | ☒ |  |
|  | Individual Care |  | ☒ |  |
|  | Staff and Resources |  | ☒ |  |
| Quality, Safety and Patient Experience |  |  |  |
| Implementation of digital systems in healthcare can have a significant positive impact on quality, safety, and patient experience. Critical to success is the wide scale adoption of an effective business change model, digital service team capacity and capability, workforce digital skills and clinical leadership. |  |  |  |  |
| Financial Implications |  |  |  |
| Please reference agenda: Digital Financial Management |  |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| None. |  |  |  |  |
| Staffing Implications |  |  |  |
| Increasing numbers of staff will be required to deliver the digital change programme in SBUHB. This will be detailed in future workforce plans, individual business cases and digital priorities and plans. |  |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| - Long Term – Health and Social Care “A Healthier Wales” (2018) sets out a long-term future vision of a ‘whole system approach to health and social care’, which is focussed on health and wellbeing, and on preventing illness - Wellbeing of Future Generations Act (2015) - Focus on prevention, not service provision. - Prevent ill health, reduce impact of illness or injury and delay onset of frailty. - Provide services to carers that prevent, reduce, or delay them developing a need for support. - Swansea Bay University Health Board’s Clinical Services Plan (2019-2024) - Adoption of digital solutions and technology. - Create a mobile workforce that is digitally connected to ensure staff work seamlessly to ‘Make Every Contact Count’. - Technology to support care closer to the patient’s home or in the community. |  |  |  |  |
| Report History |  |  |  |  |
| Appendices |  | Appendix 1 Appendix 2 |  |  |