| Meeting Date | 11 March 2025 |  | Agenda Item |  |  | 3.2 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Digital, Data, Research and Innovation Committee |  |  |  |  |  |
| Report Title | Digital Transformation Progress Report FY24/25 |  |  |  |  |  |
| Report Author | Deirdre Roberts, Assistant Director of Digital Transformation |  |  |  |  |  |
| Report Sponsor | Matthew John, Director of Digital |  |  |  |  |  |
| Presented by | Deirdre Roberts, Assistant Director of Digital Transformation Kerith Jones, Interim Head of Value Based Healthcare |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The paper provides an overview of the digital progress made across the Health Board during the reporting period (January and February FY24/25). |  |  |  |  |  |
| Key Issues | - The long-term sustainability of health and social care is dependent on having the right digital foundations in place. - The Health Board’s digital plan is aligned to the key goals, measures and outcomes of the organisations FY 24/25 annual plan. - Most digital projects included in the Digital Plan for FY24/25 are progressing to schedule or are within their programme tolerance. - Delays pertaining to the delivery of key diagnostics projects have been escalated locally and / or nationally; Radiology Information Management System and the Laboratory Information Management System. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - Note the progress being made across the digital portfolio of projects year to date. - Note the process in place to manage risks related to the delivery of the digital plan |  |  |  |  |  |

DIGITAL TRANSFORMATION PROGRESS REPORT FY24/25

- INTRODUCTION

The paper provides a summary on the digital transformation progress across the six key digital programmes of work during the reporting period (January and February FY24/25).

# DIGITAL ANNUAL PLAN PROGRESS Q3

The RAG status used within this report is aligned to the Integrated Medium-Term Plan (IMTP) quarterly reporting mechanisms.  Table 1 provides a key of the statuses that are used to reflect delivery against the milestones outlined in the plan.

Table 1

| Green | ON TRACK - action progressing as planned and to agreed timelines |
| --- | --- |
| Amber | OFF TRACK - action not progressing as planned/ to original timelines, however this is manageable, and mitigating actions are in place |
| Red | OFF TRACK - action not progressing as planned/ to original timelines, there are significant issues which require escalating |

## 2.1 Patient Empowerment & Outpatient Modernisation

Paperless Outpatients <Green>: 17 services across multiple specialities are currently running paperless outpatient clinics. This means that clinicians in these services are undertaking consultations using the electronic information available and not the paper record. An estimated 15,857 (17%) face to face appointments have been undertaken without the paper record during the reporting period. Development of new electronic forms for dermatology and the plastic trauma clinics has progressed these services from a paper lite to a paperless model, whilst also delivering benefits to other clinical teams involved in their patients care; by surfacing the completed forms in Welsh Clinical Portal (WCP).

Video Consultations<Green>: In August 2024 Health boards were informed that the TEC Cymru Virtual Consultations programme would be closing, and that the national contract with Attend Anywhere would cease at the end of March 2025. The digital team assessed the appropriateness of Microsoft Teams as an alternative solution, the assessment concluded that this was not a suitable alternative. The Health Board has therefore agreed to extend the contract for FY25/26, the cost of the extension for the current user base is £30k inclusive of VAT.

Swansea Bay Patient Portal <Green>: A public communication campaign to promote the availability and benefits of the Swansea Bay Patient Portal (SBPP) is in development in readiness for the relaunch of the SBPP in March ’25. Over 250,000 patients are registered with portal accounts but only 8,986 patients and citizens have “claimed” their record. Adoption has been inhibited by delayed approvals for use of the NHS login function, a function that is used to authenticate patients and citizens, after which point they can subsequently “claim” their record. Approval to use the NHS login function from Digital Health Care Wales (DHCW) and NHS England has been secured and the NHS login feature was enabled in the SBPP on the 12th February. The focus for March and FY25/26 is communication and patient engagement to expedite adoption rates whilst supporting patients and clinical teams to maximise the associated benefits including self-management.

Hybrid Mail <Green>: Hybrid mail can be described as posted mail (letters, leaflets, brochures etc) delivered using a combination of electronic and physical delivery; by outsourcing to a 3rd party company (Synertec). It is used to upload outpatient letters/inserts to the Swansea Bay Patient Portal (SBPP) or print and post with a hybrid mail solution. 5 services are live with the solution, 3 services went live during the reporting period (ear, nose and throat (ENT), respiratory and trauma and orthopaedics). Implementation across all services is being managed incrementally with a further 3 services due to go live the end of March. A newly established task and finish group to oversee the implementation of hybrid mail has met twice during the reporting period, focusing on the communication campaign to support patient adoption.  Services have been advised to confirm adoption targets for 25/26 with a view progress against targets will be reported via the recovery and sustainability board.

Digital Health Assessment Solution <Green>:  6 services are now live with collecting Digital Health Assessments (DHAs) from patient appointments in the Welsh Patient Administration System (WPAS) and Patient Information Management System (PIMS).  The auto form trigger from inpatient discharge (via a view in Signal), is currently scheduled to go live in the community Stroke service by the end of February 2025.  Auto form triggers from surgical procedures and any secondary care waiting list are due to go live by the end of March and end of June respectively.  These triggers will enable 9 more services to go live by the end of June 2025.  Additional work includes:

- Promptly Patient Portal via the NHS App – development phase commenced

- Data Standards (PSOM) – Work ongoing with Welsh Value in Health Centre (WViH) & Supplier

- Engagement / analytics view within Promptly – currently being tested

- Digital Health Assessments viewed with WCP – Hywel Dda Health Board currently scoping

3Ps Waiting Well National programme <Green>: 9 of the most used WPAS letters have the Waiting Well website link and QR code, 184k letters have been sent to date.  There has been a steady increase in hits to the website pages, increasing from 137 in April 2024 to 1,500 hits in January 2025, with more pages being added to it regularly.  The Single Point of Contact (SPOC) team is being established with the second round of recruitment for call handlers underway.  The Health Board is aiming to have a full team in place by the end of March 2025.  The Health Screening Questionnaire (HSQ) for patients referred for surgery is currently being validated, this is being manually collected by the SPOC, Pre-Assessment and Service teams and will be completed by the end April 2025.  HSQ will then be configured and tested in the DHA solution (Promptly) from May 2025 to August 2025 with a view to go live by the end of August 2025.  HSQ comprises of waiting list validation questions, frailty screening, national pre-assessment screening and questions asking patients how they feel completing the form digitally.

## 2.2 Unscheduled Care, Emergency Care and Hospital Patient Flow

Signal <Green>: Development of v 3.5 commenced during the reporting period in readiness for a release in April 2025.  The release will include capturing of mental health metrics to support section 28 reporting requirements, care after death functionality and performance enhancements.

Hospital electronic Prescribing and Medicines Administration (HEPMA) <Green>:

A new release (v8.2) of the software was successfully deployed on the 27th January. The release includes key clinical functionality e.g. dose range prescribing and self-service password reset capability. The digital team were deployed onsite to support users until mid-February. Work continues to optimise the use of the system including new features delivered via v8.2.

Welsh Clinical Portal (WCP) <Amber>: Hospital Initiated Referral functionality has been developed in WCP to enable an electronic process for internal hospital referrals. This will transform the way referrals are made, monitored and actioned between clinicians in SBUHB. An initial pilot in the Neurology service identified the need for further system enhancements which were delivered in February. These fixes will support further rollout, implementations in March will focus on Neurology > Neurology referrals and referrals from the Emergency Department (ED) to services. The palliative care elements of the cancer module went live at the end of January. Remaining elements of the cancer module are due to go live during Q4 allowing for the decommissioning of the existing legacy system (CANISC) across Wales.

Laboratory Information Management System 2 <Amber>: The Health Board continues to work in collaboration with organisations across Wales on this programme (current go live date is May ’25). Concerns pertaining to the ambitious delivery timescales persist; these have been escalated by the Health Board to the national programme board with options for consideration.

Radiology Information System Procurement <Amber>: This ambitious national programme will replace the current Radiology Information System (RIS) and Picture Archive Communication System (PACS). The Health Board is scheduled to go live in October 2025. Concerns relating to the challenging timescales continue to be reported to the local project board and national programme board.  To mitigate against the risk of being without a PACS system, the Health Board has extended its contract for the existing PACS service to ensure services are unaffected by potential delays in the national programme. The contract extension has been approved by the Health Board (December 24) and Welsh Government (February 25).

2.3 Integrated Health and Care

Connected Care <Green>:  Ongoing planning discussions continue with local authority partners and the Access Group to mitigate the risks associated to the decommissioning of the Welsh Community Care Information System (WCCIS).  SBUHB have received the business proposal from the Access Group and the project team have been working through this with technical colleagues, key stakeholders and procurement. The intention is to direct award to The Access Group by the end of February to ensure implementation plans for Swansea Council and SBUHB can be aligned, such that integrated teams working across both organisations will not be required to revert to paper and manual processes.

## Digital Infrastructure

Imprivata (solution to facilitate fast log in to computer systems) <Green>:  Imprivata provides a solution to facilitate fast access to computer systems. The login to the computer is made quicker and easier by simply tapping an Identity (ID) card on a card reader instead of entering a login and password using a computer keyboard, similar to chip and PIN when paying for goods. This solution is very efficient when used on shared devices, for example the Hospital e-prescribing and Medication Administration (HEPMA) carts and significantly reduces login times.

Rollout across most in-patient wards has completed; implementation in theatres and outpatients is scheduled to conclude by the end of Q4.

Cloud Business Case <Amber>: Digital Services continue to develop the SBU Cloud Business Case. As systems are upgraded/ renewed, ‘Software as a Service’ solutions are becoming more prevalent and therefore the Health Board is adopting these solutions such as Patients Know Best, NHS Wales app, Microsoft 365, Oracle Financials, Allocate HR system and future services such as RISP and WLIMS2. In addition, initial exploratory work has begun utilising Microsoft Azure and the National Data Resource investment in Google Cloud. A cloud approach will be developed in the context of the digital strategy.

Tech Refresh <Green>: As the Health Board becomes increasingly reliant on digital services to transform health care services, the underlying infrastructure used to deliver and access digital services must be built on a solid foundation. The Health Board has received significant funding in 24/25 to address priority tech refresh infrastructure requirements for 24/25 and 25/26. The total amount of capital received in this financial year in £7.2m (Health Board discretionary and Welsh Government capital). The funding will enable key programmes of working including:

- Replacement of the core networks at Morriston and Singleton

- Replacement of the Singleton Hospital network by replacing the hospital network switches which provide access to computers, video surveillance systems, medical equipment (such as CT scanners, MRI scanners).

- Replace the wireless network at Neath Port Talbot Hospital

- Replacement of the computer backup system with additional protection against cyber-attacks

- Replacement of unsupported desktop and laptop computers whilst also migrating from Windows 10 to 11 in parallel.

## 2.5 Business Intelligence (BI) <Green>: Key achievements include the launch of the Population Health App that brings together a suite of population tools into one place - including a new report demonstrating strategic indicators for ‘Objective 1 – People of Swansea Bay live healthier, equitable and more equal and prosperous lives’. Other achievements include a cellular pathology dashboard showing histology activity data and a discrete simulation model for the Minor Injury Unit (MIU) showing the impact of longer opening hours on both MIU and ED in Morriston. Testing of a machine learning auto coding model that has been integrated into the clinical coding application has commenced. Once successfully tested and deployed this application will automate diagnosis and procedure codes for specific episodes of care, expediting the time taken to code.

2.6 Centralisation of Medical Records <Green>:  Racking has been installed in Ty Samlet with records currently being moved into the unit from acute sites. Some health records staff are now based at the unit to prepare any clinic notes that have already been moved to the unit. The Coding Department will move to the unit from early March and the project remains on schedule to have the unit fully operational from April 2025.

- GOVERNANCE AND RISK ISSUES

Governance

The digital plan is overseen by the Digital Leadership Group (DLG), which has representation from each corporate directorate and service delivery group and meets quarterly. The DLG reports to Management Board. The delivery of the digital plan continues to be managed by digital programme boards, providing updates and / or escalations (where appropriate) to DLG.

Risk

Risks pertaining to the delivery of digital programmes are managed via the relevant programme board and escalated to DLG when necessary. Risks that impact a live operational service will be recorded via the digital service management group (DSMG). Where a digital risk impacts a service or a service delivery group (SDG), digital will work with the relevant SDG to ensure the risk and associated impact is reflected on the SDG risk register and where relevant, escalated to the Health Board risk register.

- RECOMMENDATION

Members are asked to:

- Note the progress being made across the digital portfolio of projects year to date.

- Note the process in place to manage risks related to the delivery of the digital plan.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Implementation of digital systems in healthcare can have a significant positive impact on quality, safety and patient experience. Critical to success is the wide scale adoption of an effective business change model, digital service team capacity and capability, workforce digital skills and clinical leadership. |  |  |  |
| Financial Implications |  |  |  |
| Please reference agenda: Digital Financial Management |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| None. |  |  |  |
| Staffing Implications |  |  |  |
| Increasing numbers of staff will be required to deliver the digital change programme in SBUHB. This will be detailed in future workforce plans, individual business cases and digital priorities and plans. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| - Long Term – Health and Social Care “A Healthier Wales” (2018) sets out a long term future vision of a ‘whole system approach to health and social care’, which is focussed on health and wellbeing, and on preventing illness - Wellbeing of Future Generations Act (2015) - Focus on prevention, not service provision. - Prevent ill health, reduce impact of illness or injury and delay onset of frailty. - Provide services to carers that prevent, reduce, or delay them developing a need for support. - SBU HB’s Clinical Services Plan (2019-2024) - Adoption of digital solutions and technology. - Create a mobile workforce that is digitally connected to ensure staff work seamlessly to ‘Make Every Contact Count’. - Technology to support care closer to the patient’s home or in the community. |  |  |  |
| Report History |  | Regular report to committee. |  |
| Appendices |  | Nil. |  |