CORPORATE RISK REGISTER

January 2026

RISKS ASSIGNED TO THE

DIGITAL, DATA, RESEARCH & INNOVATION COMMITTEE

| Datix ID Number: 1043 Date Opened: Apr 2019 |  | Date Last Reviewed: January 2026 |  | CRR Ref Number: 36 Risk Target Date: 31/03/2030 |  | Current Risk Rating 4 x 4 = 16 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovative digital solutions, research, development and innovation |  |  | SRR Ref: 3.4 | Director Lead: Matt John, Director of Digital Assuring Committee: Digital, Research & Innovation Committee For information: Quality & Safety Committee |  |  |  |
| Risk: Paper Record Storage Lack of a single electronic record means there is greater reliance on the provision of the paper record. If we fail to provide adequate storage facilities for paper records, then this will impact on the availability of patient records at the point of care. Quality of the paper record may also be reduced if there is poor records management in some wards. There is an increased fire risk where medical records are stored outside of the medical record libraries. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 5 = 20 Current: 4 x 4 = 16 Target: 3 x 3 =9 |  |  |  | Rationale for current score: C - Inability to find records for patients could delay care/increase length of stay over 15 days. Could also mean patients receive incorrect treatment. Increased risk of fire where records are stored outside of the medical record libraries. L - we know this happens from incidents raised |  |  |  |
|  |  |  |  | Rationale for target score: C - The increased development and adoption of the digital record will reduce the need for the paper health record being available at the point of care. L - The increased development and adoption of the digital record, will reduce the amount of paper required to be stored and managed. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - There is a plan in place to increase the functionality of the electronic record to document patient care. The delivery of the plan is overseen by the Digital Leadership Group and progress provided to Management Board. (Supported by individual project boards as appropriate). - Records managed by the Medical Records libraries are RFID-tagged (Radio Frequency Identification) and location tracked. - Medical Record libraries are regularly risk assessed for fire by health and safety. - Alternative offsite storage arrangements have been identified. - All records must be documented on the Information Asset Register (IAR). |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Allow for new process to stabilise and evaluate benefits of new centralised unit. | Head of Health Records & Clinical Coding |  | 28/02/2026 |
|  |  |  |  | Consider impact of IBCA Blood embargo on the acute records service and provide options for the health board to consider and mitigate the risk relating to storage and its associated financial pressures. | Head of Health Records & Clinical Coding |  | 31/03/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) - RFID has been implemented for the acute record improving the management and storage of records - Health Records performance reports developed in line with RFID technology - Attainment of the Tier 1 Health Board target for clinical coding completeness which relies on the timely availability and quality of the Paper record and electronic sources - Monitoring complaints and incident reporting. - Electronic record is being implemented in accordance with the plan e.g. implementation of WNCR (Welsh Nursing Care Record), ETR (Electronic Test Requesting), HEPMA (Hospital Electronic Prescribing and Medicines Administration) |  |  |  | Gaps in assurance (What additional assurances should we seek?) Investment required supporting the delivery and operational costs of the Digital strategy. Reliance on DHCW (Digital Health & Care Wales) for delivery of the solution for a fully electronic patient record. Impact of the Infected Blood Enquiry on the Health Boards ability to destroy notes. Process for ensuring clinical adoption of electronic ways of working and cessation of adding information to the paper record that is already available electronically needs to be agreed and enforced by the Health Board. Impact of the infected Blood Inquiry on the health board’s ability to destroy notes and the change in the records code of practice is being reviewed by the Director of Digital. |  |  |  |
| Additional Notes 22/12/2025 – Reviewed – no further amendments. 14/01/2026: Independent audit review now commenced with NWSSP, which will evaluate the benefits. Additional Action included relating to the impact of the IBCA blood embargo. 10/02/2026: Target rationale, date and action amended. |  |  |  |  |  |  |  |

| Datix ID Number: 2796 Date Opened: January 2023 |  | Date Last Reviewed: January 2026 |  | CRR Ref Number: 90 Target Risk Date: TBC |  | Current Risk Rating 4 x 5 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: The health board is a resilient, sustainable and responsible organisation |  |  | SRR Ref: N/A | Director Lead: Matt John, Director of Digital Assuring Committee: Digital, Research & Innovation Committee |  |  |  |
| Risk: Subject Access Request Risk If the Health Board is non-compliant with the UK-GDPR, then there is a risk of ICO enforcement action being taken against SBUHB, as well as reputational damage and the potential for claims. Due to insufficient resources and inconsistent processes across Swansea Bay University Health Board, there is a risk that Subject Access Requests (SARs) will not be fulfilled in compliance with UK-GDPR Article 15, resulting in potential breaches of personal data which could cause distress and lead to a loss of public and government confidence in the Health Board’s trustworthiness and legal standing. Additional Potential Consequences: - Regulatory Enforcement: ICO (Information Commissioner’s Office) may impose fines up to 4% of annual turnover for serious breaches. While the ICO has not historically issued fines for SAR breaches, this may change, especially as enforcement activity increases. Recent reprimands issued by the ICO to another NHS Trust and several public bodies signals heightened regulatory scrutiny. - Operational Disruption: Staff diverted from priority tasks to manage SARs, affecting service delivery - Legal Exposure: Increased risk of litigation & claims from individuals with compromised data rights. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 5 = 20 Current: 4 x 5 = 20 Target: 4 x 4 = 16 |  |  |  | Rationale for current score: C – This is assessed to be Major (score 4) under the Governance & Assurance risk domain of health board policy. Given the heightened external scrutiny of Swansea Bay University Health Board’s Maternity and Mental Health services, failure to comply with SAR requirements or mis-sharing of sensitive information in these areas could result in multiple complaints, loss of public confidence, negative media coverage, and/or criticism by Welsh government. L- The probability of one of these potential consequences occurring is currently considered to score 5 (expected – greater than 50% chance) due to a backlog and/or delays of SARs in a number of different areas. These delays are often the result of waiting for approval to release from Health Care Professionals. 2024/25 statistics showing 65% of SARs were released without full clinical approval. Certain areas have experienced surges in requests following media coverage, with further increases expected. The complexity and sensitivity of these cases, combined with limited resources and inconsistent processes, make delays and errors expected. While the risk of an ICO fine remains low, the frequency of breaches, solicitor correspondence, complaints, ICO involvement and claims for financial compensation is already high and likely to escalate. |  |  |  |
|  |  |  |  | Rationale for target score: C – As above L – Completion of tasks within the SAR Action Plan will lead to greater consistency in how SARs are managed across the Health Board, along with clearer guidance. There will also be an electronic redaction system in place to help support the initial redaction process. Completion of the Action Plan will lead to recommendations, the implementation of which will be resource dependent meaning that there will come a time when we have done all that is possible with the resources available. For this reason, the target likelihood score is currently a 4 instead of a 3. Additional resources would allow the organisation to make significant improvements to the process by which SARs are managed. Being able to adequately comply with legal requirements reduces the likelihood of enforcement action and fines from the ICO, as well as minimising the risk of reputational damage. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - Approved SAR Policy: Provides a formal framework for consistent SAR handling. - Dedicated SAR Lead (Band 7 IG Manager): Ensures operational oversight and coordination. - Defined Governance Roles: SIRO, Caldicott Guardian, and DPO roles are in place and active. - Legal and Risk Advice: Accessed for complex SARs to ensure lawful and appropriate handling. - Escalation to Information Governance & Cyber Assurance Group (IGCAG): Enables timely intervention and oversight of emerging issues - SAR Working Group monitoring: Tracks delivery of actions and feeds into governance structures. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Implement detailed Action Plan in line with the timescales outlined within the Plan | Data Protection Officer/Head of Health Records |  | 31/03/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) - Bi-monthly reporting to DDRI: Provides regular oversight and visibility at committee level. - IGCAG oversight: Chaired by the SIRO and attended by key governance leads. - Escalation reports to Management Board and DDRI: Ensures senior leadership awareness. - Internal audit findings: Highlighted resource gaps and informed improvement planning. |  |  |  | Gaps in assurance (What additional assurances should we seek?) Internal audit report identified the requirement to invest in resources to address gap in assurance. |  |  |  |
| Additional Comments Background and Context: The Health Board faces a sustained increase in both the volume and complexity of SARs, driven by technological advancements, expanded data availability, and evolving communication practices (e.g. use of WhatsApp and non-corporate email channels). This surge has outpaced existing capacity, including that of professional and expert staff, with many requests exceeding statutory response times and lacking adequate redaction or clinical review. The fragmented nature of record-keeping—spanning paper files, multiple systems, and sensitive content— and inconsistent handling procedures across departments further complicates timely and compliant disclosures. During the 24/25 financial year, the acute SAR team processed 8,652 requests for data. This excludes other areas of SBUHB who manage their own SAR. Each SAR application may involve multiple requests for Health Care Professionals (HCPs) to approval the release of information. The 8,652 applications resulted in 9,102 requests to HCPs to approve, with an additional 4561 released without specific approval based on an ‘open consent’ given previously. Of the requests to approve, 48% (4,366) did not reply within 7 days and therefore this data was released without approval. Therefore only 35% of all SAR requests are released with full HCP oversight. The acute SAR team note that of the 8,652 requests into them, 124 were unable to be completed within the 28-day mandatory timescale. Of these 124, 104 were relating to Children and Young People (CYP) and 18 related to complex email enquiries. Whilst these figures may not appear significant in comparison to the total annual requests received, it is important to recognise that the time required to address these CYP and complex emails is considerable and places an excessive pressure on the organisation, e.g. A large email search may result in 10,000-15,000 emails, all requiring oversight and review, often taking weeks to complete for each request. During 2024/25, SBU received 10 SAR complaints from the public, an additional 3 SAR complaints from the ICO, and reported 1 SAR breach to the ICO. Progress Notes 04/12/2025: Met with Caldicott Guardian on 17/11/25 to discuss a number of actions on the Action Plan. Some actions requiring CG input have subsequently been marked as complete. 13/01/2025: Implementation of some aspects of the action plan has been on hold since September 2025 due to reduced IG staffing. 05/02/2026 - Meeting to be arranged to allow for discussion relating to feasibility of meeting dates previously suggested for implementation of SAR Action Plan. Dates and actions will need to be reviewed and amended in light of developments including implementation of new Smartbox AI tool within the Access to Health Records Team. From 1/4/26 we anticipate having a revised Action Plan for implementation. Inherent & Target risk score reviewed and refreshed. |  |  |  |  |  |  |  |

| Datix ID Number: 443 Date Opened: May 2025 |  | Date Last Reviewed: January 2026 |  | CRR Ref Number: 104 Risk Target Date: 31/03/2027 |  | Current Risk Rating 4 x 5 = 20 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovative digital solutions, research, development and innovation |  |  | SRR Ref: 3.4 | Director Lead: Matt John, Director of Digital Assuring Committee: Digital Data & Innovation Committee For information: Quality & Safety Committee |  |  |  |
| Risk: Failure to meet Tier 1 targets in Clinical Coding Completeness Because: The volume of new inpatient episodes exceeds the available clinical coding staff capacity; There are difficulties recruiting and retaining a sufficient number of trained clinical coding staff to address the gap, and clinical information is not always of sufficient quality or completeness electronically (such as DALs) to support swift coding. There is a risk that: Clinical notes for inpatient episodes will not be coded in a timely way. Resulting in: The non-achievement of the Tier 1 Welsh Government target (which is that 95% of inpatient activity should be coded within 30-days of discharge); Insufficient coded data to support effective service planning for population health needs; Inadequate data being available for mortality review/quality and safety purposes, with increased risk of failure to spot variance that are negatively impacting levels of patient care and potentially causing avoidable deaths; Negative impact on accuracy of analysis to understand how resources are being allocated and used at Health Board level and national level (programme budgeting); Delays in claiming casemix sensitive contract lines with JCC, Hywel Da and Cwm Taff (circa 70m per annum value in total) due to lack of coding data. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 5 = 20 Current: 4 x 5 = 20 Target: 4 x 3 =12 |  |  |  | Rationale for current score: C - Insufficient coding data will negatively impact service planning for population health needs and inadequate data being available for mortality review/quality and safety purposes. This could result in failures at spotting patterns of variance that are negatively impacting levels of patient care and potentially causing avoidable deaths. Clinically coded activity is also used to understand how resources are being allocated and used at Health Board level and national level (programme budgeting), and therefore a reduction in coding completeness will impact on the accuracy of this analysis. It is also used to claim casemix sensitive contract lines with JCC, Hywel Da and Cwm Taff of circa 70m per annum with lack of coding data impacting on the timeliness in making these claims. L - Tier 1 target is currently not being met on a regular basis. |  |  |  |
|  |  |  |  | Rationale for target score: C - Insufficient coding data will negatively impact service planning for population health needs and inadequate data being available for mortality review/quality and safety purposes. This could result in failures at spotting patterns of variance that are negatively impacting levels of patient care and potentially causing avoidable deaths. Clinically coded activity is also used to understand how resources are being allocated and used at Health Board level and national level (programme budgeting), and therefore a reduction in coding completeness will impact on the accuracy of this analysis. It is also used to claim casemix sensitive contract lines with JCC, Hywel Da and Cwm Taff of circa 70m per annum with lack of coding data impacting on the timeliness in making these claims. L – Increase in what can be coded electronically, unit centralisation, greater staff retention and the development of an auto-coding model will lead to increased capacity and a reduction in likelihood for targets not being met. |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| - A three-year coding modernisation plan has been approved by executive board on 26th February 2025. This plan will see the implementation of an auto-coding solution and a re-banding of the clinical coding department within existing budgets to attain Tier 1 targets by 27/28. - The coding management team assess the staffing complement on a daily basis to ensure resources are deployed in the most efficient and effective manner, in line with demand and clinical coding priorities. - There is a comprehensive training programme in place for new Trainee Coders. - The Clinical Coding Departments raise incidents when clinical information is missing from the patient’s health records and prevents the activity being coded in a timely manner. These incidents are highlighted at the Directorate Business Meetings held on a monthly basis as part of the Clinical Coding Key Performance Indicators. - Clinical coding staff performance continues to be monitored and discussed during the monthly Clinical Coding Managers Meetings, which are chaired by the Head of Health Records & Clinical Coding, and an update is also reported and presented on the Health Board Performance Scorecard. - An App has been developed by Digital Intelligence that shows any relevant data relating to a patient episode from different systems including Signal, TOMs, EPOA and DAL in one place. This will reduce the number of systems a clinical coder needs to log into. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Auto-coding Model in production with Neurology Day-Case Episodes | Head of Digital Intelligence Programmes |  | 28/02/2026 |
|  |  |  |  | Auto-coding model in production for two specialties | Head of Digital Intelligence Programmes |  | 31/03/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) - Attainment of the Tier 1 Health Board target for clinical coding completeness which relies on the timely availability and quality of the paper record and electronic sources. Coding 95% of in-patient activity within 30 days of discharge is a tier 1 Welsh Government target that is currently not being achieved regularly within SBU – with an average of circa 74% for 24/25. Performance is reported to Digital Business Meeting every 3 months, and to Digital, Data, Research & Innovations Committee via a Coding Paper. - Episodes are coded from paper and electronic sources; the ability to code from electronic sources improves the timeliness & accuracy; approximately 52,000 episodes of 150,000 episodes are coded from electronic sources currently. This is reported to Digital Business Meeting every 3 months, and to Digital, Data, Research & Innovations Committee via a Coding Paper. - An Audit has been carried out by NHS Wales Assurance and Audit Services of the Coding Department was completed in June 2024 with a result of limited assurance. In response a twelve-point action plan was developed of which one action remains which is the escalation of the coding risk to the Health Board Risk register. |  |  |  | Gaps in assurance (What additional assurances should we seek?) - Investment required supporting the delivery and operational costs of the Digital strategy. - Replacing qualified coders who have left the department with trainees reduces productivity - the only mitigation against this is an auto-coding product to increase productivity and re-banding across coding department to put staff at same bandings as NHS England and help staff retention – the investment required for this is yet to be funded. - The Quality of Discharge Summary provision and standard of clinical information available at the point of coding requires improvement to assist with prompt and accurate coding. There continues to be missing clinical information at the point of coding, preventing accurate and timely coding. - Incomplete DALs. |  |  |  |
| Additional Comments / Progress Notes Supplementary Notes: - Coding 95% of in-patient activity within 30 days of discharge is a tier 1 Welsh Government target that is currently not being achieved regularly within SBU – with an average of circa 74% for 24/25. - Contract coders and overtime have been used to achieve that 75% average which has stopped due to the current financial situation of the Health Board. - Retaining and recruiting qualified coding staff is a big challenge due to higher bandings in England and the availability of digitised record to allow home working. - 6 WTE qualified coders have been lost to English Health Boards or DHCW in the last 3 years due to higher bandings with a further 2WTE retiring. This has resulted in circa 44% of the current coding WTE being trainees/unqualified. Currently, there are 5 qualified coder vacancies (June 2025). 08/12/2025 – Auto-Coding Model date has been amended to December - currently in final testing ahead of potential go-live week commencing 8th December. 12/01/2026: Completed additional Working from Home action due to increase in electronic coding since implementation of primary procedure and diagnosis coding - coders now working from home 2 days per week with scope for an additional day with over 70% electronic coding. Neurology auto-coding model is being used by supervisors with wider rollout in January - so have moved action date to end of January.​ 10/02/2026 – Auto-coding Model due to go live in February. Action dates extended. |  |  |  |  |  |  |  |

| Datix ID Number: 3114 Date Opened: May 2025 |  | Date Last Reviewed: January 2026 |  | CRR Ref Number: 105 Target Date: 31/12/2026 |  | Current Risk Rating: 4 x 4 = 16 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is delivered in partnership with our communities in safe and appropriate settings, supported by innovative digital solutions, research, development and innovation |  |  | SRR Ref: 3.3 | Director Lead: Matt John, Director of Digital Supporting Director: Chris Morrell, EDAHPHS Assuring Committee: Digital, Data & Innovation Committee For information: Quality & Safety Committee |  |  |  |
| Risk: Significant increased cost for the replacement Pathology System LIMS If the new Laboratory Information Management (LIMS) system is not live before 31st March 2026 across all pathology disciplines then there will be significant additional cost across NHS Wales which could impact the Health Board’s financial plans in 2026/27. Costs would have to be covered to avoid pathology losing access to the current LIMS system resulting in the inability of pathology to deliver diagnostic results and blood transfusion services across all Health Board services including emergency, acute, primary and community services. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 5 x 5 = 25 Current: 4 x 4 = 16 Target: 4 x 1 = 4 |  |  |  | Rationale for current score: Consequence – Additional costs could be in region of approximately £1m for the Health Board depending on the length of delay Likelihood – probable (10-50% chance currently) – due to being off-track on project and lack of confirmed back-up plan. |  |  |  |
|  |  |  |  | Rationale for target score: Consequence as above Likelihood will be negligible if effective system / mitigations put in place in time |  |  |  |
| Controls (What is currently in place to manage the risk?) |  |  |  | Further Actions (What more are we going to do to address the risk?) |  |  |  |
| Configuring and testing the new LIMS system SBUHB is live with Cellular Pathology and were the first users of the system in Wales. For Blood Sciences, there are 218 critical defects that must be resolved and / or mitigated against before go-live; the national programme is aiming to have fixes in place by the end of February ready for Health Board testing. The current Blood Sciences go-live date in the national plan is July. The Health Board project team is supportive of the driver to complete the All Wales go-live of the Blood Sciences module by the end of June. The project team and the Blood Transfusion service remain concerned about the delivery of the Blood Transfusion module in LIMS 2.0. The national plan (first published mid-January 2026) is indicating a go-live in Q2. The plan needs to undergo further consultation with Health Boards to assure the ambitious dates being proposed are realistic and that resources can be made available to meet the Q2 go-live. Paramount to the go-live will be assurance that the system configuration supports clinical workflow and importantly, regulatory requirements. Should Blood Transfusion go-live be delayed further, SBUHB will need to continue to use the current LIMS 1.0. The supplier, Intersystems, have waived their costs until end of August but they will begin again from September onwards at £69k per month. DHCW will not be passing on any costs. Pursuing only a ‘Minimal Viable Product’ to avoid scope-creep SBUHB Pathology Services are only seeking to pursue a safe replacement system, known as a ‘Minimal Viable Product’. This is to eliminate the possibility of testing timescales being extended. Other Health Boards and Trusts report they are following the same approach. Challenging the supplier and Digital Health and Care Wales for their technical delivery The supplier is responsible for addressing any defects identified during testing. Digital Health and Care Wales (DHCW) are responsible for delivering some of the technical integrations (in addition to co-ordinating the national programme). The SBUHB Project Team, through the programme governance, challenge the supplier and DHCW to deliver on their commitments. |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Determine what additional local costs may be attracted due to extending the project from 31st December 2025 until 31st March 2026 and how these could be funded. | SBUHB Project Team |  | 28/02/2026 |
|  |  |  |  | Continue to work in collaboration with other NHS Wales organisations to challenge supplier delivery and secure go-live dates before 31st March 2026. | SBUHB Project Team |  | 31/03/2026 |
|  |  |  |  | Determine what additional local costs may be attracted due to extending the project into financial year 26/27. | Head of Digital Planning |  | 31/03/2026 |
| Assurances (How do we know if the things we are doing are having an impact?) National Programme Board SBUHB, together with all Health Boards, Trusts and the supplier belong to the national LIMS Programme Board. The Programme Board receives updates on testing activities, including metrics showing the number of outstanding system issues. It is chaired by the Executive Director of Allied Health Professions and Health Science for Aneurin Bevan University Health Board. SBUHB Project Team A Project Manager is in place to manage the SBUHB Project Team on daily basis. Operational Delivery Network LIMS 2.0 Sub-Group SBUHB work in regional partnership with Hywel Dda University Health Board (HDUHB) and hold a joint, monthly Operational Delivery Network LIMS 2.0 Sub-Group, which receives reports from the SBUHB and HDUHB Project Managers, along with Programme Managers from the supplier and Digital Health and Care Wales. This group is jointly chaired by the SBUHB Clinical Lead for Laboratory Medicine and HDUHB Head of Pathology Service, who are also Senior Responsible Officers for the SBUHB and HDUHB projects. Morriston Management Board The SBUHB project regularly reports progress to the Morriston Management Board. Digital, Data, Research and Innovation Committee The SBUHB project regularly reports progress to the Digital, Data, Research and Innovation Committee. |  |  |  | Gaps in assurance (What additional assurances should we seek?) Meeting the costs of extending the project and access to the current LIMS The national programme has been extended until 31st March 2026 at no additional cost to the Health Board. Welsh Government funded an extension to 31st December 2025 at cost of £1.6m. Digital Health and Care Wales are covering a further £0.87m of national costs until 31st March 2026. The SBUHB project needs to determine what additional local costs may be attracted due to extending the project from 31st December 2025 until 31st March 2026 and how these could be funded. The local project team received an update paper from DHCW on the 29th January showing Q1 2026/27 costs across Wales of £2.8m. Once apportioned between participating organisations in line with the national business case, this equates to £0.3m for SBUHB. The £0.3m would fund the extension of NHS hosted infrastructure, the supplier’s programme resources and national programme resources. Should Blood Transfusion go-live be delayed beyond August 2026, SBUHB will need to continue to use the current LIMS 1.0. The supplier, Intersystems, has indicated their costs would be £69k per month for the continued use of the Blood Transfusion module of LIMS 1.0 until such time the Health Board transitions to LIMS 2.0. DHCW will not be passing on any costs. Infrastructure Mitigations The project team has written to the national programme requesting a risk assessment covering: - Risks including technical, cyber, clinical and operational if Swansea Bay was to remain on LIMS 1.0 post-August 2026 (date from which infrastructure needs to be refreshed). Associated mitigations to help manage the risks whilst the programme continues to progress to work to migrate to LIMS 2.0 for Blood Transfusion. |  |  |  |
| Additional Comments / Progress Notes The current go-live schedule is tabulated below: Tranche; Discipline; Go-live date. 1; Technical deployment only; October 2025. 2; Cellular Pathology/Andrology; January 2026. Mortuary; March 2026. 3; Public Health Wales/Microbiology/Cervical Screening; May 2026. 4; Blood Sciences/Point of Care Testing/Newborn Screening; July 2026. 5; Blood Transfusion; TBC (September 2026 proposed). User Acceptance Testing sign-off User Acceptance Testing across Wales was originally expected to take place across the two months of September and October 2024. However, a significant number of issues in the system, coupled with partial delivery of integrations between the LIMS and national systems managed by Digital Health and Care Wales, were identified early in the process. Maintaining the availability of Pathology staff to undertake testing across an extended duration, alongside maintaining service delivery, has also been challenging. Blood Transfusion services in other part of Wales SBUHB Blood Transfusion are the only Blood Transfusion service in Wales that have successfully migrated onto the current LIMS system. Pathology resource for testing Testing is reliant on the knowledge and skills of Health Board staff whose availability is limited, having to manage testing alongside normal service delivery. With a national shortage of Biomedical Scientists, there is no readily available external resource to support this process. 11/11/2025 – The pathology Operational Delivery Network LIMS sub-group chair has written to the LIMS national programme chair to request that the Backup Plan and the costs estimated within it be revisited given the increasing likelihood that go lives will take place in the new financial year. 09/12/2025 - Costs shared with 9th December 2025 Programme Board show a cost after 31st March 2026 of £3.3m per quarter, with £0.4m of those costs apportioned to SBUHB. 12/01/2026: Risk score reviewed in light of the most recent financial estimates from the national LIMS team provided​​ through the national LIMS Programme Board. Risk score remains at 16 (4 Probable x 4 Major). 06/02/2026 – Risk updated ahead of Digital Services Risk Management Meeting 09/02/2026 to reflect the proposal from DHCW to extend the national programme into Q1 2026/27, which includes a cost to SBUHB £0.3m. Updated ‘Controls’, ‘Assurances’ and ‘Gaps in assurance’, including removing historical references - especially those relating to when this risk referred to the potential loss of the system instead of a financial risk. The business continuity contingency for any further slippage is to continue to use LIMS 1.0. Added target date of December 2026 to reach the target risk score based on current estimated go-lives, with national plans still being worked through: That based on those plans currently, it would be unlikely (1) that any further additional cost would be attracted beyond December 2026. |

| Datix ID Number: 4334 Date opened: December 2025 |  | Date Last Reviewed: January 2026 |  | CRR Ref Number: 108 Target Risk Date: 31/03/2029 |  | Current Risk Rating 4 x 4 = 16 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: Care is delivered in safe and appropriate settings supported by innovative digital solutions |  |  | SRR Ref: 3.4 | Director Lead: Matt John, Director of Digital Assuring Committee: Digital, Data, Research and Innovation |  |  |  |
| Risk: WCCIS/Connecting care - Provision of an Integrated Health Record for MH&LD and PCT If the Connecting Care programme fails to deliver a digital solution that meets the operational, clinical, and reporting needs of Mental Health & Learning Disabilities (MH&LD) and Community & Therapies services, Then wider MH&LD, Community and Therapies teams will lack access to timely, accurate, and shared information across care settings, resulting in fragmented service delivery, limited availability of high-quality data for performance monitoring and informed decision making, increased duplication of effort, and elevated clinical and governance risks. This includes the potential for further Regulation 28 reports, as previous Prevention of Future Deaths (PFD) notices have explicitly cited the absence of an integrated electronic system as a contributing factor to avoidable harm. Without a fit-for-purpose solution, the Health Board may be unable to fulfil the actions required under Regulation 28, particularly around effective information sharing and risk management across agencies. Whilst the issue facing current users across integrated teams from the loss of WCCIS will be largely mitigated through the approved procurement of replacement solutions through the strategic partnership with the supplier, there remains to be 3,000 users across MH&LD and PCT who continue to provide services without an appropriate digital solution to support them. The provision of a solution is a core component of the SBU Digital Strategy. A recent independent review of Mental Health and Learning Disability services at SBUHB identified the lack of a single digital solution as a critical barrier to safe and effective care, highlighting that fragmented systems and manual processes are contributing to clinical risk, delayed interventions, and repeated Regulation 28 reports due to inadequate access to shared electronic records. |  |  |  |  |  |  |  |
| Risk Rating (consequence x likelihood): Inherent: 4 x 5 = 20 Current: 4 x 4 = 16 Target: 4 x 2 = 8 |  |  |  | Rationale for current score: Likelihood – given the current trajectory of the national Connecting Care programme and its inability to provide a clear and timely roadmap for delivering a solution that meets the needs of Mental Health & Learning Disabilities (MH&LD) and Community & Therapies services. The removal of key components such as the Shared Care Record from the business case, the absence of a national Mental Health framework, and the lack of guaranteed funding all contribute to growing uncertainty. Local service groups have already escalated concerns through multiple risk registers, and the reliance on manual workarounds continues to expose wider teams to operational inefficiencies and clinical governance issues. Without urgent intervention or a credible alternative, the probability of service disruption and further Regulation 28 reports is increasingly likely. Consequence – there would continue to be a significant impact on quality of care and capacity of the MH&LD and PCT teams. The organisation would fail to address the requirements of Regulation 28 reports and there would continue to be a lack of quality data to allow performance monitoring and informed decision making on service transformation. This has a wider impact on the health service provision across the health board, including secondary care. |  |  |  |
|  |  |  |  | Rationale for target score: Likelihood – If the health board introduce a solution for the wider community and mental health teams, then it is unlikely the consequence associated with system failure or not replacing the new system will occur and some reduction in risk level may be possible. Consequence – the consequence of not having a digital solution to support integrated teams and the wider community and MHLD teams will remain the same. |  |  |  |
| Controls (What are we currently doing about the risk?) |  |  |  | Mitigating actions (What more should we do?) |  |  |  |
| - Local Program Board has been established and is responsible for producing the business case and delivery of the interim measure - Regional Program Board is in place to ensure HB and councils are working together and align implementation of solutions - DHCW National Program Board is in place to deliver national approach |  |  |  | Action | Lead |  | Deadline |
|  |  |  |  | Implement the new interim solution | Director of Digital |  | 31/08/2026 |
|  |  |  |  | Business case completed and approved for the expansion of the interim solution across all of paper based mental health teams | Director of Digital |  | Complete |
|  |  |  |  | Business case completed and approved for the provision of an Electronic Patient Record for the whole of Community and MH&LD | Director of Digital |  | 31/03/2027 |
| Assurances (How do we know if the things we are doing are having an impact?) - Digital leadership group will have oversight of the delivery of the actions of the Local Program Board and reports to Management Board - Digital, Data, Research and Innovation Committee will have oversight of the overall plan and act as escalation route to Health Board if required. |  |  |  | Gaps in assurance (What additional assurances should we seek?) - The national approach has been delayed and is difficult to influence in terms of scope and timelines for delivery - The route to obtaining national funding to support the Health Board is not clear. |  |  |  |
| Additional Comments The Welsh Community Care Information System (WCCIS) was developed to provide staff across health and social services with a single system and shared electronic record to enable delivery of more effective and efficient services. It is used by health board teams within mental health and community services, in addition to local authority social services teams, but the system will be discontinued from January 2026. SBUHB users are mainly operating within Integrated Teams and access the solution via the Swansea Council’s contract with the system provider. - A business case for an interim solution to address the immediate needs of the current SBUHB users of WCCIS (integrated teams) was presented to and approved by Management Board on 19th December 2024. - The Health Board are continuing to support the National Program in the process for acquiring a longer-term solution - The procurement of the interim solution was completed at the end of 2025/26 and project implementation has commenced. - In September 2025 WG confirmed approval of funding to DHCW of the first year costs in the National OBC. Funding is only available in 2025/26 and a proportion of the funding is available to SBUHB to support the interim solution for integrated teams and next steps. There has been no formal commitment from WG of funding in future years. 11/11/2025 - Business case for expansion of interim solution has been completed. Procurement has been approved by Director of Finance and CEO. So the 3rd action can be marked as completed. 09/12/2025- The business case contract has been awarded for the implementation of RIO in mental health and learning disabilities for 20 teams who are currently based on paper. Work has commenced on the implementation which is due to complete by 31st March 2026. 12/01/2026: The business case to expand the implementation of Rio has been approved, allowing the rollout to 20 teams within MHLD who are currently operating on paper. The contract for implementation has been awarded, and the rollout is now underway, with completion targeted for the end of March 2026. This initiative is running in parallel with the migration of the Integrated teams, who are currently using WCCIS, onto the Rio solution. The migration for these teams is scheduled to complete by October 2026. |  |  |  |  |  |  |  |

Risk Score Calculation

For each risk identified, the LIKELIHOOD & CONSEQUENCE mechanism will be utilised.  Essentially this examines each of the risks and attempts to assess the likelihood of the event occurring (PROBABILITY) and the effect it could have on the Health Board (IMPACT).  This process ensures that the Health Board will be focusing on those risks which require immediate attention rather than spending time on areas which are, relatively, a lower priority.