Appendix 1

Digital delivery: Q4 progress report

A detailed Project Delivery Dashboard for active Digital projects in FY 2025/2026 has been developed and is detailed in Table 2 below. It tracks progress and sets out the associated RAG status for Quarter 4 of FY2025/2026.

The Red Amber Green (RAG) status used within this report is set out in Table 1 below.

Table 1 – RAG Status

| Green | ON TRACK - Action progressing as planned and to agreed timelines |
| --- | --- |
| Amber | OFF TRACK - Action not progressing as planned/to original timelines, however this is manageable, and mitigating actions are in place |
| Red | OFF TRACK - Action not progressing as planned/to original timelines, there are significant issues which require escalating |

Table 2 – Digital Delivery Dashboard

| Title | RAG Status | Rationale for RAG Status |
| --- | --- | --- |
| D01 - Unscheduled and Emergency Care Solution | Amber | The Health Board have conducted engagement sessions with suppliers to assess the capabilities of their solutions in meeting the requirements in UEC. A paper was taken to the Formal Executive meeting on 11th Feb reinforcing the need for a fit for purpose digital solution across our UEC settings. The recommendation to proceed with procuring a digital system for UEC was endorsed by executives. |
| D02 - Pathology digital system replacement (LIMS 2.0) | Red | SBUHB Cellular Pathology has successfully gone live on LIMS 2.0; the first in Wales. Blood Sciences is scheduled for a July go-live, though 218 critical defects - largely within Biochemistry - remain a significant constraint. National suggestions to use external Biochemistry resource would require substantial training; additional hours from existing staff are considered more practical. Public Health Wales Microbiology is due for an all-Wales “big bang” go-live in May 2026. Concerns persist around the Blood Transfusion module, with the national plan indicating a provisional September 2026 go-live and supplier charges of £69k per month from August. Programme extension costs to SBUHB total £180k revenue and £310k capital across Q1-Q2 FY26/27. Risks remain recorded on the Health Board risk register (HBR 105 / Datix 3114, score 16). |
| D03 - Radiology digital systems replacement (RISP) | Amber | SBUHB scheduled go live has slipped from 23 February 2026 to 30 March 2026. The project is currently on schedule to deliver to this date. |
| D04 - Welsh Emergency Care Data Set (WECDS) Implementation | Red | Usability testing was conducted during November 2025 with digital and key clinical leads. A number of concerns have been flagged; the first release will not provide the write back of demographics to WPAS. This will result in duplication of effort, as users will be required to update demographic details in WPAS and the UEC app. This has led to significant concerns from clinical, operational and digital leads. UAT testing has been delayed to March 31st. A paper setting out concerns has been presented to Execs. The paper recommends the Health Board procure a 3rd party solution, subject to funding. This recommendation was approved by Execs. |
| D05 - Patient Portal/NHS App | Green |  |
| D06 - Connecting Care (Rio Implementation across Integrated Teams) | Green |  |
| D07 - Hybrid Mail | Green |  |
| D08 - Signal | Green | V4 has been deferred to Q2 FY26/27 |
| D09 - Welsh Clinical Portal - Hospital Initiated Referrals | Green |  |
| D10 - Digital Health Assessments | Green |  |
| D11 - Welsh Nursing Care Record - Paediatrics | Green |  |
| D12 - Digital Maternity Cymru | Amber | RAG remains Amber due to ongoing technical and clinical challenges that are actively being managed, including, integration testing, data migration and validation testing and system configuration. The Lead Digital Midwife is currently on unplanned leave, which is exacerbating the implementation challenges. These are being mitigated by re-evaluating the clinical assurance processes. Although SBUHB are still working towards a 31st March go live, the Health Board remain constrained by other Health Board implementations. To mitigate this SBUHB continue to work closely with the supplier, DHCW and clinical leads within maternity services. The team are also considering a phased implementation. |
| D13 - e-Prescribing & Meds Management | Amber | We continue to work with System C to review what is required to develop the integration with the SMR, with a view this will be on their roadmap for 26/27 |
| D14 - WPAS and associated services disaggregation | Green |  |
| D15 - Implement Open Eyes (Open ERS/Open EPR) | Amber | Status is now Amber. The Electronic Referral Solution "Opera" which DHCW have procured is still not available to test and configure the WGOS pathways. Testing and training cannot be undertaken until this has completed. Timescales for completion are currently unavailable. In addition, DHCW are yet to agree a rollout schedule for Health Boards. |
| D16 - Welsh Intensive Care Information System - Implementation | Green |  |
| D17 - Expand Electronic Test Requesting | Amber | Timescales elongated for a number of integrations due to: - Awaiting supplier quote for development (SpaceLabs) - New API DHCW Process to undertake - Cellma GP Letters - undergoing further testing due to letter template conversion issues. |
| D18 - Systemic Anti-Cancer Therapy (SACT) | Green |  |
| D19 - In-Touch - Go Live with 'In Touch' in Singleton Hospital | Green |  |
| D20 - Millcare System in Sexual Health | Green |  |
| D21 - WPAS Roll out across Mental Health, Learning Disabilities and Primary Care and Therapies | Green |  |
| D22- Cyber Secure Back Ups | Green |  |
| D23 - NPT wireless equipment replacement | Amber | Prioritisation of another Delivery Action with support ending soon (D29 - Call Manager Upgrade to Cloud Voice) |
| D24 - Laptop, PC, iPad and Printer Replacement | Green |  |
| D25 - Additional Server Equipment including Storage | Green |  |
| D26 - Imprivata Rollout | Green |  |
| D27 - Implement New Core Network at Morriston & Singleton | Green |  |
| D28 - Windows 10 Removal | Green |  |
| D29 - Call Manager Upgrade to Cloud Voice | Amber | The implementation had stalled in Q3 due to a lack of response from the third-party supplier (Call Recording Supplier). However, work has since resumed with the migration partner. Migration commenced in February 2026 and is now expected to be complete in Q4. |
| D31 - Creation of a measure to be visualised in Dashboard pulling data from various systems | Green |  |
| D32- Re-banding of Coding Staff and Development of Auto-coding Software | Green |  |
| D33 - Data Literacy and Value | Green |  |
| D34 - National Data Resource (NDR) | Green |  |
| D35- Health Records Centralisation | Green |  |
| D36 - Digital Cellular Pathology | Amber | The National Digital Cellular Pathology programme has recently issued a revised project timeline outlining the cost profile and confirming SBUHB’s projected recurring and non-recurring revenue commitments. It is anticipated that procurement will take place during FY26/27 with implementation in FY27/28. SBUHB have been asked to confirm whether they plan to participate and are aligned with the national position. |
| D37 - eTriage | Closed | Removed from plan for FY25/26, due to the cost of integration from e-triage to Symphony, given the Symphony contract is due to expire 1st June, 2026. |