## Actions by date
Subject Access Request (SAR) - Action Plan 2025/26
AIM: Action Plan to improve the management of Subject Access Requests across the Health Board
Short-term actions to consider improvements that can be made within the next 6 months to improve current practices, longer-term actions will consider requirements to support the modernisation/digitisation of SAR management across the Health Board
| Action | Challenge Area (colour identifies re-occurring challenges throughout the plan) | Lead(s) | Deadline | Timescale | Status Update
| Undertake GAP analysis of current Health Board practices against legislative requirements | Unknown position on how SARs are currently being processed against legislative requirements within Health Records, Workforce and OD and other services handling their own requests | Information Governance Manager | Complete | Shorter-term action aiming for rapid improvements | Task completed
| Undertake benchmarking exercise on requests for personal data (including SARs) in collaboration with NHS organisations across Wales to determine challenges, similarities and complexities in processing requests | Unknown position on how SARs are being processed by other NHS organisations, including compliance rates, centralised models and resources | Head of Health Records | Complete | Shorter-term action aiming for rapid improvements | Task completed
| Review existing processes within the Health Records Subject Access Team producing recommendations on areas for potential improvement and efficiencies | Lack of digital solutions for processes (i.e. co-ordination, retrieval, duplication removal, redaction and version release) results in considerable duplication of time and effort throughout the administration and management of the SAR process | Digital Programme Lead | 2025-05-01 | Shorter-term action aiming for immediate improvements
| Engage with the national Health Records Management Advisory Group (HRMAG) to undertake a scoping exercise across NHS Wales on what is defined as a full clinical record when requested within a SAR | Digital improvements and expansions over recent years have meant that in addition to the paper health record, clinical data is also held across extensive systems and applications both locally and nationally. There is no known definition of what constitutes a full clinical record when requested within a SAR. Similar challenges apply to the vast amounts of non-clinical personal data held electronically across the organisation. These complexities result in a lack of consistency, duplication of information, extensive searches and disclosure of incomplete records; resulting in a detrimental impact to the levels of confidence and trust that requestors have in the Health Board to safely and securely manage their personal data. | Head of Health Records | 2025-06-01 | Shorter-term action aiming for rapid improvements
| Produce a reference document outlining the legislative requirements for health record SARs outlining where a Health Professional's input is required | Health Records are either not reviewed prior to disclosure, reviews are not thorough or are partially completed or historical "open" approval is in place (resulting in a higher risk of a data breach occurring). Lack of resources, knowledge and capacity are contributing factors. Requirement for a "Health Professional" to review health records prior to disclosure to ensure no exemptions apply. Example of an exemption only applicable by a Health Professional, is where disclosure is likely to cause "serious harm" to the physical or mental health of any individual. | Information Governance Manager | 2025-06-01 | Shorter-term action aiming for immediate improvements
| Present and discuss reference document and current practices with Caldicott Guardian to inform of the required legislative requirements for health record SARs prior to wider engagement with clinicians | Health Records are either not reviewed prior to disclosure, reviews are not thorough or are partially completed or historical "open" approval is in place (resulting in a higher risk of a data breach occurring). Lack of resources, knowledge and capacity are contributing factors. Requirement for a "Health Professional" to review health records prior to disclosure to ensure no exemptions apply. Example of an exemption only applicable by a Health Professional, is where disclosure is likely to cause "serious harm" to the physical or mental health of any individual. | Deputy Executive Medical Director Information Governance Manager Head of Health Records Head of Information Governance | 2025-07-01 | Shorter-term action aiming for immediate improvements
| Following engagement at HRMAG, complete scoping exercise to determine the clinical information used to define a SAR request for an individual’s full clinical record | Digital improvements and expansions over recent years have meant that in addition to the paper health record, clinical data is also held across extensive systems and applications both locally and nationally. There is no known definition of what constitutes a full clinical record when requested within a SAR. Similar challenges apply to the vast amounts of non-clinical personal data held electronically across the organisation. These complexities result in a lack of consistency, duplication of information, extensive searches and disclosure of incomplete records; resulting in a detrimental impact to the levels of confidence and trust that requestors have in the Health Board to safely and securely manage their personal data. | Head of Health Records | 2025-08-01 | Shorter-term action aiming for rapid improvements
| Develop additional guidance and documentation for staff reminding of their responsibilities in relation to the management of SARs - publicise on IG intranet pages | No dedicated resource across the Health Board for redaction and application of exemptions for SARs. Staff often have limited knowledge and skill, with no training and have little to no capacity to undertake redaction tasks in addition to an already pressured workload. Redaction is often completed by various staff, sometimes as a one off task, resulting in poor compliance with legislative standards, no consistency in approach and poor recording keeping of redactions made and exemptions applied leaving the Health Board open to scrutiny, legal challenge and enforcement action from the ICO. | Information Governance Manager | 2025-08-01 | Shorter-term action aiming for rapid improvements
| Consult with Caldicott Guardian and clinicians within services where the "open approval" model is in place, to determine what improvements can be made to reduce the risk of data breaches within SAR disclosures | Health Records are either not reviewed prior to disclosure, reviews are not thorough or are partially completed or historical "open" approval is in place (resulting in a higher risk of a data breach occurring). Lack of resources, knowledge and capacity are contributing factors. Requirement for a "Health Professional" to review health records prior to disclosure to ensure no exemptions apply. Example of an exemption only applicable by a Health Professional, is where disclosure is likely to cause "serious harm" to the physical or mental health of any individual. | Deputy Executive Medical Director Information Governance Manager Head of Health Records Head of Information Governance | 2025-09-01 | Shorter-term action aiming for immediate improvements
| Use the definition of a full clinical record (as determined within the scoping exercise) to develop a plan to identify which clinical systems within Swansea Bay UHB will be used to collate data in response to a SAR | Digital improvements and expansions over recent years have meant that in addition to the paper health record, clinical data is also held across extensive systems and applications both locally and nationally. There is no known definition of what constitutes a full clinical record when requested within a SAR. Similar challenges apply to the vast amounts of non-clinical personal data held electronically across the organisation. These complexities result in a lack of consistency, duplication of information, extensive searches and disclosure of incomplete records; resulting in a detrimental impact to the levels of confidence and trust that requestors have in the Health Board to safely and securely manage their personal data. | Head of Health Records | 2025-09-01 | Shorter-term action aiming for immediate improvements
| Review and update the "Quick Reference Guide to Redaction" document ensuring any process changes are accurately reflected | No dedicated resource across the Health Board for redaction and application of exemptions for SARs. Staff often have limited knowledge and skill, with no training and have little to no capacity to undertake redaction tasks in addition to an already pressured workload. Redaction is often completed by various staff, sometimes as a one off task, resulting in poor compliance with legislative standards, no consistency in approach and poor record keeping of redactions made and exemptions applied leaving the Health Board open to scrutiny, legal challenge and enforcement action from the ICO. | Information Governance Manager | 2025-09-01 | Shorter-term action aiming for rapid improvements
| Develop a high level procedure for handling requests where legal time limits are exceeded or at risk of exceeding, to include a clear escalation process across all relevant parties i.e. services, SAR Team, IG Team, etc. | Lack of dedicated resources, burdensome processes and a lack of central co-ordination for all SARs across the Health Board places the organisation at increased risk of poor practices and non-compliance with SAR specific legislation and timescales. Consequences include ICO enforcement action, breach of individual's rights, compensation requests, reputation damage and loss of trust. | Information Governance Manager | 2025-09-01 | Shorter-term action aiming for rapid improvements
| Caldicott Guardian to engage with senior clinicians to ensure they are aware of their responsibilities in the timely clinical review of documentation prior to disclosure as outlined in the reference document and consider improvements and efficiencies that can be made to better support SAR processes | Health Records are either not reviewed prior to disclosure, reviews are not thorough or are partially completed or historical "open" approval is in place (resulting in a higher risk of a data breach occurring). Lack of resources, knowledge and capacity are contributing factors. Requirement for a "Health Professional" to review health records prior to disclosure to ensure no exemptions apply. Example of an exemption only applicable by a Health Professional, is where disclosure is likely to cause "serious harm" to the physical or mental health of any individual. | Deputy Executive Medical Director | 2025-09-01 | Shorter-term action aiming for immediate improvements
| Develop a specification on the proposed requirements for an electronic solution to support the processing of information requests, to include request management, documentation searches, duplication reduction, redaction tools, records management and documentation release | Lack of digital solutions for processes (i.e. co-ordination, retrieval, duplication removal, redaction and version release) results in considerable duplication of time and effort throughout the administration and management of the SAR process | Information Governance Manager Head of Health Records Head of Information Governance Digital Programme Lead | 2025-10-01 | Longer-term action aiming for SAR modernisation
| Undertake exercise to determine recent costs incurred by the Health Board in relation to information disclosures (including legal advice, claims, compensation, etc.) to better understand how future resources can be utilised | Lack of dedicated resources, burdensome processes and a lack of central co-ordination for all SARs across the Health Board places the organisation at increased risk of poor practices and non-compliance with SAR specific legislation and timescales. Consequences include ICO enforcement action, breach of individuals' rights, compensation requests, reputation damage and loss of trust. | Information Governance Manager | 2025-11-01 | Longer-term action aiming for SAR modernisation
| Develop a specification for the routine scope and search of paper and electronic data held by the Health Board when a request is received for “all data held” on an individual to limit duplication and minimise missing information | Digital improvements and expansions over recent years have meant that in addition to the paper health record, clinical data is also held across extensive systems and applications both locally and nationally. There is no known definition of what constitutes a full clinical record when requested within a SAR. Similar challenges apply to the vast amounts of non-clinical personal data held electronically across the organisation. These complexities result in a lack of consistency, duplication of information, extensive searches and disclosure of incomplete records; resulting in a detrimental impact to the levels of confidence and trust that requestors have in the Health Board to safely and securely manage their personal data. | Information Governance Manager Head of Health Records Head of Information Governance | 2025-12-01 | Longer-term action aiming for SAR modernisation
| Use completed specification to consider software, both internal and external, against the developed specification - scoping availability and potential costs and providing recommendations to IGCAG for consideration/escalation | Lack of digital solutions for processes (i.e. co-ordination, retrieval, duplication removal, redaction and version release) results in considerable duplication of time and effort throughout the administration and management of the SAR process | Information Governance Manager Head of Health Records Head of Information Governance Digital Programme Lead | 2026-01-01 | Longer-term action aiming for modernisation of SAR management
| Develop a specification on the staffing resource requirements to effectively manage the complete SAR process using a centralised model, considering joint resources required across the Subject Access Team, IG Team and other services where SARs are managed | Lack of dedicated resources, burdensome processes and a lack of central co-ordination for all SARs across the Health Board places the organisation at increased risk of poor practices and non-compliance with SAR specific legislation and timescales. Consequences include ICO enforcement action, breach of individuals' rights, compensation requests, reputation damage and loss of trust. | Information Governance Manager Head of Health Records Head of Information Governance | 2026-02-01 | Longer-term action aiming for SAR modernisation
| Develop and publicise staff bulletins to ensure staff are updated on any changes to SAR processes or policies (as and when required but by March 2026) | Lack of dedicated resources, burdensome processes and a lack of central co-ordination for all SARs across the Health Board places the organisation at increased risk of poor practices and non-compliance with SAR specific legislation and timescales. Consequences include ICO enforcement action, breach of individuals' rights, compensation requests, reputation damage and loss of trust. | Information Governance Manager | 2026-03-01 | Longer-term action aiming for modernisation of SAR management
| Develop an e-learning package (or equivalent, within available resources) to support staff when undertaking redaction | No dedicated resource across the Health Board for redaction and application of exemptions for SARs. Staff often have limited knowledge and skill, with no training and have little to no capacity to undertake redaction tasks in addition to an already pressured workload. Redaction is often completed by various staff, sometimes as a one off task, resulting in poor compliance with legislative standards, no consistency in approach and poor record keeping of redactions made and exemptions applied leaving the Health Board open to scrutiny, legal challenge and enforcement action from the ICO. | Information Governance Manager Head of Information Governance | 2026-03-01 | Longer-term action aiming for modernisation of SAR management

## Pivot by challenge
Challenge Area (colour identifies re-occurring challenges throughout the plan) | Action | Deadline
Digital improvements and expansions over recent years have meant that in addition to the paper health record, clinical data is also held across extensive systems and applications both locally and nationally. There is no known definition of what constitutes a full clinical record when requested within a SAR. Similar challenges apply to the vast amounts of non-clinical personal data held electronically across the organisation. These complexities result in a lack of consistency, duplication of information, extensive searches and disclosure of incomplete records; resulting in a detrimental impact to the levels of confidence and trust that requestors have in the Health Board to safely and securely manage their personal data. | Develop a specification for the routine scope and search of paper and electronic data held by the Health Board when a request is received for “all data held” on an individual to limit duplication and minimise missing information | 2025-12-01
| Engage with the national Health Records Management Advisory Group (HRMAG) to undertake a scoping exercise across NHS Wales on what is defined as a full clinical record when requested within a SAR | 2025-06-01
| Following engagement at HRMAG, complete scoping exercise to determine the clinical information used to define a SAR request for an individual’s full clinical record | 2025-08-01
| Use the definition of a full clinical record (as determined within the scoping exercise) to develop a plan to identify which clinical systems within Swansea Bay UHB will be used to collate data in response to a SAR | 2025-09-01
Health Records are either not reviewed prior to disclosure, reviews are not thorough or are partially completed or historical "open" approval is in place (resulting in a higher risk of a data breach occurring). Lack of resources, knowledge and capacity are contributing factors. Requirement for a "Health Professional" to review health records prior to disclosure to ensure no exemptions apply. Example of an exemption only applicable by a Health Professional, is where disclosure is likely to cause "serious harm" to the physical or mental health of any individual. | Caldicott Guardian to engage with senior clinicians to ensure they are aware of their responsibilities in the timely clinical review of documentation prior to disclosure as outlined in the reference document and consider improvements and efficiencies that can be made to better support SAR processes | 2025-09-01
| Consult with Caldicott Guardian and clinicians within services where the "open approval" model is in place, to determine what improvements can be made to reduce the risk of data breaches within SAR disclosures | 2025-09-01
| Present and discuss reference document and current practices with Caldicott Guardian to inform of the required legislative requirements for health record SARs prior to wider engagement clinicians | 2025-07-01
| Produce a reference document outlining the legislative requirements for health record SARs outlining where a Health Professional's input is required | 2025-06-01
Lack of dedicated resources, burdensome processes and a lack of central co-ordination for all SARs across the Health Board places the organisation at increased risk of poor practices and non-compliance with SAR specific legislation and timescales. Consequences include ICO enforcement action, breach of individual's rights, compensation requests, reputation damage and loss of trust. | Develop a high level procedure for handling requests where legal time limits are exceeded or at risk of exceeding, to include a clear escalation process across all relevant parties i.e. services, SAR Team, IG Team, etc. | 2025-09-01
| Develop a specification on the staffing resource requirements to effectively manage the complete SAR process using a centralised model, considering joint resources required across the Subject Access Team, IG Team and other services where SARs are managed | 2026-02-01
| Develop and publicise staff bulletins to ensure staff are updated on any changes to SAR processes or policies (as and when required but by March 2025) | 2026-03-01
| Undertake exercise to determine recent costs incurred by the Health Board in relation to information disclosures (including legal advice, claims, compensation, etc.) to better understand how future resources can be utilised | 2025-11-01
Lack of digital solutions for processes (i.e. co-ordination, retrieval, duplication removal, redaction and version release) results in considerable duplication of time and effort throughout the administration and management of the SAR process | Develop a specification on the proposed requirements for an electronic solution to support the processing of information requests, to include request management, documentation searches, duplication reduction, redaction tools, records management and documentation release | 2025-10-01
| Review existing processes within the Health Record's Subject Access Team producing recommendations on areas for potential improvement and efficiencies | 2025-05-01
| Use completed specification to consider software, both internal and external, against the developed specification - scoping availability and potential costs and providing recommendations to IGCAG for consideration/escalation | 2026-01-01
No dedicated resource across the Health Board for redaction and application of exemptions for SARs. Staff often have limited knowledge and skill, with no training and have little to no capacity to undertake redaction tasks in addition to an already pressured workload. Redaction is often completed by various staff, sometimes as a one off task, resulting in poor compliance with legislative standards, no consistency in approach and poor recording keeping of redactions made and exemptions applied leaving the Health Board open to scrutiny, legal challenge and enforcement action from the ICO. | Develop additional guidance and documentation for staff reminding of their responsibilities in relation to the management of SARs - publicise on IG intranet pages | 2025-08-01
| Develop an e-learning package (or equivalent, within available resources) to support staff when undertaking redaction | 2026-03-01
| Review and update the "Quick Reference Guide to Redaction" document ensuring any process changes are accurately reflected | 2025-09-01
Unknown position on how SARs are being processed by other NHS organisations, including compliance rates, centralised models and resources | Undertake benchmarking exercise on requests for personal data (including SARs) in collaboration with NHS organisations across Wales to determine challenges, similarities and complexities in processing requests | Complete
Unknown position on how SARs are currently being processed against legislative requirements within Health Records, Workforce and OD and other services handling their own requests | Undertake GAP analysis of current Health Board practices against legislative requirements | Complete
(blank) | (blank) | (blank)
Grand Total