| Meeting Date | 13 May 2025 |  | Agenda Item |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Records Management- Non acute records |  |  |  |  |  |
| Report Author | Jennifer Nagle, Head of Health Records |  |  |  |  |  |
| Report Sponsor | Matthew John, Director of Digital |  |  |  |  |  |
| Presented by | Jennifer Nagle, Head of Health Records |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | This report provides an update on the six management actions identified as part of a limited assurance internal audit on the Records Management (non-acute Health) report published in November 2024. |  |  |  |  |  |
| Key Issues | The paper focuses on the six recommended actions received following the internal audit and provides an update on the outstanding actions and actions completed to date. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to receive the report for assurance |  |  |  |  |  |

Records Management- Non- Acute Record

- INTRODUCTION

This report provides an update of the six management actions identified as part of a limited assurance internal audit on records management within the non-acute SBUHB areas which was published in November 2024.

- BACKGROUND

There are a large number of Services who manage and store patients’ information/records outside of the Acute Health Records Service. This approach has led to services storing their records in a number of different areas both within the SBUHB Estate including Unit 22 and off-site third-party storage areas.

Since the embargo that came into place in 2019 on the non-destruction of records as a result of the Infected Blood Inquiry, SBUHB Departments and Services have continued to struggle to cope with storing hundreds of thousands of additional records longer than previously would have legally been required.

This situation has led to increased storage pressures on services to manage all of these additional records and when any available Health Board has been exhausted, then third-party suppliers have been sourced at considerable cost to SBUHB.

In 2024, the embargo on the non-destruction of records was lifted, with caveats in place that any patient’s records/information previously provided to the Inquiry had to be retained indefinitely. However, there are considerable backlogs in the destruction of records across the Health Board due to the length of time the embargo had been in place.

The Internal audit report recognised that there were discrepancies in how records were being managed due to policies being acute records focused and that records were being retained longer than now legally required.

The high-level key issues that required management action were:

- Establishing a Multi-Disciplinary Project Group which would review the Health Board’ wide storage requirements and would encompass all the associated security/retention and disposal of records aspects highlighted within the audit report

- The guidance in place for records management should be expanded to include the non- acute health record and corporate records. With enhanced detail over the full records lifecycle.

- The arrangements for storage of records other than Pathology at Transmedia should be formalised with a contract or agreement that clearly states the requirements and responsibilities for records storage.

Within these areas, 6 key recommendations were made.

1.1 SBUHB has produced records management guidance for Health Records in the form of the Health Records Policy, the Health Records Storage and Security Policy and the Health Records Tracking Policy. However, we note that these are more directly applicable to the acute health record, and do not contain information covering all aspects, such as record retention and destruction process.

3.1 Due to the lack of coordinated management for storage of records, there are a number of external providers holding health board records. The costs vary between the providers as such the health board may not be sourcing the best value storage.

3.2 SBUHB utilises Transmedia for external record storage from multiple departments, including Workforce. However, our review noted that the only contract in place with Transmedia is for the storage of Pathology materials. Spend with the company is more than double than the contracted value, which may leave SBUHB open to legal challenge. We also note that the lack of a formal contract for storage other than Pathology items introduces uncertainty regarding Transmedia’ s responsibilities in managing personal records, raising potential GDPR compliance concerns.

4.1 Our review of the transportation of records for all of the areas noted that records are being sent via internal mail, within private vehicles and in unsealed containers. As such the transportation of records may not meet the requirement of the Health Records Storage and Security Policy and good practice.

5.1 and 5.2  During the review, it became evident that some departments are retaining records beyond the designated retention periods partly due to the lack of health board guidance. The Occupational Therapy department has not destroyed any records since 2019 and continues to retain records dating back to 2010. Similarly, the Workforce and Organisational Development (WOD) team has also refrained from destroying records. The retention of records past defined removal dates may result in a breach of the GDPR requirements and exacerbates storage pressures.

5.1 has been completed and SBUHB intranet has re-published the guidance on the lifting of the embargo on the non- destruction of records.

Of the remaining 5 actions, 4 actions are being addressed and one remains outstanding.

  - The Health Records Policies have been updated to be less “acute record” specific. The updated Polices have been circulated across SBUHB for comments, including the key leads that were part of the records management audit on the non-acute record and to members of the Information Governance and Cyber Assurance Group (IGCAG). The Policies have been included as part of the papers for further comments from the Committee Members.

3.1, 4.1, and 5.2c. The first Project group met in April 2025 and had representation from the majority of services audited as part of the records management audit on the non-acute record. Separate meetings have now been arranged with other leads that were nominated as part of the Project Group. An action plan is currently being developed and will be presented to the next meeting.

A scoping exercise will also be initiated across SBUHB by the Head of Health Records to document any storage pressures/risks including all third- party storage areas. Documented processes are already being developed to capture this information digitally with forms being created, which will be distributed across the organisation for all records including corporate records.

3.2 The Second Project Group has yet to meet due to the difficulties experienced to date on identifying all SBUHB service users that store records or information in Transmedia. Contact has been made with Transmedia directly to obtain this information but to date has still not been received. A list has now been provided from Finance colleagues which is being worked through so that the project group can be established as a matter of urgency.

As part of the centralisation of the acute health records service to Ty Samlet and the records previously being stored at Morriston being re-located, the Health Records Service has been able to ring fence the space previously occupied in the “Undercroft” which is a shared facility, which could be re-purposed for storing other records.

Until we can ascertain the number of records stored in Transmedia, then we cannot be certain if this space could house the records currently stored in Transmedia; if it is determined that these records pose a greater risk than any other records stored across SBUHB. The health records department in Morriston has now been fully emptied and all records have been relocated.

GOVERNANCE AND RISK ISSUES

- Information Governance and Cyber Assurance Group (IGCAG)

- It should be acknowledged that a breach of United Kingdom General Data Protection Regulations (UK-GDPR) is a potential risk by retaining records passed their legal threshold. Over-collation of data not only burdens systems but also creates a larger target for cybercriminals. UK-GDPR regulations stipulate that personal information should only be retained for as long as the original consent / approval was provided for.

FINANCIAL IMPLICATIONS

Potential Savings

- Through the work of the Project Groups, efficiencies could be realised through the review of the volume of records stored with third party suppliers at a considerable cost and returned to SBUHB for storage. From historical data for the 24/25 financial year, initial scoping from finance subjective codes that circa £200k is spent with third party storage providers across the organisation.  As a priority, capacity needs to be identified and highlighted to SBUHB following the centralisation of all active acute records from NPT, Morriston and Singleton to the centralised Unit in Ty Samlet of any available storage.

- Progress has already been made with the planned cessation of the lease in Unit 22. Records that are required to be retained that do not meet the legal threshold for destruction have been identified for storage in NPT once the move to the centralised Unit is completed. The savings of circa £50k per annum has already been realised against the medical records centralisation unit project.

- Current contract arrangements with Transmedia mean that costs with the company are more than double the contracted value. Work continues with NWSSP and the third party to fully understand the scale. Initial scoping demonstrates an expenditure of circa £15k per annum with Transmedia alone, however it is not clear at this point exactly which service groups within SBUHB are utilising their services.

- RECOMMENDATION

The Committee is asked to consider the progress made against the Records Management (non-acute) Internal Audit.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (Please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High-Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |  |
| (Please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |  |
| The unavailability of patient’s records can compromise patient care and lead to complaints and negative publicity to the Health Board. |  |  |  |
| Financial Implications |  |  |  |
| Claims for redress and fines by the ICO |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| Breach in UK GDPR |  |  |  |
| Staffing Implications |  |  |  |
| Staff resources required to accelerate the destruction programme across the Health Board |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| Report History |  | This paper is in response to the Internal Audit report on Records Management-Non acute. |  |
| Appendices |  | None |  |