| Meeting Date | Tuesday 13 May 2025 |  | Agenda Item |  |  | 3.3 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Digital Data Research and Innovation Committee |  |  |  |  |  |
| Report Title | Business Intelligence and Analytics |  |  |  |  |  |
| Report Author | Lee Morgan, Assistant Director of Digital Intelligence |  |  |  |  |  |
| Report Sponsor | Matt John, Director of Digital |  |  |  |  |  |
| Presented by | Lee Morgan, Assistant Director of Digital Intelligence |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | To provide an update on Business Intelligence and Analytics within Swansea Bay University Health Board |  |  |  |  |  |
| Key Issues | The paper outlines updates on key Business Intelligence deliverables against the work plan since the last committee report in March 2025. These include: - Digital Intelligence Strategic Plan - Weekly Health Board Summary Report - Maternity Application - Artificial Intelligence - Mental Health and Learning Disabilities Application - Data Literacy Delivery |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to receive the contents of the report and the current and future work plans described within it. |  |  |  |  |  |

Business Intelligence and Analytics

- INTRODUCTION

This Business Intelligence and Analytics update report is to provide assurance to the committee on the work being carried out by the Digital Intelligence team and update on the work plan.

- BACKGROUND

Since the last update report on 11th March 2025 work has continued with the Digital Intelligence Strategic Plan and ensuring alignment with the wider Digital Strategy. The Strategic plan was taken to the Swansea Bay Business Intelligence Collaborative on the 25th March 2025, which meets every three months as part of our Business Intelligence governance process to prioritise key projects, and it is anticipated that this will be presented to Management Board and to the Digital Data Research and Intelligence Committee in Quarter 2 of this financial year. Discovery work as part of the National Data Resource Programme has also continued with the migration of the Community Dataset to the National Google Cloud platform. This dataset will be used to support the ongoing development of analytical and artificial intelligence tools available within the platform.

The Weekly Health Board Summary Report has been launched and is automatically sent to executives on Monday mornings via email, outlining key measures across Urgent and Emergency Care, Inpatients, Maternity, Mortality and Planned Care. There is also a corresponding Power BI dashboard that is automatically updated as part of this process. This report will become a mainstay in the circulation of information to the executive team. Development has commenced on using Artificial Intelligence (AI) tools to generate an automated executive summary of the report that would highlight key trends and causations across the measures and compare with historical data from the same period. This same concept of using generative AI to produce automated analysis will then be used across other dashboards and reports. (Appendix A, Fig 1 – Fig 3).

The new Maternity Application went live in April 2025 to support the monitoring of maternity performance. The dashboard includes measures such as C-section and still birth rates. Development has continued on the Neonatal dashboard which will be included within the Maternity application when it is launched in Quarter 2. The Neonatal dashboard will include priority operational, infection prevention control and quality indicators developed with the service. (Appendix A, Fig 4).

A suite of outpatient reports have been added to the Mental Health and Learning Disabilities Application – these include referrals, outpatient activity and self-service functionality to enable users to create their own Statistical Process Control (SPC) and Pareto charts. The reports will enable quicker and enhanced access to this data which previously had to be requested on an ad-hoc basis from the Mental Health Information Service. The data will be used to help support decision making across the service. (Appendix A, Fig 5).

Data Literacy courses have continued to be held with staff across the Health Board. Since the last update report, three “Introduction to Data Literacy” and two “Introduction to Power BI” training courses have taken place with over 50 staff members attending.

- GOVERNANCE AND RISK ISSUES

The Swansea Bay Business Intelligence Collaborative met in March with various stakeholders from service areas attending and given the opportunity to review and feed into the Digital Intelligence Strategic Plan with all appropriate comments reflected in the latest draft of the plan.

There is a risk on the Health Board Risk register scored at a 12 titled: Operational and strategic decisions are not data informed and this risk continues to be monitored. Significant work has gone into the Data Literacy programme over the last 12 months to address elements of this risk. This has supported the reduction of the score for this risk.

- FINANCIAL IMPLICATIONS

There are no known financial implications in this report.

- RECOMMENDATION

Members are asked to receive the contents of the report and the current and future work plans described within it.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Not applicable. |  |  |  |
| Financial Implications |  |  |  |
| Not applicable. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| Not applicable. |  |  |  |
| Staffing Implications |  |  |  |
| Across Digital Intelligence there are currently three vacancies impacted by the current recruitment freeze within the Health Board. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| Not applicable. |  |  |  |
| Report History |  | 11th March 2025 |  |
| Appendices |  | Appendix A – BI Product Screenshots |  |