| Meeting Date | 07 November 2024 |  | Agenda Item |  |  | 4.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Report Title | Update on strategy development: Digitally Enabling the One Bay Way |  |  |  |  |  |
| Report Author | Gareth Westlake, Assistant Director of Digital |  |  |  |  |  |
| Report Sponsor | Matthew John, Director of Digital |  |  |  |  |  |
| Presented by | Matthew John, Director of Digital |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | This paper presents an update on the development of the Swansea Bay University Health Board (SBUHB) Digital Strategy: Digitally Enabling the One Bay Way, for approval. |  |  |  |  |  |
| Key Issues | - The strategy sets out the Health Board’s vision, principles, enablers and programmes for the expansion of the use of digital, data and technology to support Service Transformation across the Health Board - The strategy describes the benefits, risks, issues and financial implications of the digital way forward. - The strategy will build on the strong digital foundations already established within the organisation - The strategy highlights the significant organisational wide change in culture, workforce development and business change that will be required to achieve the vision - The strategy has been endorsed by Management Board and the Workforce, Organisational Development and Digital Committee (WODD) in August 2024. Due to the investment required to deliver the strategy and financial position of the Health Board, submission to the Health Board for final approval has been paused to further develop the narrative on the benefits that can be realised. |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☒ |  | ☒ | ☐ |  |
| Recommendations | The Committee Members are asked to: - Note: the aspirations of the digital strategy: Digitally Enabling the One Bay Way. - Note: the requirement to demonstrate the financial benefits Digitally Enabling the One Bay Way can deliver and to further the enhance the narrative of the strategy to illustrate the difference it will make to patients and clinicians. - Note: the intention to establish a multidisciplinary task and finish group to: validate the 3 top priorities for delivery within the first 3 years; establish a value model and quantify the financial efficiencies of the priorities; and enhance the narrative for the 3 priorities to demonstrate the impact on cost, quality and experience for patients and clinicians |  |  |  |  |  |

Digitally Enabling the One Bay Way

- INTRODUCTION

This paper provides an update on the progress with the development of the Swansea Bay University Health Board (SBUHB) Digital Strategy: Digitally Enabling the One Bay Way.

- BACKGROUND

Work on the development of Digitally Enabling the One Bay commenced in December 2023 and is the result of: -

- extensive engagement and consultation with our staff, patients, partners and stakeholders

- a comprehensive review of the current digital landscape, the emerging trends and challenges, and the best practices from other health systems

- the Digital maturity assessment undertaken in 2023 by the Healthcare Information and Management Systems Society (HIMSS) across all Welsh Health Boards

The strategy builds on the strong digital foundations that SBU has established over the past years but recognises the need for further advances in the way we use digital, data and technology to enable service-led transformation and deliver tangible benefits to our patients, population and workforce.

The strategy highlights the significant organisational wide change in culture, workforce development and business change that will be required to achieve the vision.

The strategy aims to support SBU achieve its goal to be seen as a high-quality organisation and establish itself as a UK exempla for digital, data and technology innovation in health and care.

The strategy is aligned with the national, regional and local policies and strategies, such as the Digital and Data Strategy for Health and Social Care in Wales, the Digital Strategy for Wales, the One Bay Way, and the Population Health Strategy.

The final draft of Digitally Enabling the One Bay Way was presented to the Management Board and WODD Committee in June 2024 for final comment.  Following feedback from these forums and further discussions with individual Executives and Non-Executive members the strategy was strengthened to include greater emphasis on the realisable benefits, the organisational wide approach to benefits management required and contextualise the impact financial constraints may have on the pace of change.

The strategy was resubmitted to WODD and Management Board in August 2024 and was endorsed for approval. The endorsed version of the strategy can be found in Appendix 1. Following the endorsement of the strategy it was recognised that given, the value of the investment required to delivery the strategy, that there was a further requirement to demonstrate the financial benefits the digital strategy can deliver and to further the enhance the narrative of the strategy to illustrate the difference it will make to patients and clinicians.

It is therefore recommended that a multidisciplinary task and finish group, including representation from digital, finance, clinical and service leads, be established to: -

- validate the 3 top priorities for delivery within the first 3 years of the strategy

- outline the quality and safety benefits that these priorities will deliver, including the mitigation of health board risks

- develop a value model to facilitate the quantification the potential financial benefits of each of the priorities. The value model should be reusable so that it can be utilised to assess future digital and non-digital investment proposals going forward

- validate the costs of the 3 priorities that have been included in the strategy

- develop a narrative for the 3 priorities that describes the cost versus benefits of delivery of the transformation including financial efficiency, the impact they have on the quality of care and on patient and clinician experience.

- GOVERNANCE AND RISK ISSUES

The strategy has followed the below review and approval process:

| Governance Meeting | Requirement | Date | Status |
| --- | --- | --- | --- |
| Digital Leadership Group | Discussion and refinement | 13/06/2024 | Complete |
| Management Board | Presentation and final comments | 19/06/2024 | Complete |
| WODD Committee | Presentation and final comments | 20/06/2024 | Complete |
| WODD Committee | Assurance | 15/08/2024 | Complete |
| Management Board | Recommendation for Board approval | 21/08/2024 | Complete |
| Health Board | Approval | 26/09/2024 | Submission date TBC |

The new Digital, Data, Research and Innovation Committee will from now on become the sub-committee of the Board which has ownership and oversight of the strategy from approval through to execution.

Following approval there will be a period of mobilisation of the strategy to establish the building blocks required for its delivery. The mobilisation period will be in tandem with the Health Board’s IMTP process to ensure it aligns to delivery and investment objectives for 2025-2028. A mobilisation plan and 3 year delivery plan have been developed to support the execution of the strategy.  The current delivery plan is attached at Appendix 2, however it is recognised that this will need to be reviewed to ensure it aligns to the outcome of the work proposed to enhance the strategy.

The delivery of the Strategy will need to be governed by a clear and robust governance structure, which will ensure accountability, oversight and alignment across the health board and with our partners. The governance arrangements will need to reflect the Health Board wide ownership of Digitally Enabling the One Bay Way and will be finalised and agreed as part of the mobilisation process.

The Strategy will also be subject to regular review and evaluation, using a range of qualitative and quantitative measures and indicators, to ensure that the strategy is delivering the expected benefits, outcomes and impacts, and to identify and address any issues, risks or gaps.

The Strategy will inevitably face some challenges and risks, which will need to be proactively managed and mitigated. Some of the key risks and issues include:

- The availability and affordability of the required resources, such as staff, skills, equipment, infrastructure and funding, to deliver the digital strategy and sustain the digital solutions.

- The alignment and integration of the digital solutions with the existing and emerging national, regional and local policies, standards, systems and programmes, to ensure consistency, interoperability and compliance.

- The engagement and adoption of the digital solutions by the end-users, such as patients, staff and partners, to ensure that they are aware, informed, trained, supported and motivated to use the digital tools and services.

- The protection and security of the data and systems from any unauthorised access, cyberattack, breach or loss, to ensure the confidentiality, integrity and availability of the information and services.

- The management and resolution of any technical, operational or clinical issues or incidents that may arise during the implementation or operation of the digital solutions, to ensure the continuity and quality of the service and care.

- FINANCIAL IMPLICATIONS

The SBU Digital Strategy to 2035 will require a significant investment in digital, data and technology over the next 10 years, which will need to be carefully planned, prioritised and justified. The investment will cover the costs of developing, implementing, operating and maintaining the digital solutions, as well as the costs of decommissioning, replacing or upgrading the existing or legacy systems. The investment will also include the costs of the staff, skills, equipment, infrastructure and support required to deliver the digital strategy. This includes the resources required to deliver change across the organisation.

In 2024/25 an additional £2.5m was provided recurrently, increasing the anticipated spend on Digital, for both capital and revenue, to £26m. This investment has increased the proportion of spend on Digital solutions to 2.3% of HB budgeted income at the start of 24/25. Digital experts suggest that allocating 5-10% of total Health Board income to digital and data is the benchmark for achieving Digital Transformation and reaching HIMSS Stage 7.

As part of the strategy development a detailed costing model was developed setting out the investment requirements. A summary of the indicative cost is shown in the below graph.

The graph shows a rapid acceleration of investment required in digital transformation, from £23 million to £54 million per annum over the next 10 years, although it should be noted that it is estimated that approximately half of this additional investment would be required to keep existing digital solutions and infrastructure operational. (As digital solutions/contracts and infrastructure become obsolete they will need to be replaced). This represents an increase from 2.3% of the total Health Board budget to 4.6%.

Prioritisation within the first 3 years focuses on achieving maximum efficiencies and establishing the building blocks for enabling transformational change. This prioritisation will need to be validated as part of the work by the multidisciplinary task and finish group outlined above.

Benefits realisation and change management are key to the delivery of Digitally Enabling the One Bay Way and an organisation wide approach to the benefits identification and management from transformational activities will need to be developed and embedded into organisational culture.

The task and finish group’s work to develop a value model to assess the financial benefits of the 3 priorities for delivery will be a key aspect of this organisational wide approach to benefits and benefits realisation.

In the Kings Fund briefing: A digital NHS? An introduction to the digital agenda and plans for implementation in 2016 it was highlighted that McKinsey estimated that the digital transformation of Health organisations can save between 7% and 11.5% of their health expenditure. The briefing also acknowledged that the change process for digital transformation is complex and that it will take time to realise the benefits.

- RECOMMENDATION

The Committee Members are asked to:

- Note: the aspirations of the digital strategy: Digitally Enabling the One Bay Way.

- Note: the requirement to demonstrate the financial benefits Digitally Enabling the One Bay Way can deliver and to further the enhance the narrative of the strategy to illustrate the difference it will make to patients and clinicians.

- Note: the intention to establish a multidisciplinary task and finish group to: validate the 3 top priorities for delivery within the first 3 years; establish a value model and quantify the financial efficiencies of the priorities; and enhance the narrative for the 3 priorities to demonstrate the impact on cost, quality and experience for patients and clinicians

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☒ |
|  | Co-Production and Health Literacy |  | ☒ |
|  | Digitally Enabled Health and Wellbeing |  | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| The strategy will enable us to provide better care to our citizens, which is safer, higher quality and timelier, leading to better outcomes, delivering better value and improving efficiency. Digital and data solutions enhance services for patients, reduce unwarranted variation and positively transform care delivery. Our strategy empowers patients to play an active and meaningful role in managing their health and keeping well |  |  |  |
| Financial Implications |  |  |  |
| As outlined above there will need to be a significant investment to Digitally Enable the One Bay way. The delivery of the strategy will facilitate the achievement of both efficiency and quality benefits that the Health Board will need to ensure that are quantified and recognised appropriately. The approval of the strategy will not commit the Health Board to any financial allocations. Funding requirements will be identified via the IMTP process and sought via local and national business cases as appropriate. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| There are no known legal implications. |  |  |  |
| Staffing Implications |  |  |  |
| The strategy identifies that one of the core pillars to enable its delivery is the Workforce and Culture of the organisation. The strategy states that we will cultivate a digitally inclusive culture, where we work collaboratively with patients, clinicians and non-clinical colleagues to create effective and efficient services. It recognises the requirement to ensure that there is the appropriate digital training and literacy for the whole workforce and is aligned to the SBU workforce Strategy. It also appreciates the need to develop a supporting workforce strategy/plan specifically for digital services to ensure the Health Board’s specialist digital staff (both clinical and technical) have the capacity and capability to support the delivery of the objectives of the strategy. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The strategy is wholly aligned to the 5 ways of working outline in the Well-being of Future Generations (Wales) Act. The focus of the strategy is how the use of digital technologies can enable the Health Boad to become a high quality organisation, improving long term outcomes, increasing clinical capacity and empowering our population to contribute to their care and health and well being. It will facilitate the use of data and information to drive decision making in the organisation including supporting targeted preventative interventions and actions on an individual and wider population basis. It will support improvements in the integration of our services will other public bodies through the sharing of information safely and securely, and support us to work collaboratively within the Health Board and our external stakeholders. The strategy also supports the Health Boards long term goal of sustainable health and care by reducing waste, reliance on paper, reducing travel etc. |  |  |  |
| Report History |  | Strategy: Digitally Enabling the One Bay Way final draft presented to Committee in June 2024 for final comment Strategy: Digitally Enabling the One Bay Way final version presented to WODD on 15th August 2024 for endorsement for approval Strategy: Digitally Enabling the One Bay Way final version presented to Management Board on 21st August 2024 for endorsement for approval |  |
| Appendices |  | Appendix 1 Digital Strategy: -Digitally Enabling the One Bay Way Appendix 2 : 3 year delivery plan |  |