| Meeting Date | 13 November 2025 |  | Agenda Item |  |  | 2.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Digital, Data, Research & Innovations Committee |  |  |  |  |  |
| Report Title | Risk Management Report |  |  |  |  |  |
| Report Author | Neil Thomas, Assistant Head of Risk & Assurance |  |  |  |  |  |
| Report Sponsor | Hazel Lloyd, Interim Director of Corporate Governance |  |  |  |  |  |
| Presented by | Hazel Lloyd, Interim Director of Corporate Governance |  |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |  |
| Purpose of the Report | The purpose of this report is to inform the Digital, Data, Research & Innovation Committee (DDRIC) of the risks within the Health Board Risk Register (HBRR) assigned to the Committee for scrutiny. |  |  |  |  |  |
| Key Issues | - The Committee last received the HBRR at its July 2025 meeting. - Since then, risks have been subject to update by Executive Directors on a monthly basis. This report presents an extract of risks allocated to the DDRIC from the September 2025 HBRR. - There are five risks overseen by DDRIC in open session (additional sensitive risks are reported in closed session). |  |  |  |  |  |
| Specific Action Required (please choose one only) | Information | Discussion |  | Assurance | Approval |  |
|  | ☐ | ☐ |  | ☒ | ☐ |  |
| Recommendations | Members are asked to: - RECEIVE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Committee. - REVIEW the risk(s) and consider whether further action / assurance is required. |  |  |  |  |  |

RISK MANAGEMENT REPORT

DIGITAL, DATA, RESEARCH & INNOVATION COMMITTEE

- INTRODUCTION

The purpose of this report is to inform the Digital, Data, Research & Innovation Committee (DDRIC) of the risks within the Health Board Risk Register (HBRR) assigned to the Committee for scrutiny.

- BACKGROUND

2.1 Risk Management Framework

The Audit Committee is responsible for reviewing the establishment and maintenance of an effective system of risk management and providing assurance to the Board in that respect. While this is the case, individual risks have been assigned to other Board committees for more detailed scrutiny and assurance.  The intention is that committee work programmes are aligned so that progress made to address key risks is reviewed in depth.  Regular risk update reports are submitted to the Board and the committees of the Board to support this.

Executive Directors are responsible for managing risk within their area of responsibility.  The Management Board, chaired by the Chief Executive, oversees the overall operation of the risk management framework and the management of risks within the health board risk register.

As part of the resetting of health board risk management arrangements a new Risk Management Group had its inaugural meeting in April 2025. The Group is chaired by the Deputy Chief Executive and reports to the Management Board. It meets monthly and its role includes oversight of the risks within risk registers, and of the escalation and de-escalation of risks between them. The last meeting of the group was in August 2025. In September, Service Groups were asked by Executive Directors to review risks within their operational registers scoring 15 and above. The November meeting of the RMG will be a gateway review meeting at which these risks will be reviewed with Service Group Directors, to inform improved reporting of operational service risks to Committees and Board level, and links to the board-level strategic and corporate risk registers.

2.2 Risk Appetite

The Health Board approved a risk appetite statement in November 2022, setting out the level of risk the Board is prepared to accept in pursuit of its objectives, according to the categorization of risk.  In the context of the financial challenges facing the Health Board, the risk appetite adopted for most risk categories is described as ‘seeking’, indicating that risks assessed to be at or above a risk level of 20 will be overseen by the committees of the Board as a minimum on a quarterly basis. However, for the category of compliance risks where the risk relates to laws, regulations and standards directing the delivery of safe, high-quality care, or the health and safety of the staff and public, an ‘open’ appetite will be adopted, indicating lower threshold and requiring risks scoring 16 or above to be overseen at committee level.

2.3 Health Board Risk Register (HBRR)

The Health Board Risk Register (HBRR) is intended to summarise the greatest organisational risks facing the Health Board and the actions being taken to mitigate them.

Each Health Board risk has a lead Executive Director who is responsible for ensuring there are mechanisms in place for identifying, managing and alerting the Board to significant risks within their areas of responsibility through regular, timely and accurate reports to the Management Board/Executive Team, relevant Board Committees and the Board.

- GOVERNANCE AND RISK ISSUES

3.1	Action to update the Health Board Risk Register (HBRR)

Health Board risk register entries are circulated to lead Executive Directors monthly for review and updated where required. A consolidated, updated register is circulated to the Executive Team for agreement and final version issued. This report presents the position as recorded within the September 2025 HBRR. Key changes made in the most recent update are highlighted in red font.

3.2	Digital, Data, Research & Innovations Committee Risks

Six risks are assigned to this Committee for oversight (See Appendix 1 for full detail). The profile of risk scores is presented below:

| Risk Score | 12 & below | 15 | 16 | 20 | 25 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Risk numbers (Jul 25) | 1 | 0 | 2 | 3 | 0 | 6 |
| Risk numbers (Nov 25) | 0 | 0 | 3 | 3 | 0 | 6 |

Key movements are:

| New Risks | HBR105 Significant increased cost for the replacement Pathology System LIMS (Transferred from Q&S Committee) |
| --- | --- |
| Scores Increased | Nil |
| Scores Reduced | Nil |
| Risks De-escalated | HBR37 Operational and strategic decisions are not data informed (de-escalated: score 12) |

Five risks are received in open session (See Appendix 1 for full details):

- HBR 27	Digital Transformation to Deliver Sustainable Services

- HBR 36	Electronic Patient Record (Paper Record Storage)

- HBR 90	GDPR Subject Access Requests

- HBR 104	Failure to meet Tier 1 Targets in Clinical Coding Completeness

- HBR 105	Significant increased cost for the replacement Pathology System LIMS

In addition, the following risk is deemed sensitive and will be overseen in closed session:

- HBR 60	Cyber Security

There are three risks currently meeting or exceeding the Health Board’s risk appetite thresholds, for which action is required so that they may be reduced to acceptable levels. Table 1 below highlights recent changes / actions of note for those risks that are currently meeting or exceeding the thresholds:

Table 1 – HBRR High Risks Assigned to the DDRIC

| Risk Ref | Risk Title (See HBRR for description) | Current Score | Executive Lead & Key Actions |
| --- | --- | --- | --- |
| HBR 60 | Cyber Security and Resilience | 20 | Lead: Director of Digital The full HBRR entry is presented in closed session of the Committee for scrutiny and assurance. |
| HBR 90 | Subject Access Request Risk | 20 | Lead: Director of Digital This risk score remains the same. However, the register entry has been reviewed and refreshed: - The risk title and description have been revised within the HBRR for greater clarity. - The rationale for the current risk assessment score has been updated. - Controls and Assurances have been refreshed. - Additional detail has been presented in foot notes of the HBRR entry. Action: - Implement detailed Action Plan in line with the timescales outlined within the Plan (target 31/03/26). |
| HBR 104 | Failure to Meet Tier 1 Targets in Clinical Coding Completeness | 20 | Lead: Director of Digital The risk score remains unchanged. Update: The OCP (Organisational Change Plan) process for qualified clinical coders has been completed and re-banding taken place. Primary Procedure and Condition Coding has been signed off by IGCAG (Information Governance and Cyber Assurance Group) and Management Board. Primary Procedure coding started in September with the number of episodes coded and rate of coding showing an increase on previous months. The auto-coding model is going to be tested for implementation with neurology episodes. Further & ongoing actions: - Completion of all Actions on Audit Action Plan (target 31/10/25) - Auto-coding model in production for two specialties (target 01/11/2025) - Centralising of coding department leading to efficiencies (target 31/10/2025). |

Table 2 below lists additional risks assigned to the Committee whose risk levels do not meet the threshold currently set within the Health Board’s risk appetite. However, in line with the Board’s aspiration that thresholds could be reduced in the future, these risks are presented for information:

Table 2: HBRR risks assigned to the Committee that do not currently meet the risk appetite threshold.

| Risk Ref | Risk Title | Current Score | Executive Lead & Key Actions |
| --- | --- | --- | --- |
| HBR 27 | Digital Transformation Inability to deliver sustainable clinical services due to lack of resources to deliver sustainable Digital Transformation and services. There are insufficient resources to: - Invest in the delivery of the SBU Digital strategy - Support the growth in utilisation of existing and new digital solutions - Replace existing technology infrastructure or software at the end of its useful life. | 16 | Exec lead: Director of Digital The risk score is unchanged. Update: The forecast outturn has been presented to Director of Digital. Review of the 10-year financial plan has commenced. Ongoing action (refreshed): Review 10-year financial plan for Digital Strategy and prioritise key costs for the next 3 years. Share plan with Director of Finance for consideration and alignment to 2026/27/28/29 IMTP process (target 31/01/2026). |
| HBR 36 | Paper Record Storage Lack of a single electronic record means there is greater reliance on the provision of the paper record. If we fail to provide adequate storage facilities for paper records, then this will impact on the availability of patient records at the point of care. Quality of the paper record may also be reduced if there is poor records management in some wards. There is an increased fire risk where medical records are stored outside of the medical record libraries. | 16 | Lead: Director of Digital The risk score is unchanged. Update: All relevant records and all staff had previously been noted as moved across to Ty Samlet. Management are allowing for new process to stabilise before evaluating the benefits of new centralised unit (target 31/12/2025). |
| 105 | Significant increased cost for the replacement Pathology System LIMS If the new Laboratory Information Management (LIMS) system is not live before 31st December 2025 then there will be significant more cost across NHS Wales which could impact the Health Board’s financial plans in 2025/26 and 2026/27. Costs would have to be covered to avoid pathology losing access to the current LIMS system resulting in the inability of pathology to deliver diagnostic results and blood transfusion services across all Health Board services including emergency, acute, primary and community services. | 16 | Lead: Director of Digital This risk has been re-articulated, refreshed and re-assessed – the current risk score is now 16. It is no longer framed as a “loss of system” but as a financial risk—specifically, the cost implications of ensuring continued provision of a functioning pathology system. The programme is experiencing significant delays and defect volumes, impacting deployment timelines and operational readiness. Deployment Plan & Tranche 1 delay: The programme is structured into five tranches, with go-live dates staggered from July 2025 to March 2026. A sixth tranche (PHW/Microbiology/Cervical Screening) remains unscheduled due to unresolved middleware dependencies. Originally scheduled for mid-July, the technical go-live for Tranche 1 was deferred due to unresolved defects, including the critical trickle feed interface needed for dual running of LIMS 1.0 and 2.0. A revised dry-run is planned for late August, with go-live in early September. Defects: Approximately 160 new severity 1 and 2 defects are raised monthly. While a third have been fixed, they require retesting. Completion of UAT is contingent on resolving these defects. Dependencies and Risks: Blood Sciences must complete testing by end of August to meet the October deployment target. Significant sign-off activity is pending both locally and nationally. Actions: - Determine what additional local costs may be attracted due to extending the project from 31st December 2025 until 31st March 2026 and how these could be funded (target 31/12/25) - Continue to work in collaboration with other NHS Wales organisations to challenge supplier delivery and secure go-live dates before 31st March 2026 (target 31/03/25). |

3.3 Risks Reported to Other Committees for Information

Some of the risks allocated to this Committee for scrutiny are reported to other Committees for information. These are summarised here for information:

Table 3: Risks Reported to other Committees for Information

| HBRR Ref | Risk Detail | Current Risk Score | Committee |
| --- | --- | --- | --- |
| HBR 36 | Paper Record Storage | 16 | Quality & Safety |
| HBR 104 | Failure to Meet Tier 1 Targets in Clinical Coding Completeness | 20 | Quality & Safety |
| 105 | Significant increased cost for the replacement Pathology System LIMS | 16 | Quality & Safety |

- FINANCIAL IMPLICATIONS

This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case, they are highlighted within individual risk register entries or dedicated board/committee papers for information.

- RECOMMENDATIONS

Members are asked to:

- RECEIVE the updates to the Health Board Risk Register (HBRR) relating to risks assigned to the Committee.

- REVIEW the risk(s) and consider whether further action / assurance is required.

| Governance and Assurance |  |  |  |
| --- | --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |  |
|  | Best Value Outcomes and High Quality Care |  | ☒ |
|  | Partnerships for Care |  | ☒ |
|  | Excellent Staff |  | ☒ |
|  | Digitally Enabled Care |  | ☒ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☒ |
| Health and Care Standards |  |  |  |
| (please choose) | Staying Healthy |  | ☒ |
|  | Safe Care |  | ☒ |
|  | Effective Care |  | ☒ |
|  | Dignified Care |  | ☒ |
|  | Timely Care |  | ☒ |
|  | Individual Care |  | ☒ |
|  | Staff and Resources |  | ☒ |
| Quality, Safety and Patient Experience |  |  |  |
| Ensuring the organisation has robust risk management arrangements that ensure organisational risks are captured, assessed, monitored and managed, supports the quality, safety & experience of patients receiving care and staff working in the UHB. |  |  |  |
| Financial Implications |  |  |  |
| This report does not present any matters for decision with financial implications. There may be financial implications arising from actions required to improvement the treatment of risks entered on the HBRR. Where this is the case they are highlighted within individual risk register entries for information. |  |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |  |
| It is essential that the Board has robust arrangements in place to assess, capture and mitigate risks faced by the organisation, as failure to do so could have legal implications for the UHB. |  |  |  |
| Staffing Implications |  |  |  |
| All staff have a responsibility for promoting risk management, adhering to SBUHB policies and have a personal responsibility for patients’ safety as well as their own and colleague’s health and safety. Executive Directors/Service Group Directors are responsible for the review of their operational risks and escalation of those requiring board-level oversight SBUHB. |  |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |  |
| The HBRR sets out the framework for how SBUHB will make an assessment of existing and future emerging risks, and how it will plan to manage and prepare for those risks. |  |  |  |
| Report History |  | This report provides an update on the risk profile last reported to DDRIC in July 2025 |  |
| Appendices |  | Appendix 1 – Health Board Risk Register (HBRR) Risks Assigned to the DDRIC. |  |