Appendix 1

Digital delivery: Q2 progress report

A detailed Project Delivery Dashboard for active Digital projects in FY 2025/2026 has been developed and is detailed in Table 2 below. It tracks progress, sets out the associated RAG status and milestones for forthcoming periods. Further context relating to each of the projects listed in the delivery dashboard is also provided.

The Red Amber Green (RAG) status used within this report is set out in Table 1 below.

Table 1 – RAG Status

| Green | ON TRACK - Action progressing as planned and to agreed timelines |
| --- | --- |
| Amber | OFF TRACK - Action not progressing as planned/to original timelines, however this is manageable, and mitigating actions are in place |
| Red | OFF TRACK - Action not progressing as planned/to original timelines, there are significant issues which require escalating |

Table 2 – Digital Delivery Dashboard

| Title | RAG Status | Rationale for RAG Status |
| --- | --- | --- |
| D01 - Unscheduled and Emergency Care (UEC) Solution | Amber | The requirements of the 6 goals programme to deliver against the Welsh Emergency Care Data Set (WECDS) and the need for DHCW to develop a UEC app to address this, coupled with the contract end date of Symphony in the Minor Injuries Unit (MIU) has meant that the Health Board has had to prioritise these challenges. A strategic way forward for the Health Board is yet to be determined. |
| D02 - Pathology digital system replacement (LIMS 2.0) | Red | Cellular pathology on schedule to go live mid Nov 2025. There are concerns with the number of outstanding defects, in particular for blood sciences which require resolution prior to go live by the end March 2026. |
| D03 - Radiology digital systems replacement (RISP) | Amber | Data Migration Testing has completed, however a number of queries relating to the incorrect source of scans across Wales need to be addressed before Data Migration can commence. A joint plan has been agreed with the supplier, however issues with configuration of Radiology+ has meant that milestones have slipped and need to be reviewed. |
| D04 - Welsh Emergency Care Data Set (WECDS) UEC App Implementation | Amber | An implementation plan has been submitted to the 6 goals programme. The release of the Urgent and Emergency Care (UEC) app for local testing has been delayed from Sept to Dec 2025. |
| D05 - Patient Portal/NHS App | Green |  |
| D06 - Connecting Care (Rio Implementation across Integrated Teams) | Green |  |
| D07 - Hybrid Mail | Green |  |
| D08 - Signal | Amber | Delay in releasing v3.6 from Sept to Nov due to a number of factors: -5 urgent patches required to v3.5 - development of HEPMA alerts, late additions to requirements. - new requirements to support discharge flow programme absorbed for release with v3.6. |
| D09 - Welsh Clinical Portal - Hospital Initiated Referrals (HIR) | Amber | A Welsh Clinical Portal fix was required from Digital Health and Care Wales to enable rollout of the Hospital Initiated Referrals (HIR) functionality. |
| D10 – Digital Health Assessments | Amber | Final integration trigger went live as planned in September, however, full outcome data flow back into the Health Board is continuing to be delayed but progress is being made with the data mappings. No delivery date confirmed as of yet. |
| D11 - Welsh Nursing Care Record - Paediatrics | Green |  |
| D12 - Digital Maternity | Amber | Amber due to delays in system configuration (unplanned absence of key staff member), coupled with no agreed dates for integration with Welsh Patient Administration System (WPAS) and Welsh Birth Notification Service. However, this work has since been prioritised by DHCW. |
| D13 - e-Prescribing & Meds Management | Green |  |
| D14 - WPAS and associated services disaggregation | Green |  |
| D15 - Implement Open Eyes (Open ERS/Open EPR) | Green |  |
| D16 - Welsh Intensive Care Information System - Implementation | Green | Deliverable for Q2 was to contribute to an all-Wales strategic review for consideration by Welsh Government. SBUHB has been heavily involved in the review and await confirmation of next steps. |
| D17 - Expand Electronic Test Requesting | Amber | - Additional Cardiology costs for Cardiobase which require funding. - Elongated timelines for all 3 cardiology integrations - Celma GP Letters - issues in letter templates delaying progress |
| D18 - Systemic Anti-Cancer Therapy (SACT) | Amber | The ChemoCare (SACT) contract extension was not completed by 30 September 2025. A two-month extension has been granted to finalise negotiations, aiming for a fixed three-year term to enable NHS Wales to prepare a full tender and develop a national programme to standardise SACT regimens and protocols across Wales. |
| D19 - Outpatient Flow (In-Touch) | Amber | Resourcing constraints have prevented progress from being made, however recent recruitment of a Product Specialist has enabled readiness work for an implementation in Singleton to commence. |
| D20 - Millcare System in Sexual Health | Green |  |
| D21 - WPAS Roll out across Mental Health, Learning Disabilities and Primary Care and Therapies | Green |  |
| D22- Cyber Secure Back Ups | Green |  |
| D23 - NPT wireless equipment replacement | Amber | Prioritisation of another Delivery Action with support ending soon (D29 - Call Manager Upgrade to Cloud Voice) |
| D24 - Laptop, PC, iPad and Printer Replacement | Green |  |
| D25 - Additional Server Equipment including Storage | Green |  |
| D26 - Imprivata Rollout | Green |  |
| D27 - Implement New Core Network at Morriston & Singleton | Green |  |
| D28 - Windows 10 Removal | Green |  |
| D29 - Call Manager Upgrade to Cloud Voice | Green |  |
| D31 - Creation of a measures to be visualised in Dashboard pulling data from various systems | Green |  |
| D32- Re-banding of Coding Staff and Development of Auto-coding Software | Green |  |
| D33 - Data Literacy and Value | Green |  |
| D34 - National Data Resource (NDR) | Green |  |
| D35- Health Records Centralisation | Green |  |
| D36 - Digital Cellular Pathology | Amber |  |
| D37 - eTriage | Amber | The implementation of eTriage has been delayed due to the cost of integration to Symphony, given that the current contract ends in September 2026. Continued engagement with DHCW and the national 6 goals programme to extend the scope of the UEC app project to include integration of e-triage. |

## Additional Context to support the Project Delivery Dashboard

## Planned Care

Signal <Amber>: Version 3.6, which includes the surfacing of alerts from the Hospital Electronic Prescribing and Medicines Administration (HEPMA) system is scheduled for release in November. Delays to the release date have been experienced by the need to release fixes to v3.5, emerging HEPMA requirements identified through testing, and enhancements to support the ‘Discharge to Recover and Assess’ (D2RA) pathway, ‘Red to Green’ recording and national reporting. A change freeze is now in place to prevent future delays to the deployment of Admission, Discharge and Transfer integration in version 4.

Welsh Clinical Portal (WCP) <Amber>:

Hospital Initiated Referral (HIR) functionality has been developed in Welsh Clinical Portal (WCP) to enable the electronic sending of internal hospital referrals. All services to Neurology have been live since June and an additional 2 services (Respiratory and Urology) went live on 15th October. This will inform a wider Health Board roll out by Q4 FY2025/2026.

Colposcopy and Screening module of Welsh Clinical Portal (WCP) went live during July which replaces the legacy system CANISC. DHCW have continued to support CANISC for a minimum of 16 weeks post go live, this is expected to conclude on November 3rd.

Swansea Bay Patient Portal <Green>: A public communication campaign to promote the availability and benefits of the Swansea Bay Patient Portal (SBPP) continues. Patients are now able to access SBPP via the NHS Wales app providing a digital unified patient experience. 32,000 patients now access the patient portal via the app to support their care.  A text messaging campaign ran through September/October and had a positive impact on patient sign up, over 10,000 patients have registered during October. A new release of the NHS Wales App will include functionality to surface the receipt of GP referral by the Health Board and will notify patients of outpatient appointment date and time.  The release is scheduled for the end of October.

Hybrid Mail <AMBER>: 14 services are now live with the solution; 4 new services went live during the reporting period. The task and finish group continues to oversee the adoption of the solution across services. The Planned Care Board have accepted a proposal to accelerate the roll out of Hybrid Mail, detailed planning is underway.

Open Eyes (Electronic Patient Record (EPR)) <Green>: Open Eyes was successfully implemented across all Ophthalmic sub specialities on 8th September. Work continues to enhance and develop workflows from initial data sets. The Health Board are actively supporting Hywel Dda with their implementation readiness.

Digital Health Assessment Solution – Status: <AMBER>: 5 additional services went live this period, bringing the total to 16. All automatic form triggers linked to agreed patient activity events—such as surgical procedures, Referral to Treatment at Stage 1 and Stage 5 Waiting Lists—are now fully operational. A further 5 services are scheduled to onboard in the coming months.

- National Collaboration:

- Promptly Health Patient Portal via NHS Wales App: Implementation underway; Memorandum of Understanding (MoU) is being finalised.

- Patient Reported Outcome Measures (PROMs) Standard Operating Model (PSOM): Audit planning in progress to ensure compliance across live services.

- Welsh Patient Administration System (WPAS) Integration: Real-time integration initiated for national PROM pathways. Scoping for inclusion of local PROMs and Digital Health Assessments (DHAs) will follow.

- Local PROMs Data Standard (LPDS): mappings completed and submitted; now being converted into FHIR (Fast Healthcare Interoperability Resources) format by the National Value in Health team. Data flow into the Health Board expected in Quarter 4; interim access via manual CSV downloads.

3Ps Waiting Well National Programme – <Green> 
PROMOTING healthy lifestyles, PREVENTING deterioration, and PREPARING patients for treatment.

- Engagement: 493k patients reached via website link and QR code (140k increase since last reporting period). Website hits doubled in Sept ’25 (3,734 vs. 1,860 in Aug ‘25), likely due to the launch of the Waiting Well Health Assessment.

- Service Delivery: Fully operational since Jun ’25, the Waiting Well team offers Mon–Fri support with input from Occupational Therapist, Dietitian, Physio and Pharmacist for holistic patient optimisation.

- Health Screening Questionnaire (HSQ): Screens surgical patients for fitness. The Waiting Well team are currently collecting manually for colorectal cancer cohort; digital rollout (likely via Pro Mapp) pending confirmation.

- Waiting Well Health Assessment (WWHA) Rollout: Live in Promptly system for Gynaecology Stage 1 (2,205 patients). Expanding to priority services. Sent to newly referred patients pre-first outpatient appointment, signposting lifestyle/self-management resources. Waiting times now visible via WW website and NHS Wales App.

- Funding: Current funding ends Mar ’26. Executive SRO has requested a 12-month extension from Welsh Government to embed and evaluate the service.

Diagnostics

Laboratory Information Management System 2 <Red>:

SBUHB Cellular Pathology are scheduled to go live during November, bringing the first users in Wales onto the system. This is dependent on the preceding technical go-live going well; SBUHB are, together with other Health Boards, supporting the programme by testing the bulk data upload and trickle feed. It is also dependent on the supplier fixing defects identified during testing, so that these defects can be re-tested and closed.

Concerns remain that the level of defects is not reducing quickly enough. With full functionality for Blood Sciences not due for delivery until 16th February, and without a clear downward trajectory of open defects, determining when the system can safely pass through testing for remaining pathology disciplines is challenging.

Welsh Government have agreed to fund the £1.6m Mitigation Plan, which was constructed to fund resources until 31st December 2025. However, the Programme Board in September heard that - after the £1.6m funding has been accounted for - an additional £690k overspend is expected due to resources being extended to 31st March 2026, and heard in the October meeting that this has risen to £870k. DHCW are looking to cover these costs with DPIF underspend and they do not expect the overspend to increase past £870k in this financial year.

Swansea Bay is the only Health Board in Wales reliant on the current LIMS for Blood Transfusion, creating an additional pressure to transition to the new LIMS.

Radiology Information System Procurement <Amber>: This ambitious national programme will replace the current Radiology Information System (RIS) and Picture Archive Communication System (PACS). The Health Board is scheduled to go live in February ‘26. SBUHB are putting every resource and effort available into absorbing the impact of supplier delays but remain concerned of Philips’ ability to successfully manage their deliverables that would enable us to meet a 23rd February 2026 go-live.

The SBU current PACS contract (Fuji) has been extended to March 2027 by way of mitigation should delivery timescales slip beyond March 2026. A delayed go live has an associated benefit of reduced dual running costs alongside the Fuji contract.

Women and Children

Digital Maternity <Amber>: Following successful recruitment to the Product Specialist role, configuration of the Digital Maternity system “Badgernet” has commenced, working closely with the digital midwife. The integration requirements are being worked on nationally with DHCW.  The delivery of the required integration could pose a risk to the overall project delivery timescales.  System C have proposed a revised go-live date of 31st March2025 for Swansea Bay.

Unscheduled Care

Unscheduled Care and Emergency system <Amber>: In the context of the Ministerial Advisory Group position on investment in Electronic Records, the Health Board UEC redesign programme is looking to secure funding for a system to span UEC. However, funding is linked the wider UEC redesign business case.

Welsh Emergency Care Data Set (WECDS) <Amber>: The Health Board continues to engage with the national Welsh Emergency Care Data Set programme and a local plan to support delivery of the UEC App has been developed. Usability testing will be conducted during November with a release of the App in UAT scheduled for Dec. UAT testing will be carried out locally throughout January/February 2026. The requirements for the Minor Injuries Unit have been incorporated into the minimum viable product to ensure the UEC App will meet the needs of the service.

e-triage <Amber>: The Six Goals for Urgent and Emergency Care National Programme had confirmed funding for the FY 2025-26 to implement an e-triage system in the Minor Injuries Unit (MIU) in Neath Port Talbot hospital in the first instance. However, following a meeting with the Director of the 6 goals programme, it was agreed that due to the Optum contract expiry in September 2026, the cost of integration from Symphony (the system in use in the minor injuries unit) to the e-triage system does not make the investment worthwhile. Clarification is being sought from the national WECDS programme as to whether integration to the UEC app would be included in the minimal viable product (MVP).

Welsh Intensive Care Implementation System (WICIS) <Green>:

A national recommendation that the programme continues, subject to further detail on end system design has been submitted to Welsh Government for consideration. A strategic assessment was carried out to inform the recommendation. The assessment highlights the needs for clarity on funding and participation from all Health Boards.

The programme will progress to the discovery phase during November 2025 allowing users to observe clinical workflow functionality in a test environment. A Technical Assurance Group has been stood up with a priority on scoping the integrations required. For Swansea Bay the priority integration is to the health board’s live Hospital E-Prescribing and Medicines Administration (HEPMA).

Mental Health and Learning Disabilities

Welsh Patient Administration System (WPAS) implementation for Mental Health, Learning Disabilities, Primary Care and Therapies: <Green>: Digital and mental health services have worked collaboratively to explore the use of the Health Care Professional (HCP) module of WPAS as an interim solution for those teams who are still using paper, excel spreadsheets and access databases. Following a prioritisation exercise the HCP module was implemented in the following teams

- Single Point of Access (SPOA)- Neath Port Talbot

- Crisis Resolution Home Treatment Team

- Assessment Home Treatment Team

- Dechrau Newydd

For updates pertaining to the Rio implementation please see the Mental Health digital transformation update.

## Digital Infrastructure

Technology Refresh

<Green>:

- The new core networks at Morriston and Singleton have been implemented, and work is underway to migrate from the old core network to the new core network. This is expected to complete by the end of Q3.

- Replacement of the Singleton Hospital network by replacing the hospital network switches which provide access to computers, video surveillance systems, and medical equipment such as Computerised Tomography (CT) scanners and Magnetic Resonance Imaging (MRI) scanners. This work will commence in Q4.

- The replacement of unsupported desktop and laptop computers whilst also migrating from Windows 10 to 11 in parallel is progressing well. The migration to Windows 11 is currently at 96% of desktops and laptop computers. The remaining 4% is stalled due to technical issues with the Radiology Information System (RADIS).  SBUHB has subscribed to a paid for Microsoft Windows 10 support agreement to cover the next 12 months.

<Amber>:

- Neath Port Talbot Hospital wireless equipment replacement: Call Manager Upgrade re-planned for Q3 due to complexity of the project and engagement with a CISCO approved third party. Planned Q2 replacement of the wireless network at Neath Port Talbot Hospital will begin in Q4.

Business Intelligence (BI) <Green>: Key achievements include the launch of the next phase of the Quality and Safety Dashboard which now includes assurance and compliance metrics, the addition of Mental Health and Learning Disabilities measures in the daily and weekly health board summary reports which are sent automatically to executives. Other achievements include the Flu Vaccinations Dashboard to help support the vaccination team in monitoring flu vaccination up-take rates across Swansea Bay. The Parkinson’s admissions dashboard has been developed which shows Parkinson’s patients that have been admitted into Swansea Bay hospitals to help support medication management. Data literacy courses have continued to be delivered with circa 50 staff members attending during this period.