Appendix 1

Digital plan FY2026/27: Q2 to end of August Progress Report

A detailed Project Delivery Dashboard for active Digital projects in FY 2026/2027 has been developed and is detailed in Table 2 below. It tracks progress in Q2 up to the end of August 2026 and sets out the associated quarterly RAG status.

The Red Amber Green (RAG) status used within this report is set out in Table 1 below.

Table 1 – RAG Status

| Green | ON TRACK - Action progressing as planned and to agreed timelines |
| --- | --- |
| Amber | OFF TRACK - Action not progressing as planned/to original timelines, however this is manageable, and mitigating actions are in place |
| Red | OFF TRACK - Action not progressing as planned/to original timelines, there are significant issues which require escalating |

Table 2 – Digital Delivery Dashboard

| Report Order | Project | Q2 Milestone RAG | Q2 Rationale for RAG Status | RAG Trend |
| --- | --- | --- | --- | --- |
| 1 | UEC Solution procurement | On Track |  | ▲ Improved |
| 2 | Signal | Off Track (Amber) | Support of Optimal Hospital Flow is ongoing. Development of ADT's is complete, testing is ongoing, go live to be deferred from Sept to Oct. | ▼Deteriorated |
| 3 | WICIS | Off Track (Amber) | Awaiting Welsh Government decision on national implementation | ▬ No Change |
| 4 | LIMS 2.0 | Off Track (Red) | Micro go live in August. Blood Sciences go-live is delayed as required supplier fixes were not delivered to agreed timescales. Escalation continues while local readiness is maintained pending correction plan from supplier. | ▬ No Change |
| 5 | Diagnostic Requesting | On Track |  | ▬ No Change |
| 6 | RISP | On Track | System stabilisation work continues, with a backlog of activities from go live. Risk to Q3 milestones due to resourcing constraints within the service. | ▬ No Change |
| 7 | Digital Health Assessments |  | Integration of promptly with the NHS Wales App underway, go live end of September. | ▲ Improved |
| 8 | Digitisation of Mental Health clinic letters | Off Track (Amber) | Capacity issues in mental health. New requirements identified whilst undertaking baseline of current ways of working. | ▼Deteriorated |
| 9 | Hybrid Mail | On Track |  | ▬ No Change |
| 9 | NHS Wales App/SBPP | On Track |  | ▬ No Change |
| 10 | AI/Ambient Listening | On Track |  | ▬ No Change |
| 11 | Hospital Initiated Referrals | On Track |  | ▬ No Change |
| 12 | Validation of Waiting lists using AI | Off Track (Amber) | Awaiting feedback on initial results so logic can be improved. | ▼Deteriorated |
| 13 | Implement Paperlite Ways of Working | On Track |  | ▬ No Change |
| 14 | Digital Cellular Pathology | On Track |  | ▬ No Change |
| 15 | e-Prescribing and Meds Management | On Track |  | ▬ No Change |
| 16 | Implement ReQol (Recovery Quality of Life), part of the outcome measures framework for Wales | On Track | Seeking options to automate Phase 1 collection (inpatients, currently on paper). | ▬ No Change |
| 17 | Mental Health - Business Case for wider rollout of an EPR | On Track |  | ▬ No Change |
| 18 | Digital Maternity | On Track |  | ▬ No Change |
| 19 | PCT - Business Case for wider rollout of an EPR | On Track |  | ▬ No Change |
| 20 | Rio implementation to replace legacy systems (including WCCIS & Signal V2) | Off Track (Amber) | Virtual Wards are now live with Rio. Although good progress has been made with the migration of data from WCCIS, this remains amber due to the complexity of migration activities and the dependency of go live on the Swansea council implementation timeline. Migration of activities and progress notes requires sign off. | ▬ No Change |
| 21 | Open Eyes/ERS (Digitsation of Opthalmology) | On Track |  | ▬ No Change |
| 22 | Millcare replacement (Recommissioning) | Off Track (Amber) | Formally written to Public Health Wales to request plan going forward. Awaiting confirmation; follow up email sent. | ▬ No Change |
| 23 | Continuing Healthcare (CHC) | On Track |  | ▬ No Change |
| 24 | Laptop, PC, iPad and Printer Replacement | On Track |  | ▬ No Change |
| 25 | Replacement of Singleton LAN | On Track |  | ▬ No Change |
| 26 | Cyber Vault | On Track |  | ▬ No Change |
| 27 | Replacement of Morriston LAN | On Track |  | ▬ No Change |
| 28 | Install of Telephone System Hardware | On Track |  | ▬ No Change |
| 29 | Data warehouse and dashboards for LIMS 2.0 | On Track |  | ▬ No Change |
| 30 | Data warehouse, dashboards and submissions for Badgernet | On Track |  | ▬ No Change |
| 31 | Data warehouse, dashboards and submissions for Rio | On Track |  | ▬ No Change |
| 32 | Data warehouse, dashboards and submissions for WECDS | Off Track (Red) | The UEC business case to procure a third-party solution has been approved by PFAG. This solution will enable the Health Board to report on the new dataset. It is likely that the solution will not be available prior to March 2027 (WECDS deadline). | ▬ No Change |
| 33 | National Data Resource (NDR) | On Track |  | ▬ No Change |
| 34 | Re-banding of Coding Staff and Development of Auto-coding Software | On Track |  | ▬ No Change |
| 35 | Data Literacy and Value | On Track |  | ▬ No Change |