Agenda item: 1.5

[image: image1.jpg]


                                                       [image: image2.jpg]$5>

¥

/
0

g_
&20

=
>
-
m
A

Bwrdd lechyd Prifysgol
Bae Abertawe

Swansea Bay University
Health Board



                                  [image: image3.jpg]



Performance and Finance Committee Action Log

	Open Action

	Action No. 
	Minute Ref.
	Date
	Agreed Action
	Lead 
	Timescale
	Status 

	1. 
	76/23
	23/06/2023
	Agenda Planning 

Joint agenda planning session be arranged for the Quality and Safety and Performance and Finance committees.
	Director of Corporate Governance 
	Summer 2023
	TBC

	2. 
	44/23
	28/03/2023
	Board Effectiveness Action Plan

The budget delegation and accountability letters be circulated for assurance purposes to Committee members. 
	Director of Finance and Performance 
	July 2023 
	In progress, to be circulated to members once finalised. 



	3. 
	26/23
	23/02/2023
	Endoscopy Performance 

A deep dive report on endoscopy would be brought to the August 2023 committee.
	Chief Operating Officer
	August 2023
	To be added to the August agenda once it has been to Management Board.

	4. 
	26/23
	23/02/2023
	Neck of femur interventions

A deep dive report on neck of femur interventions would be brought to the committee.
	Deputy Chief Operating Officer
	September 2023
	To be placed on the September 2023 agenda. 

	5. 
	89/23
	27/06/2023
	Deb Lewis agreed to seek an update on the stroke pilot and circulate outside of the committee.
	Chief Operating Officer
	July 2023
	To be circulated outside of the committee. 

	6. 
	90/23
	27/06/2023
	Orthopaedics 

Follow up report on orthopaedics be brought to October 2023 committee once the theatres are up and running.
	Chief Operating Officer
	October 2023
	To be placed on the October 2023 agenda. 

	7. 
	102/23
	25/07/2023
	The high level spreadsheet which details the weekly movement of the savings position of the service groups be shared on a regular basis with independent members.
	Director of Finance and Performance
	August 2023
	To be shared with committee members moving forward. 

	8. 
	104/23
	25/07/2023
	Deb Lewis agreed to seek an update on the discharge summary position.
	Chief Operating Officer
	August 2023
	To be shared with members outside of the committee. 

	9. 
	105/23
	25/07/23
	A summary report of the key updates of the qualitative measures which aren’t usually covered in the routinely performance report.
	Director of Finance and Performance/Head of Performance 
	TBC – reported on every 6 months
	To be included in the performance report on receipt every 6-months. 

	10. 
	106/23
	25/07/2023
	Neurodevelopment

Further update on the neurodevelopment service be received at the December 2023 committee which was confirmed on the committee work programme.  
	Chief Operating Officer
	December 2023
	Placed on the work programme.  

	11. 
	107/23
	25/07/2023
	Pathology

A performance report on pathology to be brought to the October 2023 committee
	Chief Operating Officer
	October 2023
	To be placed on the October 2023 agenda. Added to the work programme.

	Closed Actions

	1.
	107/23
	25/07/23
	A spreadsheet detailing the tumour site leads to be circulated outside of the committee.
	Chief Operating Officer
	July 2023
	Completed – circulated to members on 25th July 2023.


Financial Reporting and Monitoring Final Internal Audit Report Actions

	Ref No:
	Recommendation
	Lead
	Timescales
	Update

	1. 
	The importance of signing and returning delegation letters is re-iterated to budget holders to formally recognise budget accountability
	Deputy Director of Finance
	Quarter 3 2022-23
	CLOSED - The 2023/24 Letters have been issued to all Service Group Directors and Executive Directors setting out the opening budgets, with clear timescales on returning the signed acceptance form. The document also included the Budgetary Management process agreed by PFC in April. 

Responses required in 2 weeks and follow up emails will be issued is no response received by this deadline from the DOF office. 

	2. 
	Consideration is given to assess the need to issue delegation letters to a wider group of budget holders
	Deputy Director of Finance
	Quarter 3 2022-23
	CLOSED - Actions as per point 1 above

	3. 
	FCP 6 - Budgetary Control Procedures should be updated to reflect current working practices.
	Assistant Director of Finance
	Quarter 3 2022-23
	Review started but awaiting learning from 2023/24 Audit to build in best practice.

	4. 
	Further work is undertaken to establish what support budget holders require and consider regular engagement
	Deputy Director of Finance
	2023/24
	Finance team have established a ‘Budget Is A Budget Holder’ work programme, within which this is one aspect. Programme supported by work for next 18 months.

	5. 
	We recommend a wider review of this listing is undertaken, to assess the need for this number of authorisers given the NHS Wales ‘No PO, No Pay’ policy
	Assistant Director of Finance
	Annual Process
	To be undertaken post-AMSR as this significant service change will mean a full review of signatories, with significant changes linked to other service changes following OCP on T&O, Theatres & Anaesthetics this will continue to need reviewing and refining.

	6. 
	A virements listing is maintained that captures budgetary transfers between Service Groups.
	Deputy Director of Finance
	July 2022
	CLOSED – and part of standard processes at Month End.


Performance and Finance Committee                                                                                                                                      4 | Page

