The following are highlights of the Quarter 3 achievements by area.

Information on achievements have been reported as part of the Highlight Reports provided for APOG on 6th February 2024.

UEC / Six Goals

Programme 1: Co-ordination, signposting and alternatives to admission

Heart Failure redesign: (project and associated GMO’s requires validation by VHBC Team)

Primary reporting via VBHC Team – Project covers multiple GMO’s – activity monitored as part of 6 Goals Portfolio. GMO’s monitored include:

Offer a clinic based, annual review for ALL Heart Failure patients who are correctly coded as having heart failure on GP Practice Registers: On-track (Green)

- Phased roll-out of annual reviews began 1st April 23

- 1565 patients offered an appointment and 528 patients attended appointment

Enhance & strengthen the Core Community Heart Failure Service: On-track (Green)

- Recruitment – all business case posts have been recruited

- Training with clinical competencies ongoing

- Secured clinical spaces across region to expand service

- Increased weekly clinic provision from 18 to 35 clinics per week

Maintain Diagnostic Heart Failure Hub @ Gorseinon community hospital: On-track (Green)

- See above recruitment of business case posts

Improve the quality and efficiency of diagnosis and treatment for patients admitted to hospital in SBUHB with a primary diagnosis of heart disease: On-track (Green)

- Service supporting 8 virtual wards

- Increased use of digital technology to increase efficiency

Atrial Fibrillation redesign: (project and associated GMO’s requires validation by VHBC Team)

Primary reporting via VBHC Team – Project covers multiple GMO’s – activity monitored as part of 6 Goals Portfolio. GMO’s monitored include:

Improved management of new AF patients: On-track (Green)

- Activity underway re: improved access to one stop clinics for AF by clinical professionals with specialist interest in AF. Specifically:

  - Equipment purchased – Spacelabs setting up the hardware – awaiting software update to be able to use devices (work around in place until update has been completed)

  - Digital systems in development – service launch date of the 26 of September 2023 was met

- Staff recruitment completed to provide new community based echo service for newly diagnosed AF patients

Programme 2: Integrated front door

Implement a programme in five clusters for the early detection of pre-diabetes and to deliver intervention to stop the use in Diabetic Type 2 patients in practice registers, from the 20/21 levels. On-track (Green)

- Programme delivered in 7 clusters since Sept 2023

- 31 practices are engaged with the programme. Commenced delivery in additional 1 cluster during Sept 23 (Bay Cluster)

Increased psychology presence in Primary Care clusters: On-track (Green)

- Funding sourced to take community psychology forward initially for Cwm Tawe, Bay and Upper Valleys (review performance and further develop model).

- Recruitment underway for Cwm Tawe Community Psychologist – advertisement on Trac for Cwm Tawe

Care home rapid response & optimisation of care/ trialling chest pain & falls pathways: On-track (Green) *NOTE: This project does not have a GMO (as sourced external funding outside of planning cycle) but is monitored via 6 Goals portfolio

- Project operational

- Pharmacy reviews for all residents at the agreed care homes continue to be rolled out

- Rapid response element of project operational

- Baseline data collated and compared to monthly performance data (early indications that project is having a positive impact)

Programme 3: Acute hospital flow and discharge

Implementation and embedding of SAFER, Red2Green, D2RA across all sites: On-track (Green)

- Further work taking place re; D2RA, preventing deconditioning and criteria led discharge. Patient flow team at MGH to working across SBUHB. Criteria Led Discharge launched

- Criteria Led Discharge underway

- Signal system changes underway so as to carry out reporting of all discharges (all discharges forming part of D2RA framework)

Programme 4: Integrated discharge

Extend sanctuary service provisions: On-track (Green)

- Budget sourced for capital improvements to improve the environment within the Forge Centre to extend sanctuary provisions. Activity underway in line with plans

- Recruitment of staff is progressing

- Costings re; capital improvements are higher than expected which has affected timetable but still on track to launch in January 2024

Ensure implementation and reporting of all D2RA pathways (in conjunction with SAFER roll-out) from the hospital to community with right community services in place (right-sizing infrastructure to deliver model)*: On-track (Green)

- D2RA conversations underway at ward level re; D2RA terminology used in ward rounds. D2RA data is currently only reported for the Home First service. Changes to Signal system underway which will allow recording of all data at Board Rounds (and subsequent reporting)

Implementation of a Single Point of Access/ Integrated Discharge Hub for all community services: On-track (Green)

- Model for IDH agreed and implementation to commence with target implementation of Q3. Project roll out began on 4th September with Patient Assignment Team (PAT) and ran for 4 weeks. Agreement in place to operate PAT during winter period

- Improvement project started on 4th Sept and with roll-out of Patient Assignment Team (PAT) within AMU. PAT improvement project operated for 4 weeks – PAT to be stepped up again throughout winter period (beginning 20/11/23)

In conjunction with RPB provide additional EMI beds to provide discharge to assess services: On-track (Green)

- Pilot approved in June 23 subject to ongoing review – increase in EMI capacity (8 beds) in place for 23/24.

- Pilot subject to ongoing review – pilot began June 23 (running until March 24)

Ty Olwen: Commission 4 inpatient beds: On-track (Green)

- Activity underway – 2 additional beds commissioned (12 beds in place) against target of commissioning additional 4 inpatient beds (14 total)

- Social worker recruitment underway – delayed start date

- Delayed start date of Social Worker starting coupled with requirement to review nurse staffing has prevented 2 additional beds opening this period – investigation (re finance for workforce) has been completed and noted that head room has been built in for staff for the additional 2 beds

Pathway of Care Delays (POCD) – Action plan development/ roll-out: On-track (Green) *NOTE: This project does not have a GMO (as POCD action plan developed in year) but is monitored via 6 Goals portfolio

- Action plan updated/ redeveloped and submitted to national team - plan confirmed to be satisfactory by national team

- Process in place to report delays/ data on monthly basis

- Change of POCD lead – Carol Doggett now health board lead

- POCD working group set-up with representation from LA’s, Health Board and RPB

- Action plan refresh/ re-development completed with ownership for issue allocated to appropriate person that can impact change

Mental Health & Learning Disabilities

The majority of the GMOs are progressing well and are on track.  These include:

- Improvement in 111 Press 2 response times and call rates

- Expansion of Adult Sanctuary Service into NPT

- Construction work on Seclusion Suite for Taith Newydd

- Continued successful roll out of SIGNAL, WCP & HEPMA

- Continued work on development of implementation plan for Dual Diagnosis Strategy

- Additional funding agreed for 12 months for 2 additional experts by Experience in Learning Disabilities.

- Recruitment of Business Intelligence Partner to link in with Service Group.

- CMHT Modernisation Board and work streams set up

Cancer

Cancer Services GMOs: (Divisional Lead – Adel Davies Pugh, SRO- Ceri Gimblett)

Radiotherapy:

- SABR, LIN5 (replaced 4th Linac) and 2nd CT Sim (currently the recommissioned old machine, agreed funding from SBU until 31st Mar 24)) are all functioning well in the service and are demonstrating positive outcomes on waiting times and enhanced patient care.

- SWWCC Bi monthly meetings have been established with Hywel Dda whish are assuring timelines are met for regional projects.

Haematology:

- Successful recruitment of 2 JCFs.

- 2 SCFs back out to advert and shortlisting to be completed ASAP.

- Reduction in agency spend from Feb 24 will create cost saving within the department.

- The LLMF are currently funding 1 year fixed term Physician's Associate post until November 24 which is aiding the ward.

AOS:

- 5 day acute oncology service in place at Morriston supported with 5 day Acute Oncology Haematology Assessment Unit (AOHAU) at Singleton.

- RAG rated action plane in place with teams to support the requirements against the 'Service Specification of Acute Oncology Services for the NHS in Wales'.

- Additional financial support is anticipated to support AOHAU and 7 day working

PCT led GMOs – SRO, Helen Annandale

- Joanne Horton in post as Consultant AHP for Cancer Services.

Morriston Led GMOs, Divisional Lead, Mollie Kearns

Business case for Surgical Robot in Urology agreed by BCAG/ Management Board in December 2024. Notice served to Cardiff. Use of robot will be rolled out in Urology from April 24.

Primary Care, Communities and Therapies (PCT)

- 14 out of 18 are on track with a further 3 on track for year-end recovery

Children & Young People

- The Children and Young People Programme has a total of 24 schemes which are Tier 1/Funded/Cost Neutral.

- The delivery of those schemes for Q3 are:

|  | ON TRACK - Action progressing as planned and to agreed timelines | OFF TRACK - action not progressing as planned/ to original timelines, there are significant issues which require escalating |
| --- | --- | --- |
| Cost Neutral | 11 | 2 |
| Funded | 6 | 2 |
| Tier 1 | 1 | 2 |
| Total | 18 | 6 |

18 of the 24 GMO’s are on track in quarter 3 with the main achievements to note detailed below:

- The SBUHB neonatal service has benefited from a funding uplift as a result of the phase 1 WHSSC cot capacity reconfiguration across South Wales. The formal outcome and funding have now been received. This has allowed the service to fund the posts which had already been recruited at risk (supported by Health Board), these included nursing, medical and therapy posts. Further focused work continues to deliver robust recruitment and retention strategies for nursing roles. To date, this is proving to be very successful. The service is also working with Head of Child Psychology to recruit to a Psychology post which has been lacking from the service.

- Adult services vacated Morriston Paediatric outpatient department in November 2023 which returned the paediatric outpatient department to sole paediatric use.

- The Welsh Government Neurodivergent Improvement programme has been launched. Childrens services representatives are attending meetings and there is a drive to develop a national model. In the interim, recruitment is ongoing for key substantive and interim posts to support the service.

Maternity

MAT_009- Continuity of Carer/ MAT_012 Sustainable Quality Services

The 2 OCP processes for community midwifery and the Obstetric Unit were completed in Q3 following an extended consultation period and full engagement with staff.  Implementation of the outcomes is underway and recruitment to key posts commenced.  This will support our aim of women being seen by no more than 2 midwives in the community and support us in reopening community services by redirecting staff and patients from Singleton back into the birth centre and home births.  Maternity Services Improvement and Performance Board established for oversight of all workforce changes in maternity services, and action plans.

MAT_010 – Ante Natal Clinic Review

Data collection undertaken by management trainee in preparation for the review.

Digital

- Execution of the coherent digital roll out plan to enable the digitisation of the Mental Health and Learning Disabilities service; the plan has been sequenced in such a way as to maximise the system benefits, to provide digital systems support to the areas of greatest flow pressures within the Service Group and to enable roll out of wider systems. The implementation of HEPMA was completed across all Mental Health sites.

- The Signal team have undertaken significant consultation with many user groups to comprehensively develop onboarding functionality, enabling reporting to the NHS Wales Delivery Unit, proactive patient flow management and a productive feedback loop for any patients referred to Home First.

- The implementation of HEPMA completed in NPT & Singleton hospitals.  Although the surgical rollout was challenging, it has provided invaluable learning prior to the surgical implementation in Morriston hospital during Q4.

- An invitation to tender was issued under the National ePMA multi-vendor framework during September.  Demonstrations were held with 2 potential suppliers, followed by evaluation sessions with key stakeholders during November and December. The tender evaluation is being finalised ahead of HEPMA board, CRG and Health Board approval.

- Pathology Electronic Test Requesting (ETR) uptake has reached 79% in secondary care and 89% in primary care, towards an aim of 90%. Began implementing approach to increasing uptake pathology Electronic Test Requesting (ETR) in adult outpatients, focussing on Radiology Renal initially.

- Radiology Electronic Test Requesting (ETR) reached over 2,500 requests in the month of December following go-live in the Acute Medical Unit.

- Phlebotomy Module still awaiting fix from LIMS supplier who have committed to delivering a fix, but other LIMS upgrade priorities have taken precedence.

- National Data Resource – proposal put forward to national programme on using the National Data and Analytics Platform for a proof of concept to host a limited amount of near real-time data from Signal for the Acute Medical Unit floor map. Began development of Natural Language Processing pipeline for Neurology letters. Undertook training in data exchange format standards that will underpin sharing of data between applications across Wales.

- A Blood Culture Dashboard has gone live providing regular updates on blood cultures taken within ICU to improve the quality of blood cultures taken.

- The Emergency Preparedness Resilience and Response (EPRR) dashboard has gone live showing key metrics for gold command.

- Phase 2 of the Quality and Safety Dashboard has gone live during this quarter.

- Renal went live with paperlite in Q3

- During the implementation of the new wireless infrastructure, digital services discovered some coverage issues, to remedy this more Wireless Access Points were used than originally planned, which has led to shortage.  An additional order has been placed and delivery of the extra equipment is expected by mid-February. ITU is the predominant area that remains on the old environment

Workforce

The following highlights some of the key milestones that have been delivered in Q3:

Goal 1: Planning Our Workforce

- A digital dashboard tracking the contingent medical workforce has been developed and is due to go live imminently

- The programme of work to record our funded establishment on our Electronic Staff Records (ESR) system is progressing well, with Mental Health and Learning Disabilities Service Group establishments completed in Q3

Goal 2: Attract and Recruit our Workforce

- We have continued to embed our new recruitment branding resulting in an increase in the number of hits on our website

Goal 3: Engage and Retain Our Workforce

- We have launched a new SharePoint site for managers to access Workforce policies, processes and toolkits

- We have launched a new Thinking of Leaving 6 month pilot as part of our retention plans

Goal 4: Equality, Diversity and Inclusion

- All our main (All Wales) workforce policies have been translated by the Welsh Language team and made available on the intranet

Goal 5: Health and Wellbeing

We have exceeded our Q3 targets in the number of staff trained in REACT and suicide prevention and stress awareness

Population Health

| GMO Reference | Achievements |
| --- | --- |
| POPHEALTH_001: Develop internal strategic & system leadership to agree organisational strategic priorities emerging from the PHS, to include actions as a healthcare provider; as an employer; as an anchor institution; and through our external partnerships that address the root causes leading to health inequities. | - Active engagement of independent members at Population Health and Partnerships Committee. Strategic direction agreed through Population Health & Partnerships Committee - Capability & capacity - Strategic Population Health Indicators - Local Population Health Measures - Organisational Development: Behavioural change & Health Intelligence - Anchor Institution baselining - Anti-poverty agenda - Population Health Development Board role, function and membership currently being refined as part of agile response to organisational requirements. - Scoping external partnerships to support the delivery of priorities agreed through governance processes. - Development of Population Health Strategic Indicators - Strategy & Planning: Integration of PHS within SBUHB Strategic Objectives (Strategic Objective 1: People of Swansea Bay lead healthier, equitable more equal and prosperous lives) - 24/25 R&S plan: Facilitated workshops to support SDGs to outline population health commitments - VBHC: Supported development of VBHC strategy ensuring alignment with Organisational Objectives & PHS. - Ongoing support to One Bay Way pathways redesign engagement to deliver population heath priorities. |
| POPHEALTH_002: An action plan is developed for implementing year 1 priority actions aligned to the organisational strategic priorities emerging from the PHS | - Population Health aligned with strategic objective 1: people of Swansea Bay live healthier, equitable more equal prosperous lives. - Population health priorities required for all 24/25 R&S plan submissions will enable a better understanding of the 24/25 actions for SDGs agreed through R&S plan process. |
| POPHEALTH_003: Supporting programme/project support infrastructure & capacity is established to help drive forward implementation of PHS goals/priorities and cross organisation delivery/response | - Active engagement of independent members at Population Health and Partnerships Committee. - Q3 supporting SDGs to develop local population health measures - Development of behavioural change capability and resource to support organisational development - Identification of health intelligence capability requirements to facilitate organisational development. - Population Health workshops to support 24/25 planning process. - Scoping of external partnerships to support delivery of agreed priority areas. |
| POPHEALTH_004: Health Board's internal processes & structures are adapted/developed to act as enablers to whole system/organisation thinking and acting, leading to detailed delivery plans & responses that expressly address population health challenges | - Progress made as part of ongoing developmental work programme. - Population health strategy aligned to SBUHB Strategic Objective 1 with actions to be captured through 24/25 R&S plan process. - Active engagement of independent members at Population Health and Partnerships Committee. - Development of population health strategic indicators. - Agreement to develop local population health measures reported through APOG. - Quarterly Service Reviews with SDGs on population health performance - Population Health Strategy delivery and associated GMO's represented on HBRR. |
| POPHEALTH_005: Operational delivery mechanisms are established that take account of system wide responsibility and accountability for delivery of population health outcomes | - Operational delivery remains federated through SDGs. - Progress on developing internal structures at system level, impact of these and capability development not being realised at operational level in Q3. - Proactive engagement and progress on embedding population health into SBUHB Strategic Objectives along with the development of strategic indicators. - Local population health measures process agreed and to be reported quarterly through APOG from Q4. - Leads developed to operationalise PHS in some SDGs. Work continuing to engage with SDGs that as of yet have not been responsive. |
| POPHEALTH_006: Review & develop our regional and local leadership & partnership opportunities & functions in relation to delivery of PHS priorities & where needed, agree a development programme/journey to improve ways of working leading to productive partnerships that deliver population health gain - with measurable impact on inequity | - Internally population health influencing R&S Plan Development, approach to developing strategic partnerships and VBHC offer. - Identification of potential external partnerships to support delivery of population health key workstreams. - Regional Health Protection Manager in post actively engaging partners across the region. - Supporting Strategy/Partnerships to implement Population Health practice into Strategic Partnerships work internally. |
| POPHEALTH_007: Develop a population health intelligence function and products that ensure data & intelligence led decision making. | - Scoped additional support requirements to facilitate organisational development around health intelligence. - Identification of health intelligence capability requirements to build capacity to facilitate organisational development. |
| POPHEALTH_008: Planning, service development & commissioning approaches are informed by population health intelligence & evidence based practice, with a focus on addressing drivers of health inequities. | - Planning: Integration of PHS into Strategic Objective 1: People of Swansea Bay lead healthier more equal prosperous lives. - Planning: population Health component required as a corporate component of 24/25 GMO submissions. - Population health influence at One Bay Way limited due to continued focus on service delivery, limited health intelligence capability and pathway data. - Management Board Paper - resource allocation to achieve population health gains agreed. Ongoing development around operationalising this proposal through population health governance. - Population Health supporting development of VBHC strategy and governance infrastructure. - Development of Strategic Population Health Indicators for organisation. |
| POPHEALTH_009: Public health technical expertise & function is used to embed a focus on addressing health inequities at a population level, including addressing their root causes, through programmes, strategies and partnerships internally & externally (within capacity and prioritised based on need). | - Resource constraints within public health team Q3 - Recruitment processes successful in key areas effect not felt till Q4 23/24 |
| POPHEALTH_010: Implement year 1 priorities of the AWWMP (HWHW) delivery plan and establish / develop / refine reporting processes & mechanisms with a particular focus on establishing an integrated level 2 and level 3 services for (higher risk) adults (and holistic / root causes / behavioural science approach) | - Delays in WG agreeing funding have impacted timescales. - Public Health Team have produced a governance paper to agree ownership around weight management for SBUHB as a cross cutting programme (not yet agreed). Governance issues for a pathway that cuts across service groups. Risks flagged through PCT around SDGs offering weight management services on a locality or SDG basis. Development of service specifications for the pathway components that have been agreed. - Development of weight management pathway & service specification being led by Public Health team. |
| POPHEALTH_011: Develop a Whole System Approach to healthy weight in line with the HWHW strategy through system mapping and social network analysis to better understand the causes and systems contributing to healthy weight at a population level, working at a regional level in collaboration with HDUHB. | - Recruitment completed effect not felt till Q1 24/25 - Contractual agreement with HDUHB progressing to support regional approach. Regional sub-system work planning underway |
| POPHEALTH_012: Implement year 1 priority actions within the SBUHB Tobacco Control plan with a focus on establishing a maternal smoking service and developing a HMQ in Hospital approach , alongside the continued operation and improvement of the integrated Help Me Quit smoking cessation service. | - WG Have confirmed 23/24 & 24/25 Prevention and Early Years funding for Maternal Smoking Cessation. - Development of weight tobacco control pathway & service specification being led by Public Health team. - Governance issues for a pathway that cuts across service groups. Risks flagged through PCT around SDGs offering tobacco control services on a locality or SDG basis. - Development of service specifications for the pathway components that have been agreed. |
| POPHEALTH_013: Implementation of national immunisation framework | - Regional Health Protection Manager appointed Q3. - Scoping around regional health protection underway. |