| Date | 28th January 2025 |  | Agenda Item |  |  | 5.1 |
| --- | --- | --- | --- | --- | --- | --- |
| Name of Meeting | Performance & Finance Committee |  |  |  |  |  |
| Report Title | Annual Plan 24/25 Delivery Mid-Year Review |  |  |  |  |  |
| Report Author | Ruth Tovey, Head of Strategic Planning Ffion Ansari, Head of IMTP Development & Implementation |  |  |  |  |  |
| Report Sponsor | Karen Stapleton, Deputy Director of Strategy Nerissa Vaughan, Interim Director of Strategy Deb Lewis, Chief Operating Officer |  |  |  |  |  |
| Presented by | Karen Stapleton, Deputy Director of Strategy |  |  |  |  |  |
| FOI | Open |  |  |  |  |  |
| Purpose of the Report | This paper provides the reported mid-year status of the priorities for delivery, as set out in the Health Board Annual Plan 24/25 as Goals Methods Outcomes (GMOs). |  |  |  |  |  |
| Key Issues | - The Annual Plan 24/25 lists a number of organisational priorities, in the form of Goals, Methods and Outcomes (GMOs), to be delivered by Programme Boards and Service Delivery Groups. - As part of standard Annual Plan Reporting processes, a mid-year review was undertaken in December to establish the proposed end-of-year delivery position of all GMOs. - This paper sets out the number of GMOs reporting to be. Delivery as Planned, Delivery Delayed or Will not be Delivered; Rationale is provided for those delayed or removed from the Plan. - Management Board/ P&F/ Board approved any changes to the Plan which were described in the Q2 reporting paper (November 2024). |  |  |  |  |  |
| Specific Action Required | Information | Discussion |  | Assurance | Approval |  |
|  |  |  |  | x |  |  |
| Recommendations | Members are asked to: - BE ASSURED on the Mid-Year review status of GMOs, indicating which will be delivered, delayed or not delivered at the year-end (24/25). |  |  |  |  |  |

ANNUAL PLAN 24/25 DELIVERY MID YEAR REVIEW

1. INTRODUCTION

This paper provides the reported mid-year status of the priorities for delivery, as set out in the Health Board Annual Plan 24/25 as Goals Methods Outcomes (GMOs).

2. BACKGROUND

The Health Board has a statutory duty to submit a financially balanced Integrated Medium Term Plan (IMTP) annually. The Health Board approved and submitted to WG its Annual Plan for 24/25 in March 2024. Subsequently, the Health Board resubmitted the Annual Plan for 2024-25 to WG on 31st May 2024. Whilst the Plan remained unchanged in terms of planning assumptions, the HB advised WG that further work at speciality/divisional level had been undertaken to refine the 24/25 demand and capacity profiles, leading to revised performance trajectories for several WG Key Performance Indicators (KPIs). As such, the respective Ministerial Templates and Minimum Data Set (MDS) were resubmitted as revised based on the updated trajectories set against new targets from WG.

The Annual Plan is structured in ‘systems’-based programmes of work that have key deliverables (GMOs) outlined. The responsibility for GMO operational delivery and performance sits with the Service Groups.  However, the accountability in providing direction and monitoring the delivery progress of System GMOs is via Programme Boards (or equivalent group). The Exec Lead/SROs for the system areas are set out in Table 1, below:

| System /Programme | SRO/ Exec Lead |
| --- | --- |
| Urgent & Emergency Care | Chief Operating Officer |
| Planned Care | Chief Operating Officer |
| Cancer | Executive Medical Director |
| Children and Young People | Executive Director of Nursing and Patient Experience |
| Maternity and Womens’ Health | Executive Director of Nursing and Patient Experience |
| Mental Health and Learning Disabilities | Group Service Director for Mental Health and Learning Disabilities (reporting to Chief Operating Officer) |
| Primary Care | Group Service Director for Primary, Community, and Therapies (reporting to Chief Operating Officer) |
| Workforce | Executive Director of Workforce and Organisational Development |
| Digital | Director of Digital |

The Annual Plan Oversight Group (APOG), , received an update on Q2 position from all areas on 1st October, 2024. Subsequently in November 2024, the Management Board, Performance & Finance Committee approved the proposed changes to the Plan in respect of Q2 delivery position as recommended by APOG.

3. ANNUAL PLAN 24/25 DELIVERY UPDATE

As part of standard Annual Plan Reporting processes, a mid-year review was undertaken in December to establish the proposed end-of-year delivery position of all GMOs. SROs were asked to update at the mid-year point of the Method (Action) component of the GMOs, indicating if the expected Year End Position will be;

- Delivered as per Plan;

- Delayed; or,

- Will not be delivered.

These are summarised by reporting area in Table 2 below:

| Reporting Area |  | Expected position at Year End 24/25 |
| --- | --- | --- |
| Primary Care |  | - 8 Delivered as per Plan |
| Urgent and Emergency Care |  | - 21 Delivered as per Plan - 4 Delayed - 3 Will not be delivered |
| Planned Care |  | - 25 Delivered as per Plan - 5 Delayed |
| Cancer |  | - 20 Delivered as per Plan - 1 Will not be delivered |
| Mental Health & Learning Disabilities |  | - 24 Delivered as per Plan - 6 Delayed |
| Children & Young People |  | - 20 Delivered as per Plan - 3 Delayed - 1 Will not be delivered |
| Maternity |  | - 15 Delivered as per Plan - 2 Delayed |
| Workforce |  | - 25 Delivered as per Plan |
| Digital |  | - 37 Delivered as per Plan - 2 Delayed - 2 Will not be delivered |
| Population Health/ OBW |  | - 7 Delivered as per Plan - 6 Delayed |
| OVERALL | Expected position at Year End 24/25 |  |  |
|  | - Delivery as per Plan = 201 GMOs 85% - Delayed = 29 GMOs 12% - Will not be Delivered = 7 GMOs 3% |  |  |

GMOs that will not be delivered and their rationale for non-delivery, are highlighted in table 3, below, for the awareness of the Board:

| System |  | GMO |  | Reason | Mitigation |
| --- | --- | --- | --- | --- | --- |
| UEC | UEC_001: Predictive identification of future high users of UEC - Data analysis & interpretation (demand forecasting of longer and shorter term trends to drive future portfolio activity) |  | Initial planning discussion recognised that due to current resource constraints it would be not possible take forward meaningful project in year. |  | GMO deferred to 25/26 and resource reviewed to date to confirm deliverable (build on moving into 25/26). |
|  | UEC_007: Expansion of District Nursing OOH/ SPOA: Enhance the Community Nursing Service over 24hrs to support End of Life care |  | No funding available for this GMO in 24/25 |  | GMO is closed for 24/25. Revised as per Further Faster funding proposal. Continue to roll out followed by review of activity with the outline plan of activity moving into 25/26. |
|  | UEC_012: Evaluation of current Home First discharge support and subsequent agreement / development of future intermediate bed provision (RPB & SBUHB in partnership) including Bonymaen beds |  | GMO cannot be delivered due to a lack of identified funding. |  | Home First programme board has been discontinued by the RPB. Work continuing and incorporated into the older persons group. |
| Digital | D_012: TOMS redevelopment. |  | Theatre management solution will form part of the initial Digital Strategy implementation. Theatres Board is looking at the wider theatre management processes, which will further inform the approach. |  | The Theatres Board are looking at the wider theatre management processes, which will further inform the approach. |
|  | D_021: Align the local ePMA solution to the National ePMA Framework and the recently published National Standards relating to interoperability. |  | The procurement activities for a new ePMA system were paused due to contractual limitations with the current supplier and organisation pressures in unscheduled care. |  | Removed from 24/25 GMOs. This will now be aligned to the new digital strategy |
| CYP | NPTS_070: Collaborative scoping to explore use of Advanced Practitioner posts to demonstrate prudent use of skill set, and release consultant capacity. Linked with SPOA work for Y2; there is a need to work around SPOA/Medical Workforce. |  | GMO cannot be delivered due to a lack of identified funding. |  | Further actions will be considered through planning processes |
| Cancer | NPTS_010: Develop a ring-fenced Haematology Elective Bay on Ward 11 to increase elective capacity, reduce treatment wait times and improve patient flow across Singleton and Morriston sites. |  | GMO cannot be delivered due to a lack of identified funding. |  | Paper submitted to SLT highlighting issues with Cancer Services and Ward 11. At risk financial agreement to support beds remaining open to support flow across site. |

Appendix 1 details by priority area, information relating to the following situations, for the information of the Board.

- Slides 3-11: GMOs reported as ‘off-track – red’ at the mid-year point. Despite the current ‘red’ status of these GMOs, some are still expected to be delivered by year-end. Rationale for the position of each is noted, as well as proposed revised delivery timescales, where relevant.

- Slides 12-16: GMOs reported as ‘off-track - amber’ (manageable) for consecutive quarters are highlighted. It is expected, however, that these will be delivered by Q4 24/25. Feasibility will be reviewed, in detail, in the Annual Plan Oversight Group (APOG) in February 2025.

- Slides 16-26: GMOs which are reported to be on-track or to have been ‘off-track – amber’ for only one quarter, but which it is known will not be delivered in 2024/25 due to foreseen barriers. These are described in every instance.

Members are asked to:

BE ASSURED on the Mid-Year review status of GMOs, indicating which will be delivered, delayed or not delivered at the year-end (24/25).

| Governance and Assurance |  |  |
| --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |
|  | Partnerships for Improving Health and Wellbeing |  | ☐ |
|  | Co-Production and Health Literacy |  | ☐ |
|  | Digitally Enabled Health and Wellbeing |  | ☐ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |
|  | Best Value Outcomes and High Quality Care |  | ☐ |
|  | Partnerships for Care |  | ☐ |
|  | Excellent Staff |  | ☐ |
|  | Digitally Enabled Care |  | ☐ |
|  | Outstanding Research, Innovation, Education and Learning |  | ☐ |
| Health and Care Standards |  |  |
| (please choose) | Staying Healthy |  | ☐ |
|  | Safe Care |  | ☐ |
|  | Effective Care |  | ☐ |
|  | Dignified Care |  | ☐ |
|  | Timely Care |  | ☐ |
|  | Individual Care |  | ☐ |
|  | Staff and Resources |  | ☐ |
| Quality, Safety and Patient Experience |  |  |
| No direct implications of this report, however the Plan is predicated on improving quality, safety and patient experience. |  |  |
| Financial Implications |  |  |
| No direct financial implications of this report, |  |  |
| Legal Implications (including equality and diversity assessment) |  |  |
| A Quality Impact Assessment and Equality Impact Assessment process will be part of the broader planning arrangements to ensure that service models detailed in the Plan are quality and equality/ diversity impact assessed. |  |  |
| Staffing Implications |  |  |
| No direct impact outlined in this report however there will be significant staffing implications as a result of new service models outlined in the Annual Plan – risks and implications to workforce form an integral part to planning arrangements. |  |  |
| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |  |
| The Annual Plan aims to deliver Strategic Objectives aligned to our Wellbeing Objectives through development of the Organisational Strategy. This paper sets out the alignment of the approved Health Board Wellbeing Objectives directly to the Annual Plan Deliverables. |  |  |
| Report History |  | Management Board 22nd January 2025 |
| Appendices |  | Appendix 1: Mid Year Review supporting slides |