| Meeting Date | 23rd July 2024 |  | Agenda Item |  | 3.1 |
| --- | --- | --- | --- | --- | --- |
| Report Title | Targeted Intervention Update |  |  |  |  |
| Report Author | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention |  |  |  |  |
| Report Sponsor | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention |  |  |  |  |
| Presented by | Deb Lewis, Chief Operating Officer and SRO for Targeted Intervention |  |  |  |  |
| Freedom of Information | Open |  |  |  |  |
| Purpose of the Report | To provide a summary of the Performance and Outcomes issues with services escalated to Targeted Intervention level of performance monitoring by Welsh Government; namely: - Urgent and Emergency Care (UEC) - Cancer - Planned Care - Healthcare Acquired Infections (HCAIs) - Child and Adolescent Mental Health (CAMHs) |  |  |  |  |
| Key Issues | Following the Welsh Government’s tripartite meeting in December 2023, SBUHB was put into targeted intervention for performance and outcomes in the areas noted above. A comprehensive work-programme has been put in place across the Health Board to monitor progress. This report provides an update against performance measures following the previous oversight and assurance of the programme. |  |  |  |  |
| Specific Action Required (Please choose one only) | Information | Discussion | Assurance | Approval |  |
|  | ☒ | ☐ | ☒ | ☐ |  |
| Recommendations | Members are asked to: - NOTE the monthly update in respect of performance against targeted intervention measures and de-escalation criteria. |  |  |  |  |

- INTRODUCTION

The previous and initial report described the immediate actions and longer-term proposals being developed and implemented in response to escalated performance monitoring arrangements by Wales Government. The report provided an update on the operational programme to manage the delivery of improved performance and outcomes for services under targeted intervention, namely:

- Urgent and Emergency Care (UEC)

- Cancer

- Planned Care

- Healthcare Acquired Infections (HCAIs)

- Child and Adolescent Mental Health (CAMHs)

At the time of writing this report, no further, formal meetings have taken place between the HB and WG since the previous update.  The next scheduled meeting in Tuesday 19th June and the slide pack developed for that meeting is being presented to Management Board today.

- BACKGROUND

Following Welsh Government’s tripartite meeting in December 2023, the Health Board was notified of an escalation of performance monitoring for performance and outcomes from enhanced monitoring to targeted intervention.  The services noted above were specifically included in that escalation.  On 12th April 2024, the HB had its inception meeting with WG colleagues and on 24th April the first quarterly meeting was held with the Chief Executive of NHS Wales.  It is anticipated that the quarterly meeting will subsequently alternate with formal Joint Executive Team (JET) meetings.  Monthly review meetings will be held with WG officers.  The Chief Operating Officer has been given the function of SRO for targeted invention and each work programme is supported by senior management and clinical leads.

The escalation is managed formally via an escalation framework, which is attached for information.  For services to move from targeted intervention back to enhanced monitoring, a set of de-escalation criteria are to be met and maintained for at least three months.  The measures are noted below:

Cancer

- 60% performance maintained for 3 months against the SCP target.

Planned Care

- 100% of open outpatient pathways to be waiting less than 52 weeks and maintained for 3 months.

- 100% of open pathways to be waiting less than 104 weeks and maintained for 3 months.

- 80% of open pathways to be waiting less than 52 weeks and maintained for 3 months.

- 15% reduction in the number of patients delayed by 100% for their follow up appointment in three consecutive months and maintained for 3 months (Based on the November 2023 baseline.)

- 65% R1 ophthalmology patient pathways to be waiting within or no longer than 25% of their target date for an outpatient appointment and maintained for 3 months.

- 80% of patients waiting for a diagnostic test to be waiting less than 8 weeks and maintained for 3 months.

- 80% of patients waiting for a diagnostic endoscopy to be waiting less than 8 weeks and maintained for 3 months.

- 80% of patients waiting for a NOUS and non-cardiac MRI to be waiting less than 8 weeks and maintained for 3 months.

- 85% of patients waiting for therapies to be waiting less than 14 weeks and maintained for 3 months.

- Assessment of health board response and handling of concerns, complaints, incidents and patient experience feedback related to planned care.

- Improving ratings from patient experience surveys and evidence of use of Datix and CIVICA data to inform quality improvement processes and the experience of patients and their families.

Urgent and Emergency Care

- A continuous reduction of ambulance handovers over an hour of at least 11% in three consecutive months and maintained for 3 months (Based on quarter 2 and 3 2023 baseline).

- Continuous improvement towards no more than 7% of patients waiting over 12 hours at each individual site and across the health board.

- Median time from arrival at an emergency department to assessment by a clinical decision maker should not exceed 60 minutes.

- A continuous reduction in delayed pathways of care of 5% for three consecutive months and then maintained for three months (based on Oct-Dec 23 baseline).

- Assessment of health board response and handling of concerns, complaints, incidents and patient experience feedback related to planned care.

- Assessment of declared BCIs, including reasons why, actions taken, and lessons learnt.

- Improving ratings from patient experience surveys and evidence of use of Datix and CIVICA data to inform quality improvement processes and the experience of patients and their families.

CAMHS

- 80% of LPMHSS mental health assessments undertaken within 28 days from the date of receipt of referral.

- 65% of therapeutic interventions started within 28 days following an assessment by LPMHSS.

- 80% of HB residents in receipt of secondary mental health services who have a valid care and treatment plan.

HCAI Improvements

- Stabilisation of the increased trajectory of cases of HCAI and evidence of continuous improvement accompanied by a strong QI approach and plan that has oversight and monitoring by board Quality Safety Committee and Board.

- The health board to have a clear improvement plan based on a root cause analysis to address the issue of hospital onset HCAIs.

- C-Diff: reduce the number of hospital onset infections by 40% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 10 cases to no more than 6 per month)

- Staph aureus: reduce the number of hospital onset infections by 25% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 4 cases to no more than 3 per month)

- E-coli: reduce the number of hospital onset infections by 20% and maintain for 3 months (from a baseline of the average number of cases in quarter 3 of 5 cases to no more than 4 per month)

- Klebsiella: reduce the number of hospital onset infections by 10% and maintain for 3 months based on 2017/18 figures (baseline – 54 cases in 2017/18, reduce to average of at most 4 per month)

The accompanying slide deck gives an update on the HB’s most recent performance against the de-escalation criteria noted above.

Recommendation

Members are asked to:

- NOTE the monthly update in respect of performance against targeted intervention measures and de-escalation criteria.

| Governance and Assurance |  |  |
| --- | --- | --- |
| Link to Enabling Objectives (please choose) | Supporting better health and wellbeing by actively promoting and empowering people to live well in resilient communities |  |
|  | Partnerships for Improving Health and Wellbeing | ☐ |
|  | Co-Production and Health Literacy | ☐ |
|  | Digitally Enabled Health and Wellbeing | ☒ |
|  | Deliver better care through excellent health and care services achieving the outcomes that matter most to people |  |
|  | Best Value Outcomes and High Quality Care | ☒ |
|  | Partnerships for Care | ☒ |
|  | Excellent Staff | ☐ |
|  | Digitally Enabled Care | ☐ |
|  | Outstanding Research, Innovation, Education and Learning | ☐ |
| Health and Care Standards |  |  |
| (please choose) | Staying Healthy | ☐ |
|  | Safe Care | ☒ |
|  | Effective Care | ☒ |
|  | Dignified Care | ☐ |
|  | Timely Care | ☒ |
|  | Individual Care | ☐ |
|  | Staff and Resources | ☒ |
| Quality, Safety and Patient Experience |  |  |

Outlined within the body of the paper but in summary considerable backlog of patients awaiting a diagnostic and treatment services across a range of services. Issues of harm in relation to high levels of HCAIs noted.

Financial Implications

Funding not yet agreed for 24/25

Legal Implications (including equality and diversity assessment)

Delay to diagnosis and treatment potential.in service delivery

Staffing Implications

Additional support staffing required to deliver the programme

| Long Term Implications (including the impact of the Well-being of Future Generations (Wales) Act 2015) |  |
| --- | --- |
| Report History | First comprehensive update presented. |
| Appendices | - Resource Section of Admin Control |